## SAG Activity Record
SAG Activity Record
TASK | AGENCY OR INSTITUTION | PRIMARY CONTACT | RECIPIENT | START DATE |  | DEADLINE | COMPLETION DATE | DURATION (days) | STATUS | NOTES
Order of Abatement | CARB |  | Parks | 2018-04-30 |  | na | 2018-04-30 | 1 | na
SAG Formation and Operations | SAG | William Nickling | na | 2018-07-01 |  | 2018-07-01 | 2019-02-25 | 239 | na
SAG (fall meeting) | SAG | William Nickling | Parks | 2018-10-18 |  | na | 2018-10-19 | 2 | Complete | Work on development of 6 month plan. SAG members advised to suspend activities until contracts are approved.
PMRP (Preliminary Concept) | Parks + Mig | Dan Canfield , Chris Dugan | APCD + SAG | 2018-10-19 | * | 2019-02-01 | 2019-02-01 | 105 | Complete
PMRP Plan - attachment #8 | Parks + Mig | Dan Canfield , Chris Dugan | APCD + SAG | 2019-02-21 | * | 2019-02-21 | 2019-02-22 | 1 | Complete
SAG (winter meeting) |  |  |  | 2019-02-07 |  |  | 2019-02-08 | 2 | Complete | Meeting to review PMRP document. Final document wth workplan not provided.
SAG report to APCD | SAG | William Nickling | APCD, Gary Willey | 2019-02-11 |  | 2019-02-25 | 2019-02-25 | 14 | In Progress
CONTRACTS |  |  |  | START DATE |  | DEADLINE | COMPLETION DATE | EXTENDED TIME (weeks) | STATUS
| Nickling Environmental (NE) | William Nickling |  | 2018-07-19 | ** | 2018-10-19 | Incomplete | -17.7143 | Overdue | * Date assigned to fall meeting of SAG
| Arizona State University (ASU) | Ian Walker |  | 2018-07-19 | ** | 2018-10-19 | Incomplete | -17.7143 | Overdue | ** Start date assigned to first organizational meeting of SAG and the end date to the second meeting
| Cal Poly (CP) | Mike Bush |  | 2018-07-19 | ** | 2018-10-19 | Incomplete | -17.7143 | Overdue
| Desert Research Institute (DRI) | Jack Gillies |  | 2018-07-19 | ** | 2018-10-19 | Incomplete | -17.7143 | Overdue
| Independent | Carla Scheidlinger |  | 2018-07-19 | ** | 2018-10-19 | Incomplete | -17.7143 | Overdue
| Independent | Raleigh Martin |  | 2018-07-19 | ** | 2018-10-19 | Incomplete | -17.7143 | Overdue
[7 empty] | Today's date: | 2019-02-20

## Evaluation Metrics
PMRP EVALUATION METRICS - ANNUAL RECORD
OUTCOME METRICS | Unit | Target | Reporting Period |  | Duration | Comments
Emission reduction: |  |  | START | END
Reduction in the maximum 24-hour PM10 baseline emissions (initial 4-year goal: 50%) | % | 50
Meteorological Monitoring
Changes in annual and average high wind day mean 24-hr PM10 by station | µg m-3
Foredune Restoration:
Annual survival rate of plants | %
Increase in area covered by live plants | Acres, ha
Net change in foredune sand volume | m3
Change in the number of hummocks formed | %
Change in rugosity (topographical variability) of the foredune area | m/m
Increase in silhouette profile area of restored foredune | m3
Backdune Stabilization:
Annual survival rate of plants | %
Planted areas buried by drifting sand | Acres, Coordinates
Fractions of average wind fence profile areas protruding above sand surface by area
Saltation Monitoring
Changes in annual and average high wind day fluxes by station | kg m-1 h-1
Mean sand flux reduction for each control area | kg m-1 h-1
PERFORMANCE METRICS | Unit | Target | Reporting Period |  | Duration | Comments
Foredune Restoration:
Area planted to foster natural foredune restoration | Acres, ha
Area planted per average day | Acres, ha
Plant Density | #/Acre, #/ha
Increase in area covered by plants | %
Frequency of plant inspection and viability monitoring
Annual budget approved for foredune development (supplies, contracts, personnel) | USD
Backdune Stabilization:
Number of acres planted annually to stabilize backdunes | Acres, ha
Number of acres planted per average day | Acres, ha
Plant Density | #/Acre, #/ha
Average quantify of mulch and fertilizer applied per acre | Tonnes
Number and locations of acres replanted annually to maintain backdune stability
Average number of plants per acre replanted | #/Acrea
Frequency of plant inspection and viability monitoring
Area stabilized by installation of roughness elements (straw bales or wind fencing) | Acres, ha
Average area stabilized per day by straw bales or wind fencing | Acres, ha
Average number of straw bales per acre installed | #/Acre, #/ha
Fractions of average straw bale profile areas protruding above sand surface by area
Length of wind fencing installed annually | Km
Length of wind fencing installed per average day | Km/day
Wind fence spacing and average length of wind fencing installed per acre | Km/ha
Fractions of average wind fence profile areas protruding above sand surface by area | m2/ha
Annual budgets approved for backdune stabilization by planting, straw bales placement, and wind fencing installation (supplies, contracts, personnel) | USD
Plant Cultivation:
Quantities of native seed harvested annually by species | Kg
Numbers of plants by species cultivated annually for initial and replacement planting
At odsvra facilities
At calpoly facilities
By private growers
Annual budget approved for plant cultivation at each facility type (supplies, personnel, contracts) | USD
Saltation Monitoring
Number of saltation monitoring stations operated in riding and downwind areas |  | 10
Frequency of saltation monitor height check, readjustment, and sample collection |  | Jack?
Meteorological Monitoring
Number of meteorological monitoring stations operated in riding, downwind, and adjacent areas |  | 10
General locations of monitoring stations and sodar installation |  | TBD
Data capture rate by station |  | hourly
Frequency of station inspection and calibration check |  | Jack?
Annual budget approved for meteorological monitoring (equipment, supplies, and personnel) | USD
Remote sensing
Sampling frequency for LIDAR survey of the foredune area |  | annual
Sampling frequency for UAS survey of the foredune area |  | semi-annual
Annual budget approved for aerial surveying (contracts) | USD
PI-SWERL Emissivity Monitoring
Frequency of PI-SWERL traverses |  | annual
Total number of test points |  | 300
Annual budget approved for PI-SWERL monitoring (contracts, support personnel) | USD
Metrics from Ian's Section 7
PI-SWERL testing of non-riding and riding surfaces
PSD analyses of non-riding and riding surfaces
PSD analyses of vertical profiles of undisturbed and disturbed sand deposits
Laser diffraction PSD and SEM testing of non-riding and riding surfaces to determine dust grain morphology
PM10 monitoring at meteorological towers
PM10 monitoring at a downwind array of sites between APCD stations
Baseline DEM and orthophoto mosaic of foredune area and reference Oso Flaco site by UAS and SfM photogrammetry
Biennial vegetation health surveys by UAS (red spectral band) for assessing vegetation cover and health, sedimentation patterns, and volumetric changes
Meteorological, PM10 (particle profilter), and Sensit stations transecting new foredune
Formation of incipient (nebkha) dunes, blowouts, deflation surfaces, transverse or parabolic dune monitoring from UAS datasets
Increasing geomorphic diversity
Distribution, species assemblage, survivorship, and general health of vegetation in foredune restoration area by 5-band sensor array on UAS biennial surveys
Development of monitoring methods for quantifying spatial extent and gradient of boundary layer disruption (wind shielding) behind restored foredune

## Modelling
PMX MODELLING
TASK | AGENCY OR INSTITUTION | CONTACT | START DATE | END DATE | DURATION (weeks) | STATUS | NOTES
Model Selection and Approval | DRI + CARB | Jack Gillies, Earle Withycombe | 2018-07-18 | 2018-10-19 | 13.2857 | Complete
Model Calibration and Simulation for 2013 | DRI + APCD | Jack Gillies | 2016-01-01 | 2019-02-01 | 161 | Complete
Preliminary Sensitivity Analysis | DRI | Jack Gillies | 2017-01-01 | 2019-02-01 | 108.7143 | Complete
Update model inputs (e.g., Emission grid, DEM) | DRI | Jack Gillies | 2019-09-30 | 2019-12-31 | 13.1429
Additional Senstivity Analysis (e.g., 3 m vs 10 m winds) | DRI | Jack Gillies | 2019-06-01 | 2019-08-31 | 13
Model Improvements (e.g., improved downscaling, wind reanalysis assimilation ) | DRI | Jack Gillies | 2019-06-01 | 2019-12-31 | 30.4286
Annual dust climatology (2019 winds and updated emisison grid) | DRI | Jack Gillies | 2019-12-01 | 2020-03-01 | 13
Annual Evaluation of Control Effectiveness on Mass Emissions | DRI | Jack Gillies | 2019-12-01 | 2020-03-01 | 13
Annual Evaluation of Control Effectiveness on PM10 at selected receptor(s) | DRI | Jack Gillies | 2019-12-01 | 2020-03-01 | 13

## Mitigation
MITIGATION - TYPICAL ANNUAL CYCLE BASED ON 2018-2019
TASK | AGENCY OR INSTITUTION | PRIMARY CONTACT | FOREDUNE ACREAGE (Acres) | BACKDUNE ACREAGE (Acres) | START DATE | END DATE | DURATION (Days) | TIME REMAINING (Weeks) | STATUS | Notes
[7 empty] | Today's Date >> | 2019-02-20
YEAR 1
ROUGNESS ELEMENTS (fencing +/or straw bales) | Parks | Ronnie Glick | ? | ? | 2019-02-01 | 2019-03-01 | 28 | 1.2857 | In Progress
VEGETATION
Seed Collection | CalPoly, Parks | Mike, Carla and Ronnie |  |  | 2019-06-01 | 2019-10-01 | 122 | 31.8571 | Complete
Seedling Cultivation (Greenhouse) | CalPoly, Parks, Private | Mike, Carla and Ronnie |  |  | 2019-09-01 | 2019-12-01 | 91 | 40.5714 | Complete
Planting | CalPoly, Parks | Mike, Carla and Ronnie | ? | ? | 2019-12-01 | 2020-02-01 | 62 | 49.4286 | Complete
Vegetation Survey | CalPoly | Mike and Carla | TBD | TBD | 2019-08-01 | 2019-08-30 | 29 | 27.2857 | Pending | Establish survival/growth rates from previous year
REDUCTION IN RIDER ACCESS (Day Permits) | Parks | Dan Canfield |  |  | 2019-04-01 | 2019-07-01 | 91 | na | As Required | May be needed if other benchmarks not met. Contingent on wind conditions.
SOUTHERN RELOCATION OF CAMPGROUND AREAS | Parks | Dan Canfield |  |  | na | na |  |  | Under Advisement | Long term plan

## Monitoring
MONITORING
TASK | AGENCY OR INSTITUTION | CONTACT | FREQUENCY | START DATE | END DATE | PERIOD (Days) | NUMBER | Metric | STATUS | NOTES
YEAR 1
METEORLOGICAL
SODAR Installation | ASU | Ian Walker | Once | 2019-05-01 | 2019-06-01 | 31 | 1 | < Stations | Pending Contract | Waiting on site confirmation
SODAR Monitoring | ASU | Ian Walker | Hourly | 2019-06-01 | 2019-12-31 | 213 |  |  | Pending Contract | Waiting on Parks to contract ASU
Met Network Installation | DRI/Nickling Env | Gillies+ Nickling | Once | 2019-05-01 | 2019-06-01 | 31 | 10 |  | Pending Contract | Waiting on Parks to place purchase order
Met Network Monitoring | DRI/Nickling Env | Gillies+ Nickling | Hourly | 2019-05-01 | 2019-12-31 | 244 |  |  |  | Through Parks contract with DRI
REMOTE SENSING
LIDAR | ASU | Ian Walker | Annual | 2019-04-01 | 2019-05-01 | 30 | 1 | < Tansects | Pending Contract | Pending approval from Parks
UAS | ASU | Ian Walker | Semi-Annual | 2019-04-01 | 2019-05-01 | 30 | 1 |  | Pending Contract | Pending approval from Parks
| ASU | Ian Walker |  | 2019-09-01 | 2019-10-01 | 30 | 1 |  | Pending Contract | Pending approval from Parks
SURFACE/PARTICLE PROPERTIES
Emissivity: PI-SWERL | DRI/Nickling Env | Gillies+ Nickling | Annual | 2019-05-01 | 2019-06-01 | 31 | 300 | < Plots | Pending Contract | Planning Complete
Particle analyses | Nickling Env/Trent | Nickling + McKenna | Annual | 2019-09-01 | 2019-12-01 | 91 | 300 | < Samples | Pending Contract | Waiting on Parks to contract Nickling Emv
Mass transport rate: Sand traps | DRI/Nickling Env | Gillies+ Nickling | By transpot event | 2019-05-01 | 2019-12-31 | 244 | >100 | < Stations | Pending Contract | A combination of control effectiveness montioring and colocated with Met and PM stations