## Overview
Construction Delay Log Template for EOT Claims
Arbitration-ready delay log pre-formatted for Indian construction contracts (CPWD Clause 2.5, FIDIC Sub-Clause 20.1). Includes 28-day notice deadline calculator, contract clause mapping, cost linkage fields for RA Bill reconciliation, and concurrent delay apportionment tracking.
- Pre-formatted for CPWD 2014 Clause 2.5 and FIDIC 1999/2017 Sub-Clauses 20.1, 8.4, 4.12, and 19.1
- Includes automatic 28-day deadline calculator from 'Date of Awareness' field
- Cost linkage column allows direct reference to RA Bill items for quantum substantiation
- Concurrent delay fields support apportionment analysis required by Indian arbitration tribunals
- Compatible with Superwise digital hindrance log for import/export
- Preserve this log for minimum 12 years per Indian Limitation Act for construction contracts

## Delay Log
Delay Log Register
Event Ref No | Date of Event (Start) | Date of Event (End) | Date of Awareness | Notice Deadline (28 Days) | Notice Date Sent | Notice Ref No | Contract Clause | Delay Category | Factual Description | Affected BOQ Items/Activities | Impact Start Date | Impact End Date | Duration Claimed (Days) | Concurrent Delays (Y/N) | Concurrent Delay Details | Mitigation Actions Taken | Cost Impact (INR) | RA Bill Link/Ref | Photo Evidence Refs | Supporting Documents | Status | Engineer Response
DEL-2024-001 | 15-Mar-2024 | 18-Mar-2024 | 15-Mar-2024 | 12-Apr-2024 | 16-Mar-2024 | NT-001/24 | CPWD 2.5 / FIDIC 8.4 | Force Majeure | Heavy rainfall 85mm prevented external plastering at Block A Level 2. IMD records confirm. Work resumed after 3-day site drying period per safety protocol. | Ext Plaster Block A L2 (BOQ Item 12.3) | 15-Mar-2024 | 18-Mar-2024 | 3 | N | - | Covered fresh plaster with tarpaulin; redeployed labour to internal works | 45000 | RA-12 Labour idle charges | IMG_1503-1505 | IMD Weather Report, Site Diary p.45 | Notice Accepted | EOT granted 3 days vide letter dt 25-Mar
DEL-2024-002 | 10-Mar-2024 | 25-Mar-2024 | 10-Mar-2024 | 07-Apr-2024 | 12-Mar-2024 | NT-002/24 | CPWD 2.5 (i) | Employer Delay | Delayed approval of revised GFC drawings for Block A electrical works. Submitted 01-Mar, approved 25-Mar. 15 days delay vs 7-day contractual turnaround. | Electrical 1st Fix Block A (Act EL-04) | 10-Mar-2024 | 25-Mar-2024 | 15 | Y | Labour shortage 18-20 Mar (contractor risk) | Chased Engineer via email on 08, 10, 12 Mar; redeployed to Block B | 125000 | RA-13 Extended site establishment | Email screenshots dt 08,10,12 Mar, Approval letter dt 25-Mar | Drawing submission register, Correspondence file | Claimed | Pending determination
DEL-2024-003 | 05-Apr-2024 | 20-Apr-2024 | 05-Apr-2024 | 03-May-2024 |  |  | FIDIC 4.12 | Unforeseeable Conditions | Encountered hard rock at 2.5m depth where soil survey indicated clay. Required rock breaking equipment. Unforeseeable per pre-tender geo report. | Foundation Excavation Zone C (Act EX-08) | 05-Apr-2024 | 20-Apr-2024 | 15 | N | - | Engaged rock breaker on emergency hire; revised sequence to work Area D first | 280000 | RA-14 Additional excavation costs | Geo report pp12-15, Rock photos IMG_1801-1810, Expert assessment | Pre-tender survey, Revised method statement | Notice Sent | Awaiting Engineer inspection
DEL-2024-004 | 01-May-2024 | 10-May-2024 | 01-May-2024 | 29-May-2024 | 02-May-2024 | NT-004/24 | CPWD 2.5 (iii) | Third Party | Utility diversion delayed by MSEDCL. Scheduled completion 30-Apr, actual clearance 10-May. Affected road and drainage works. | External Drainage Line 3 (Act DR-12) | 01-May-2024 | 10-May-2024 | 10 | Y | Material delivery delayed 02-03 May (contractor risk) | Attended daily coordination meetings; diverted work to Zone 2 | 85000 | RA-15 Idle equipment charges | MSEDCL letter dt 25-Apr, Minutes of coordination meetings | Utility diversion schedule | Notice Accepted | EOT granted 7 days (net after apportionment)
Notice Deadline auto-calculates as Date of Awareness + 28 days. Send notice before this date to comply with CPWD/FIDIC requirements.
Contract Clause: Reference specific clause (CPWD 2.5, FIDIC 20.1/8.4/4.12/19.1) for each delay type.
Concurrent Delays: Mark 'Y' if contractor-caused delays overlap. Document separately to support apportionment analysis.
Cost Impact: Link directly to RA Bill line items or separate expense vouchers for arbitration-ready quantum proof.
Photo Evidence: Use mobile apps with GPS/timestamp embedding. Format: IMG_#### or reference photo log.
Status options: Identified, Notice Sent, Detailed Claim Submitted, Approved, Rejected, Under Arbitration

## Email Templates
Email Templates
Template Type | Subject Line | Body Content | When to Use | Attachments Required
Initial Notice (28-Day) | Delay Event Notice - [Project Name] - Event Ref: [XXX] | Dear [Engineer-in-Charge], As per Clause [2.5/20.1] of the Agreement dated [Date], we formally notify you of a delay event occurring on [Date]: Event: [Factual description] Affected Works: [Specific BOQ items/Activities] Expected Impact: [X] days delay to the critical path This notice is issued within the contractual 28-day period. We will submit detailed particulars of extension and cost impact within the time stipulated in the contract. Please acknowledge receipt. Regards, [Authorized Signatory] [Contractor Name] | Within 28 days of becoming aware of delay event | Preliminary event photos, Site diary extract
Detailed Claim | Detailed EOT Claim - [Event Ref] - [X] Days Extension Sought | Dear [Engineer-in-Charge], Pursuant to our notice dated [Date] (Ref: [XXX]), we submit detailed particulars: Event Chronology: [Dates and facts] Contract Basis: Clauses [X], [Y] Schedule Analysis: [Critical path impact - attach TIA] Cost Impact: Rs. [Amount] (detailed calculation attached) Mitigation: [Steps taken to minimize delay] Attachments: Delay log extract, photographs, correspondence, schedule analysis. We request your determination within [XX] days as per Clause [Z]. Regards, [Authorized Signatory] | After notice period, with full documentation | Delay Log extract, TIA/Schedule analysis, Cost calculations, Photos
Follow-up/Chasing | Reminder: Pending Determination of EOT Claim [Ref: XXX] | Dear [Engineer-in-Charge], We refer to our EOT claim submitted on [Date] (Ref: [XXX]). As [X] days have elapsed without determination, we request urgent review to avoid further project disruption and cost escalation. Please confirm receipt and expected determination date. Regards, [Authorized Signatory] | When engineer exceeds contractual determination period | Previous correspondence trail
Copy subject lines exactly as written to ensure tracking
Always send via email with read receipt, follow with RPAD for critical claims
Replace bracketed text [ ] with project-specific details before sending