## Overview
Document Control Starter Pack for Indian Construction Projects
Complete implementation toolkit containing folder structure templates, naming convention guide, pre-construction document index, and monthly audit checklist for CPWD/PWD/NHAI projects.

## Folder Structure
Project Folder Structure Template
Folder Level | Folder Name | Contents Description | Responsible Role | Retention Period
1 | 00_CONTRACT | Agreement, LOA, BGs, Insurance | Contracts Manager | 10 years
2 | 01_Agreement_and_LOA | Signed contract, amendments, letter of acceptance | Contracts Manager | 10 years
2 | 02_Bank_Guarantees | Performance BG, Advance BG, retention copies | Accounts/Contracts | 10 years
1 | 01_DRAWINGS | All GFC, shop drawings, as-builts | Project Engineer | DLP + 10 years
2 | 01_Architectural_GFC | Approved architectural working drawings | Architect/Site Engineer | DLP + 10 years
2 | 02_Structural_GFC | Approved structural drawings | Structural Engineer | DLP + 10 years
2 | 99_Revision_Register | Master log of all drawing revisions | Document Controller | DLP + 10 years
1 | 02_CORRESPONDENCE | All letters, RFIs, minutes | Project Manager | 10 years
1 | 03_BILLING | MBs, RA Bills, payment certs | Billing Engineer | 8 years
1 | 04_COMPLIANCE | QC reports, safety records, labour regs | QS/Safety Officer | 5-10 years
1 | 05_CLAIMS_EVIDENCE | Delay notices, hindrance photos, EOT docs | Contracts Manager | 10 years
Replace 'Project-Code' in root folder with your actual project identifier (e.g., CPWD-2024-EM-II-123)
Create subfolders for each month (01_Jan2024, 02_Feb2024) within Billing and Correspondence folders
Maintain separate 99_ARCHIVE folders for completed packages to keep active folders clean

## Naming Conventions
Document Naming Convention Guide
Document Category | Naming Format | Example | Revision Scheme | Notes
RA Bills | RA_Bill_YYYYMMDD_RAB-XX_RevX | RA_Bill_20250115_RAB-12_Rev0.pdf | Numeric (0,1,2) | Use Rev0 for initial submission, Rev1 for resubmission after corrections
Drawings (GFC) | Discipline-DrawingNo_RevLetter | GFC-STR-001_RevD.dwg | Alphabetic (A,B,C) | Never use 'Final' or 'Latest' - always specify revision letter
Correspondence Inward | INW_YYYYMMDD_Sender_Ref_Subject | INW_20250110_PMC_045_SiteAccess.pdf | None (chronological) | INW prefix distinguishes from outward letters
Correspondence Outward | OUT_YYYYMMDD_OurRef_Recipient_Subject | OUT_20250112_CEC-234_PMC_DelayNotice.pdf | Rev1, Rev2 if amended | Keep outward register serial number in OurRef field
RFI | RFI_Project_YYYYMMDD_Sequence_Response | RFI_Metro_20250108_045_Response.pdf | Original/Response/Rev1 | Include 'Response' suffix when saving AE/PMC reply
Hindrance Photos | HIND_YYYYMMDD_Location_Description | HIND_20250110_TowerA_Foundation_Waterlogging.jpg | None | Ensure camera timestamp matches filename date
MB Scans | MB_VolumeNo_PageNo_YYYYMMDD | MB_Vol3_P45_20250115.pdf | None | Volume number as per physical MB register
Test Reports | TEST_MaterialType_LabRef_Date | TEST_Steel-TMT_NABL-456_20250112.pdf | None | Include NABL lab reference for traceability
Use underscores instead of spaces to prevent URL encoding issues
Date format must be YYYYMMDD for chronological sorting
Avoid special characters: / \ : * ? " < > ¦
Maintain a master 'Filename Register' if multiple teams create documents

## Pre-Construction Index
Pre-Construction Document Index
S.No | Document Category | Document Name | Mandatory (Y/N) | Source/Provider | Due Before | Received Date | Verified By | Status
1 | Contract | Signed Agreement with all annexures | Y | Client/Owner | Mobilization |  |  | Pending
2 | Contract | Letter of Acceptance (LOA) | Y | Client/Owner | Mobilization |  |  | Pending
3 | Financial | Performance Bank Guarantee | Y | Bank/Contractor | Mobilization |  |  | Pending
4 | Financial | Advance Bank Guarantee (if applicable) | N | Bank/Contractor | 1st RA Bill |  |  | NA
5 | Insurance | Contractor's All Risk Policy | Y | Insurance Co. | Mobilization |  |  | Pending
6 | Drawings | Good-for-Construction (GFC) Drawings - Architectural | Y | PMC/Architect | Start of Work |  |  | Pending
7 | Drawings | Good-for-Construction (GFC) Drawings - Structural | Y | PMC/Structural | Start of Work |  |  | Pending
8 | Approvals | Site Handover Certificate | Y | Client/PMC | Mobilization |  |  | Pending
9 | Approvals | Construction Methodology Approval | Y | PMC/Client | Start of Work |  |  | Pending
10 | Compliance | Labour License (Form V) | Y | Labour Dept | Mobilization |  |  | Pending
Do not start billing until all 'Mandatory' contract documents are received
Store received documents in 00_CONTRACT folder immediately upon receipt
Update 'Status' column weekly during pre-construction phase

## Monthly Audit
Monthly Document Control Audit Checklist
S.No | Audit Area | Verification Point | Method | Status | Gaps Identified | Corrective Action | Target Date
1 | Folder Structure | All new documents saved in correct folders per structure | Random sample check
2 | Naming Convention | No files named 'Final', 'Latest', 'New' or with spaces | Folder scan
3 | Drawing Control | Revision register updated with latest approved drawings | Compare register vs folder
4 | Correspondence | All outward letters logged in register with acknowledgment | Register review
5 | RFI Tracking | Pending RFIs >14 days old flagged and escalated | RFI tracker review
6 | Billing Docs | Current RA bill linked to correct GFC revision | Bill vs Drawing check
7 | MB Maintenance | Measurement books sequentially numbered, no missing pages | Physical MB audit
8 | Photo Documentation | Billing photographs dated and linked to MB entries | Photo log review
9 | Backup | Digital backup completed for all critical documents | Backup log check
Conduct this audit on the first working day of each month
Status: Yes/No/NA
Maintain signed copies of completed checklists for audit trail