## Overview
Document Control Maturity Assessment Checklist
Rate your current document control setup across 8 critical dimensions to identify arbitration risks, compliance gaps, and build a business case for DMS implementation. Scoring guide included.
- Instructions: Score each of the 32 assessment items based on your current document control setup.
- 0 = Poor/Not implemented, 1 = Adequate/Partially implemented, 2 = Excellent/Fully implemented with audit trails.
- Sum all scores and check the Scoring Guide sheet to determine your risk level and next steps.

## Assessment
Document Control Maturity Assessment
Category | Item # | Assessment Criteria | Score (0-2) | Evidence / Notes
Drawing Management | 1 | Single source of truth for GFC drawings exists
Drawing Management | 2 | Superseded drawings automatically archived and marked
Drawing Management | 3 | Site teams can access latest drawings offline
Drawing Management | 4 | Drawing revision history maintained with change logs
Contract Correspondence | 1 | All formal notices stored in searchable archive
Contract Correspondence | 2 | Contractual time bars tracked automatically
Contract Correspondence | 3 | Correspondence linked to relevant BOQ items
Contract Correspondence | 4 | Export capability for arbitration bundles
Measurement & Billing | 1 | Measurement sheets digitally linked to RA Bills
Measurement & Billing | 2 | Photo evidence geotagged and timestamped
Measurement & Billing | 3 | M-book entries validated against schedule items
Measurement & Billing | 4 | Hindrance logs formally maintained with delay impact
Approval Workflows | 1 | Multi-level approval chains configured
Approval Workflows | 2 | Approval status visible to all stakeholders
Approval Workflows | 3 | Escalation rules for pending approvals
Approval Workflows | 4 | Audit trail of who approved what and when
Statutory Compliance | 1 | NOC expiry dates tracked with renewal alerts
Statutory Compliance | 2 | Building plan approval status visible to site teams
Statutory Compliance | 3 | CC/OC documentation centrally stored
Statutory Compliance | 4 | Statutory submission deadlines tracked
Access Control | 1 | Role-based document access configured
Access Control | 2 | External stakeholders (consultants, clients) have controlled access
Access Control | 3 | Mobile access with offline capability
Access Control | 4 | Document access logging enabled
Retention & Archival | 1 | 7+ year document retention policy implemented
Retention & Archival | 2 | Automated backup and disaster recovery
Retention & Archival | 3 | Document export for statutory audits
Retention & Archival | 4 | Historical project records searchable
Version Control | 1 | Document check-in/check-out enforced
Version Control | 2 | Automatic version numbering
Version Control | 3 | Conflict resolution for simultaneous edits
Version Control | 4 | Superseded version archival
Scoring: 0 = Poor (Not implemented or ad-hoc), 1 = Adequate (Partially implemented), 2 = Excellent (Fully implemented with audit trails)

## Scoring Guide
Scoring Interpretation
Total Score | Risk Level | Recommended Action
0-8 | Critical risk | Immediate DMS implementation required
9-12 | High risk | DMS implementation should be priority
13-16 | Moderate risk | Address gaps systematically
17+ | Good control | Maintain and optimize
Maximum possible score: 32 (8 categories x 4 items x 2 points)
Use this assessment to identify specific risk areas before arbitration or statutory audit