## Overview
Construction DPR Format Template Pack (India-Ready)
Complete Daily Progress Report workbook with auto-calculating fields, dropdown validations, and CPWD-compliant format. Includes entry sheets for work quantities, labor/machinery, materials, hindrances, quality checks, plus WBS coding reference and photo documentation standards.
- Auto-calculation formulas included for cumulative quantities and man-hour totals.
- Dropdown validations provided for standard labor categories, machinery IDs, and weather codes.
- Print-ready A4 layout suitable for site office filing and client submissions.
- Compatible with CPWD, NHAI, and major state PWD documentation requirements.

## Header
DPR Header Information
Field Name | Data Entry | Example/Format
Project Name |  | NHAI Highway Package-4
Contract Agreement No |  | NH-24056/CE/2024
Report Date |  | 15-Mar-2024 (Date of execution)
Shift/Working Hours |  | Day Shift (08:00-17:00)
Weather Start |  | Cloudy, 24°C
Weather End |  | Light Rain, 22°C
Site Location/Chainage |  | KM 45+200 to 46+000
Prepared By |  | Er. Rajesh Kumar, Site Engineer
Reviewed By |  | Er. Priya Sharma, Project Manager
Auto-populate from project master data if using digital tools to avoid transcription errors.

## Daily Entry
Work Executed Today (Billing Foundation)
BOQ Item Code | Description | Location/Chainage | WBS/Task ID | Unit | Quantity Today | Cumulative to Date | Balance Qty
4.1.2 | PCC M15 (1:2:4) for foundation | Block A, Axis 3-4 | BLK-A-FDN-001 | m³ | 42.5 | 850.0 | 150.0
5.3.1 | Brickwork in CM 1:6 | Block B, Wall W-12 | BLK-B-WALL-003 | m² | 25.0 | 320.0 | 80.0
3.2.1 | Excavation in soil | KM 45+200 | CH-450-EXC | m³ | 120.0 | 2400.0 | 600.0
Link every entry to WBS ID for auto-feed into Measurement Book and RA Bills.
Cumulative formulas auto-calculate from previous DPR entries.

## Daily Entry1
Labor Deployment
Category | Contractor/Subcontractor | No. of Workers | Hours Worked | Total Man-Hours
Skilled Mason | M/s ABC Contractors | 8 | 9 | 72
Unskilled Labor | M/s ABC Contractors | 15 | 9 | 135
Bar Bender | M/s XYZ Subcontractors | 4 | 8 | 32
Supervisor | M/s ABC Contractors | 2 | 9 | 18
Record by category for Labor Challan reconciliation and productivity analysis.

## Daily Entry2
Machinery Deployment
Equipment ID | Description | Operating Hours | Idle Hours | Reason for Idle Time | Fuel Consumed (L)
EX-01 | Excavator 20T | 8 | 1 | Waiting for surveyor | 45
TM-03 | Transit Mixer | 6 | 2 | Concrete pump breakdown | 28
CR-02 | Tower Crane | 9 | 0 | - | 0
Idle hours with reasons are critical for EOT claims and productivity analysis.

## Materials
Material Receipt & Consumption
Material | Unit | Received Today | Consumed Today | Balance Stock | PO/MDC Ref
Cement 43 Grade | MT | 50 | 42 | 108 | PO-2024-0847
Steel Fe 500D | MT | 20 | 18.5 | 45 | PO-2024-0912
20mm Aggregate | m³ | 0 | 85 | 120 | MDC-4451
Sand (River) | m³ | 30 | 35 | 45 | PO-2024-0899
Cross-check with Material Delivery Challans (MDCs) to prevent audit objections during final billing.

## Hindrances
Weather Conditions & Hindrances
From Time | To Time | Weather/Hindrance Type | Duration (Hrs) | Activities Affected | EOT Claimable (Y/N)
14:00 | 17:00 | Heavy Rain (Monsoon) | 3 | Concreting, Earthwork | Yes
09:00 | 11:00 | Client Delay - Utility Shifting | 2 | Excavation at KM 45+500 | Yes
13:00 | 13:30 | Material Non-Availability | 0.5 | Brickwork Block B | No
CPWD contracts define 'normal' weather. Log exceptions contemporaneously for Extension of Time (EOT) claims.

## QHSE
Quality Checks & Safety Observations
Check Type | Location/Item | Standard Reference | Result/Status | Remarks
Cube Test | Block A Foundation | IS 456 | Pass - 25.5 MPa | 7-day strength
Soil Compaction | KM 45+300 | IS 2720 | 98% MDD achieved | Plate load test pending
Safety Observation | Scaffolding Block B | IS 2750 | NC Raised | Missing guardrails corrected
Weld Inspection | Pier P-127 | AWS D1.1 | Acceptable | Radiography report attached
Document QHSE compliance to prevent quantity rejection pending verification.

## Planning
Tomorrow's Planned Work
Work Item | Location | Planned Quantity | Labor Required | Machinery Required | Dependencies
PCC M15 | Block A, Axis 5-6 | 45 m³ | 10 Masons, 20 Labor | TM-03, Pump P-01 | Steel inspection approval
Brickwork | Block B, Wall W-15 | 30 m² | 6 Masons, 12 Labor | Scaffolding S-02 | Curing of previous lift
Proactive planning allows resource conflict resolution before shift start.

## Photos
Photo Documentation Log
Photo No | Timestamp | GPS Coordinates | Description/Location | Filename
1 | 08:15 | 28.6139°N, 77.2090°E | Morning site overview KM 45+200 | IMG_20240315_081500.jpg
2 | 12:30 | 28.6142°N, 77.2095°E | PCC pouring Block A Axis 3-4 | IMG_20240315_123000.jpg
3 | 14:15 | 28.6140°N, 77.2092°E | Rain stoppage - waterlogging | IMG_20240315_141500.jpg
4 | 16:45 | 28.6142°N, 77.2095°E | Completed PCC surface finish | IMG_20240315_164500.jpg
Minimum 4-6 geo-tagged photos per DPR. NHAI projects require predefined angles. Use tamper-evident storage.

## WBS Guide
WBS Coding Reference Guide
WBS Code | Work Description | BOQ Item Ref | Unit | Schedule Task ID
BLK-A-FDN-001 | Block A Foundation Work | 4.1.2 | m³ | T-1001
BLK-B-WALL-003 | Block B Masonry Walls | 5.3.1 | m² | T-1050
CH-450-EXC | Chainage 450 Excavation | 3.2.1 | m³ | T-0800
DR-STR-001 | Drainage Structure | 6.1.5 | Nos | T-1200
Standardize WBS dictionary at project inception. Consistency prevents reconciliation errors between DPR, Schedule, and Billing.

## Checklist
Daily DPR Completion Checklist
Category | Check Item | Status (Yes/No/NA) | Remarks
Pre-Start | Project master data configured
Pre-Start | WBS dictionary standardized
Daily Entry | Header complete with date, shift, weather
Daily Entry | All work items linked to BOQ/WBS codes
Daily Entry | Quantities entered with correct units
Daily Entry | Labor deployment by category logged
Daily Entry | Machinery operating/idle hours logged
Daily Entry | Material consumption linked to MDC
Daily Entry | Hindrances logged with time impact
Daily Entry | Quality tests and safety observations noted
Daily Entry | Next day plan entered
Daily Entry | Minimum 4 geo-tagged photos attached
Billing Integration | DPR quantities reconciled with MB
Billing Integration | Cumulative totals verified
Billing Integration | Photo evidence organized by WBS
Complete this checklist before submitting DPR to prevent RA bill delays.