## Overview
Construction Drawing Folder Structure Template
CPWD/PWD-compliant folder hierarchy with naming conventions, drawing transmittal logs, revision tracking registers, as-built checklists, and RA Bill cross-reference tables. Ready for immediate use on Indian government and private construction projects.
- Customize the Project Code in cell B2 of the Naming Convention sheet to auto-populate examples across the workbook.
- Maintain the Transmittal Log in real-time; dates in this log determine delay claim validity under Indian contract law.
- Never overwrite files—create new revision folders (R0, R1, R2) to preserve arbitration evidence chains.
- Backup strategy: Maintain local server (primary), cloud with version history (secondary), and monthly offline/DVD backup (tertiary) for government projects.
- Color code physical folders to match digital: Blue=Architectural, Red=Structural, Green=MEP/Services, Yellow=Finishes.
- As-built drawings must be updated weekly during execution; waiting until project completion creates inaccurate records and settlement delays.
- Ensure drawing references in the Measurement Book exactly match the Drawing No + Revision format in this register (e.g., 'STR-S201-R1').

## 01-FOLDER-HIERARCHY
Folder Hierarchy Index
Level | Folder Path | Purpose | Access Role | Example Contents | Backup Priority
Level 1 | 00-ADMIN/ | Project administration & contracts | Project Manager | Contract agreements, MoM, approvals | Critical
Level 1 | 01-CLIENT/ | Client instructions & correspondence | Billing Engineer | Architect instructions, change orders | Critical
Level 1 | 02-DRAWINGS/ | Master drawing repository | All (read) | Discipline subfolders only | Critical
Level 1 | 05-RA-BILLS/ | Billing workflow linkage | Billing Engineer | MB entries, drawing references | Critical
Level 2 | 02-DRAWINGS/00-ARCHITECTURAL/ | Architectural drawings | Site Engineer | Tender, GFC, As-built folders | High
Level 2 | 02-DRAWINGS/01-STRUCTURAL/ | Structural drawings | Site Engineer | Foundation, column, slab layouts | High
Level 2 | 02-DRAWINGS/02-SERVICES/ | MEP & utilities | MEP Engineer | Plumbing, electrical, HVAC, fire | High
Level 3 | .../00-TENDER/ | Baseline scope drawings | Billing Engineer | R0 drawings from tender docs | Archive
Level 3 | .../01-GFC/ | Good For Construction approved | Site Engineer (view) | Stamped approved revisions only | Active
Level 3 | .../02-AS-BUILT/ | Record of actual construction | Site Engineer (edit) | Red-line marked, joint measurement | Active
Level 3 | .../03-RECORD/ | Final O&M handover docs | Document Controller | Clean drafted as-builts | Final
Level 4 | .../YYYY-MM-DD_R#/ | Specific revision container | Document Controller | PDF, DWG, transmittal memo | Version history

## 02-NAMING-CONVENTIONS
Naming Convention Cheat Sheet
Element | Format | Example | Critical Rules
Project Code | PRJ-YY-LOC-### | CPWD24-HSR-001 | Unique across all projects
Discipline Code | ARCH/STR/MEP/FIN | STR | Use CPWD standard codes only
Drawing Number | ### or A-### | S-201 | Match consultant numbering
Description | LOCATION-ELEMENT | FOOTING-LAYOUT-GRID-A-D | Hyphens only, no spaces
Date | YYYY-MM-DD | 2024-05-22 | ISO format for correct sorting
Revision | R# | R1 | R0=initial, R1=first revision
Full Filename | [CODE]_[DISC]_[NO]_[DESC]_[DATE]_[REV].pdf | CPWD24-HSR_STR_S-201_FOOTING-LAYOUT_2024-05-22_R1.pdf | Max 80 chars, no special symbols
Transmittal Ref | TRN-YYYY-MM-DD-[DISC]-### | TRN-2024-05-22-STR-001 | Links drawing to issue date
Sheet Size | SUFFIX-A0/A1/A2/A3 | _A1 | For print shop clarity

## 03-TRANSMITTAL-LOG
Drawing Transmittal Log
Transmittal No | Date Issued | Recipient | Drawing References | Purpose | Status | Received By | Arbitration Relevance
TRN-2024-03-15-ARCH-001 | 2024-03-15 | PMC/Architect | ARCH-A101-R0 to A105-R0 | Initial GFC Approval | Approved | AE Sharma | Baseline for scope
TRN-2024-05-22-STR-001 | 2024-05-22 | Structural Consultant | STR-S201-R1 | Revision for Column Grid | Approved | Er. Gupta | Delay claim evidence
TRN-2024-07-08-MEP-001 | 2024-07-08 | MEP Consultant | MEP-P301-R0 to P310-R0 | Shop Drawing Submission | Pending | - | Awaiting approval
TRN-2024-08-12-ARCH-002 | 2024-08-12 | PMC/Architect | ARCH-A101-R2 | Elevation Change | Rejected | Ar. Verma | Note comments for R3
TRN-2024-12-10-ASB-001 | 2024-12-10 | Client/AE | ALL-AS-BUILT-R0 | Final Bill Submission | Under Review | AE Sharma | Joint measurement pending

## 04-REVISION-TRACKING
Revision Tracking Register
Project Code | Discipline | Drawing No | Description | Current Rev | Date | Previous Rev | Change Description | Approved By | Billing Impact
CPWD24-HSR | ARCH | A-101 | Ground Floor Plan | R1 | 2024-05-22 | R0 | Column grid revised per client instruction | Ar. Verma | Variation claimable
CPWD24-HSR | STR | S-201 | Footing Layout | R2 | 2024-07-08 | R1 | Depth increased due to soil report | Er. Sharma | Extra item rate
CPWD24-HSR | ARCH | A-101 | Ground Floor Plan | R0 | 2024-03-15 | - | Initial GFC issue | Ar. Verma | Baseline quantity
CPWD24-HSR | MEP | P-301 | Plumbing Layout GF | R1 | 2024-06-10 | R0 | Shaft location shifted | Plumb Consultant | Coordination delay
CPWD24-HSR | STR | S-201 | Footing Layout | R0 | 2024-03-20 | - | Tender drawing baseline | N/A | Tender scope

## 05-AS-BUILT-CHECKLIST
As-Built Drawing Checklist
Item No | Verification Point | Status (Y/N/NA) | Remarks | Verified By | Date | AE Sign-off
1 | Foundation levels match actual excavation records
2 | Column positions verified with total station survey
3 | Slab levels checked with dumpy level / Auto Level
4 | MEP routing matches actual concealed work
5 | All changes from GFC marked in red ink / red-line
6 | Joint measurement conducted with Client AE
7 | Executing engineer stamp and signature affixed
8 | Cross-referenced with Measurement Book entries
9 | Ready for final bill submission (no pending items)

## 06-RA-BILL-XREF
RA Bill Cross-Reference
RA Bill Period | BOQ Item No | Description | Drawing Reference | Revision | Quantity Claimed | Drawing Date | Verification Status
April 2024 | C-01 | PCC Work | STR-S201 | R1 | 150 cum | 2024-03-15 | Verified
April 2024 | C-02 | Column Concrete | STR-S201 | R1 | 45 cum | 2024-03-15 | Verified
May 2024 | C-02 | Column Concrete | STR-S201 | R2 | 12 cum | 2024-05-22 | Pending AE check
June 2024 | A-01 | Brickwork Ground Floor | ARCH-A101 | R1 | 850 sqm | 2024-05-22 | Verified
July 2024 | M-01 | Concealed Wiring | ELEC-E105 | R0 | 1200 m | 2024-04-10 | Pending