## Overview
Construction Submittal Register Template for Indian Projects
Multi-sheet Excel workbook for tracking construction submittals across CPWD, PWD, NHAI and private projects. Includes master register with GST supplier fields, BIS/ISI certification tracking, material checklists, shop drawing approval workflows, and submittal scheduling.
- Enable filters on all header rows for easy sorting by status, supplier, or date
- Protect formula cells (Submittal No generation, date calculations) to prevent accidental deletion
- Include separate column for 'Days Overdue' with formula calculating from Required By Date
- Add validation lists for Status fields to ensure consistent data entry

## Master Register
Submittal Master Register
Submittal No | Category | Description | Specification/BOQ Ref | Supplier/Subcontractor | GSTIN | BIS/ISI Cert No | Date Submitted | Submitted To | Required By Date | Status | Approved Date | RA Bill Link | Remarks
SUB-MAT-2025-001 | Material | TMT Steel Bars Fe-500D | BOQ Item 2.1, IS 1786:2008 | Tata Steel Ltd. | 27AABCT0001C1Z5 | ISI-BIS-12345 | 15-Jan-2025 | PMC M/s ABC Consultants | 30-Jan-2025 | Approved | 28-Jan-2025 | RA Bill-3 | Approved with comment on storage
SUB-SD-2025-015 | Shop Drawing | Structural Steel Fabrication - Truss T1 | Drawing Ref: S-101 | M/s XYZ Fabricators | 29AADFX1234E1Z2 | N/A | 10-Jan-2025 | Structural Consultant | 25-Jan-2025 | Under Review |  |  | Awaiting architect coordination
SUB-MS-2025-008 | Method Statement | Deep Excavation & Shoring | Work: Basement Excavation | Self |  | N/A | 05-Jan-2025 | EIC/PMC | 20-Jan-2025 | Reviewed with Comments |  |  | Revise dewatering plan per comments
SUB-MAT-2025-042 | Material | Ceramic Wall Tiles 300x600mm | BOQ Item 8.3, IS 13712 | Kajaria Ceramics | 09AAACK1234N1Z0 | ISI-CM/L-XXXX | 20-Jan-2025 | Architect | 05-Feb-2025 | Submitted |  |  | Physical sample attached
Use formula: SUB-[TYPE]-[YEAR]-[SEQ] for Submittal No (TYPE: MAT/SD/MS/MK)
Status dropdown: Submitted, Under Review, Reviewed with Comments, Approved with Comments, Approved, Rejected
Conditional formatting: Green for Approved, Yellow for Under Review/Submitted, Red for Overdue

## Material Checklist
Material Submittal Checklist
Material Description | BIS/IS Standard | Test Certificate Required | Physical Sample Required | MSDS Required | Photo Documentation | NABL Lab Test | Make/Brand Approval | Customs Docs (Import) | Status
OPC 43 Grade Cement | IS 269:2015 | Yes | No | No | Yes (ISI mark on bags) | Yes | Yes | No | Pending
TMT Bars Fe-500D | IS 1786:2008 | Yes | No | No | Yes | Yes | Yes | No | Pending
Vitrified Tiles (Imported) | EN 14411 (or equiv) | Yes | Yes | No | Yes | No | Yes | Yes | Pending
Waterproofing Chemical | IS 9103:1999 | Yes | Yes | Yes | Yes | No | Yes | No | Pending
Electrical Wires (FR) | IS 694:2010 | Yes | Sample length | No | Yes (ISI mark) | Yes | Yes | No | Pending
Verify BIS certificate validity at www.bis.gov.in before submission
For imported materials, attach customs clearance and attested translation of manufacturer certs
Photo documentation should show ISI marks, batch numbers, and manufacturing dates

## Shop Drawings
Shop Drawing Tracker
Drawing No | Description | Revision | Submitted Date | Contractor Review | PMC Review | Architect Review | EIC Approval | Current Status | Comments Log | Delay Impact (Days)
SD-STR-001 | Column Reinforcement Details | R0 | 10-Jan-2025 | Approved 12-Jan | Approved 15-Jan | Under Review |  | Under Review | Architect requested section A-A detail | 3
SD-ARC-015 | False Ceiling Layout - 2nd Floor | R1 | 18-Jan-2025 | Approved 19-Jan | Comments 22-Jan |  |  | Reviewed with Comments | Revise grid alignment as per latest ceiling plan | 5
SD-MEP-008 | Electrical Panel Layout | R0 | 05-Jan-2025 | Approved 06-Jan | Approved 08-Jan | Approved 12-Jan | Approved 15-Jan | Approved | Approved for fabrication | 0
SD-STR-042 | Steel Staircase Detailing | R0 | 20-Jan-2025 | Submitted |  |  |  | Submitted | Awaiting structural engineer review | 0
Track review time at each level to identify bottlenecks
Maintain revision history - do not overwrite previous versions
Link delay impact to EOT claim documentation if consultant review exceeds contract period

## Schedule
Submittal Schedule
Submittal Activity | Work Start Date | Approval Required By | Submission Deadline | Review Period (Days) | Buffer Days | Responsible Party | Status | Critical Path
TMT Steel Approval | 15-Feb-2025 | 01-Feb-2025 | 15-Jan-2025 | 14 | 7 | Procurement Manager | Completed | Yes
Facade Shop Drawings | 01-Mar-2025 | 15-Feb-2025 | 01-Feb-2025 | 21 | 7 | Structural Engineer | In Progress | Yes
Tile Sample Approval | 20-Feb-2025 | 10-Feb-2025 | 27-Jan-2025 | 14 | 7 | Site Engineer | Delayed | No
Method Statement - Piling | 10-Feb-2025 | 01-Feb-2025 | 20-Jan-2025 | 10 | 5 | Project Manager | Completed | Yes
Sanitary Ware Approval | 15-Mar-2025 | 01-Mar-2025 | 15-Feb-2025 | 14 | 7 | Procurement Manager | Not Started | No
Formula: Submission Deadline = Approval Required By - Review Period - Buffer
Government projects: Use 50% buffer on review times
Critical Path items require weekly monitoring in DPRs