## Overview
Billing Milestone Tracker Template for Indian Construction Projects
A comprehensive Excel tracker for managing contractor billing milestones in CPWD/PWD and private construction projects. Includes milestone tracking, documentation checklists, cash flow projections, and delay analysis dashboards.
- Customize milestone descriptions based on your specific contract BOQ
- For infrastructure projects (roads/bridges), modify stages to reflect GSB, WMM, BM, BC layers
- Link this tracker with your Daily Progress Report (DPR) system for automatic updates
- Share 'Billing Ready %' with project manager weekly to prioritize documentation
- Retain soft copies of all referenced documents in a structured folder system

## Milestone Tracker
Milestone Tracking Register
Stage | Milestone Description | Contract Weightage (%) | Target Start Date | Target Completion Date | Actual Start Date | Actual Completion Date | Physical Progress % | Billing Ready % | RA Bill Submitted Date | Certified Date | Payment Received Date | Status | Notes
Foundation & Plinth | Excavation, PCC, RCC foundation, plinth beams | 12% |  |  |  |  | 0% | 0% |  |  |  | Not Started | Include soil test reports
Superstructure - Slab 1 | Ground floor columns, beams, slab casting | 15% |  |  |  |  | 0% | 0% |  |  |  | Not Started | Require centering checklist
Superstructure - Slab 2 | First floor RCC work completion | 12% |  |  |  |  | 0% | 0% |  |  |  | Not Started | Link to steel reconciliation
Brickwork | 50% and 100% brickwork per floor | 10% |  |  |  |  | 0% | 0% |  |  |  | Not Started | Brick test certificates required
Internal Plastering | Room-wise plaster completion | 8% |  |  |  |  | 0% | 0% |  |  |  | Not Started | Check curing records
Flooring | Tile/marble laying with approval | 10% |  |  |  |  | 0% | 0% |  |  |  | Not Started | Material approval copy attached
Electrical & Plumbing | Concealed work, fixtures, testing | 12% |  |  |  |  | 0% | 0% |  |  |  | Not Started | Test reports mandatory
External Works | Waterproofing, external plaster, services | 8% |  |  |  |  | 0% | 0% |  |  |  | Not Started | Warranty docs required
Final Completion | Snagging, cleaning, handover | 13% |  |  |  |  | 0% | 0% |  |  |  | Not Started | Defect liability period starts
Update Physical Progress % weekly
Billing Ready % only updates when all documents are ready
Status options: Not Started, In Progress, Ready for Billing, Submitted, Certified, Paid, Disputed

## Document Checklist
Documentation Checklist
Milestone Stage | Document Required | Responsibility | Target Preparation Date | Completed (Y/N) | Reference Number | Storage Location | Remarks
Foundation & Plinth | Soil Test Report | Site Engineer |  | No |  |  | Valid for 6 months
Foundation & Plinth | Concrete Cube Test Reports | QC Engineer |  | No |  |  | 28 days prior to billing
Foundation & Plinth | Reinforcement Inspection Record | Site Engineer |  | No |  |  | Joint inspection with JE
Foundation & Plinth | Measurement Book Entries | Billing Engineer |  | No |  |  | Signed by both parties
Superstructure | Centering/Shuttering Checklist | Site Engineer |  | No |  |  | Pre-concrete approval
Superstructure | Steel Reconciliation Statement | Billing Engineer |  | No |  |  | Compare with BOQ
Superstructure | NDT Reports (if specified) | QC Lab |  | No |  |  | As per contract specs
Brickwork | Brick Test Certificate | Procurement |  | No |  |  | From approved lab
Brickwork | Mortar Mix Design | QC Engineer |  | No |  |  | Masonry work only
Finishing | Material Approval Copies | Project Manager |  | No |  |  | Tiles, paint, fixtures
Finishing | Waterproofing Warranty | Waterproofing Contractor |  | No |  |  | Minimum 10 years
All Stages | Work Completion Certificate | Site Engineer |  | No |  |  | Client signature required
All Stages | Labour Compliance (EPF/ESI/Bonus) | HR/Admin |  | No |  |  | Valid challans
All Stages | Progress Photos (Geo-tagged) | Site Engineer |  | No |  |  | Date and GPS stamped
Start document preparation 14 days before milestone target date
Mark 'Completed' only after verification
Link reference numbers to physical/digital files

## Cash Flow Tracker
Cash Flow & Delay Analysis
Milestone | Planned Value (INR) | Expected Billing Date | Actual Submission Date | Client Review Date | Certified Amount (INR) | Retention Deducted (5-10%) | Advance Recovered | Net Payment (INR) | Payment Received Date | Delay in Days | Delay Reason | Mitigation Action
Foundation & Plinth | 1500000
Superstructure Slab 1 | 2000000
Superstructure Slab 2 | 1800000
Brickwork | 1200000
Internal Finishing | 2500000
External Works | 1000000
Track the 'Milestone-to-Payment' cycle time
Target: 30-45 days from submission to payment
Flag delays >15 days for escalation
Use Delay Reason codes: Measurement Dispute, Missing Documents, Rate Dispute, Client Delay, Previous Bill Adjustment