## Overview
Auto-Calculating DPR Format Excel Template for Indian Construction Projects
Field-tested Daily Progress Report template with auto-calculating quantities, hindrance tracking for EOT claims, and RA bill integration. Includes Master Data, Daily Report, and Monthly Summary sheets designed for PWD/CPWD compliance and BOCW Act documentation.
- All auto-calculation formulas use standard Excel SUMIF and INDEX-MATCH functions
- Customize units in Master Data to match your BOQ exactly (meters vs feet)
- Insert company logo and GSTIN in header sections before printing
- Enable 'Track Changes' if sharing file with multiple site engineers
- Password protect formula cells to prevent accidental deletion of calculations

## Master Data
Master Data - Project Setup
Field Name | Input Value | Notes
Project Name | Widening of NH-44 from km 45 to 55 | As per Work Order
Work Order/Agreement No | PWD/CNH/2024/EOI-45 | For GCC reference
GCC Clause Reference | GCC 2014 Clause 10, 25 | EOT and retention clauses
Contractor Name | M/s Sharma Construction Pvt Ltd | Registered entity
Contractor GSTIN | 27AABCS1234A1Z5 | For tax invoices
Engineer-in-Charge (EIC) | Shri R.K. Verma, Executive Engineer | Countersignatory authority
Defect Liability Period | 24 months from completion | For retention calculation
Configure BOQ items in the table below before starting daily entries
All dropdown lists in Daily Report sheet reference this Master Data

## Master Data1
BOQ Reference Master
BOQ Item No | Description | IS Code | Unit | Total BOQ Quantity | Rate (INR)
1.1 | Earthwork in excavation | IS 1200 (Part 1) | cum | 15000 | 450
2.3 | PCC M10 (1:3:6) | IS 456 | cum | 850 | 5200
3.1 | RCC M25 (Foundation) | IS 456 | cum | 2400 | 8500
4.2 | Brick masonry 230mm | IS 1077 | sqm | 12000 | 1250
5.1 | Plastering 12mm | IS 1661 | sqm | 45000 | 380

## Daily Report
Daily Work Accomplishment Log
Date | BOQ Item No | Description | IS Code | Location/Chainage | Unit | Today's Quantity | Cumulative Quantity (Auto) | Balance Quantity (Auto) | Photo Ref No | Remarks
15/03/2024 | 1.1 | Earthwork in excavation | IS 1200 | Km 45+200 to 45+400 LHS | cum | 125 | 8750 | 6250 | IMG_001-003 | Ordinary soil
15/03/2024 | 3.1 | RCC M25 (Foundation) | IS 456 | Pier P-12, P-13 | cum | 45 | 1250 | 1150 | IMG_004-006 | Cube test done
15/03/2024 | 3.1 | RCC M25 (Foundation) | IS 456 | Pier P-14 | cum | 28 | 1278 | 1122 | IMG_007 | Partial pour
16/03/2024 | 1.1 | Earthwork in excavation | IS 1200 | Km 45+400 to 45+600 LHS | cum | 140 | 8890 | 6110 | IMG_008-010 | Hard rock encountered
Cumulative Quantity column contains SUMIF formula: sums all 'Today's Quantity' for matching BOQ Item No
Balance Quantity = Total BOQ Quantity (from Master) - Cumulative Quantity
Enter Photo Ref No as serial numbers corresponding to your dated photo folder

## Daily Report1
Hindrance and Stoppage Register
Date | Hindrance Type | Description | From Time | To Time | Hours Lost | Engineer Notified (Name/Time) | EIC Initials | Claimable (Y/N)
15/03/2024 | Client Delay | Land handover pending Plot C | 08:00 | 18:00 | 10 | JE Sharma/10:30 hrs | RKV | Y
15/03/2024 | Material Shortage | Cement supply failure PO-234 | 10:00 | 14:00 | 4 | AE Gupta/11:30 hrs | RKV | N
16/03/2024 | Weather | Heavy rain - 45mm recorded | 08:00 | 14:00 | 6 | JE Sharma/09:00 hrs | RKV | Y
Critical for EOT claims under GCC Clause 10
Must be signed by EIC within 48 hours of occurrence
Keep separate photographic evidence for weather stoppages

## Daily Report2
Manpower and Labour Deployment
Date | Category | Trade/Designation | Count | Safety Training Date | PPE Issued (Y/N) | BOCW Compliance
15/03/2024 | Skilled | Mason | 12 | 10/03/2024 | Y | Toolbox talk done
15/03/2024 | Skilled | Bar Bender | 8 | 10/03/2024 | Y | Cert valid
15/03/2024 | Unskilled | Helper/Mazdoor | 25 | 10/03/2024 | Y | Basic safety induction
15/03/2024 | Supervisory | Site Engineer | 2 | NA | Y | Site in-charge
15/03/2024 | Supervisory | Safety Officer | 1 | NA | Y | BOCW Form V maintained

## Monthly Summary
Monthly Summary for RA Bill Preparation
BOQ Item No | Description | Unit | Opening Cumulative (Start Month) | Monthly Quantity (Auto-sum) | Closing Cumulative | Balance BOQ Qty | % Complete | MB Page Ref
1.1 | Earthwork in excavation | cum | 8750 | 265 | 9015 | 5985 | 60.1% | MB-45
2.3 | PCC M10 | cum | 450 | 85 | 535 | 315 | 62.9% | MB-46
3.1 | RCC M25 (Foundation) | cum | 1205 | 73 | 1278 | 1122 | 53.3% | MB-47
4.2 | Brick masonry 230mm | sqm | 0 | 0 | 0 | 12000 | 0% | -
Monthly Quantity auto-sums from Daily Report based on date range filters
Reconcile this sheet with Measurement Book before submitting RA bill
Variance >5% between DPR and MB requires written explanation