## Overview
Field-to-Office Collaboration Pattern Flowchart Pack
Five printable workflow templates and checklists to implement the collaboration patterns: Morning Alignment agenda, Measurement-to-Billing handoff steps, Hindrance Escalation decision tree, Photo Documentation legal checklist, and Weekly Reconciliation three-way match worksheet.
- Print and laminate the Morning Alignment agenda for daily use in site cabins
- Use the Hindrance Escalation tree as a wall poster for Site Engineers
- The Weekly Reconciliation worksheet should be filed with RA Bill supporting documents

## Morning Alignment
Pattern 1: Morning Alignment Meeting Template (15-Minute Agenda)
Time | Activity | Owner | Input Required | Output / Decision
7:45-7:48 | Yesterday's Actuals Review | Site Engineer | Previous day DPR + Measurements | Confirmed completion % vs plan
7:48-7:52 | Variance Analysis | Project Manager | Schedule baseline + Resource status | Root cause identified (Resource/Hindrance/Planning)
7:52-7:56 | Today's Target Lock | Site Engineer + PM | Work Order quantities + Crew availability | Daily target quantities agreed
7:56-8:00 | Hindrance & Risk Flag | All participants | Open issues from site | Escalation path activated if needed
Hard stop at 8:00 AM to avoid delaying work start
Site Engineer must join from work front, not site cabin
Billing Engineer optional but recommended for quantity clarity

## RACI Matrix
Pattern 1: RACI Matrix - Morning Alignment
Activity | Site Engineer | Project Manager | Billing Engineer
DPR Verification & Entry | A - Accountable | R - Responsible | C - Consulted
Resource Reallocation | C - Consulted | A - Accountable | I - Informed
Target Quantity Setting | R - Responsible | A - Accountable | C - Consulted
Hindrance Flagging | A - Accountable | R - Responsible | I - Informed
R = Performs the work, A = Final decision maker, C = Consulted before decision, I = Kept informed

## MB to Billing Flow
Pattern 2: Measurement-to-Billing Handoff Workflow
Step | Field Action (Site) | Office Action (Billing/PM) | Data Handoff | Risk Mitigated
1 | Measure work with geotagged photos | - | Digital MB entry (Location + Timestamp) | Illegible handwriting / Lost pages
2 | - | Review Measurement Sheet | Shared digital sheet with approval trail | Quantity disputes / Re-measurement
3 | Verify BOQ references | Accept/Reject with comments | Linked DPR + Photos attached | Unlinked measurements
4 | - | Prepare RA Bill draft | Auto-populated quantities from MB | Transcription errors / Decimal mistakes
5 | - | Apply retention & deductions | System calculation per Work Order | Manual calculation errors
Critical: No Excel bridge - keep data in system from field to certification
Government contracts require date/location stamps - verify metadata capture

## Hindrance Escalation
Pattern 3: Hindrance Escalation Decision Tree
Hour | Trigger Condition | Required Action | Owner | Evidence Package
0 (Immediate) | Delay observed (Drawing/Material/Utility) | Log specific hindrance with ID | Site Engineer | Photos + Specific description (Not 'client delay' but 'Drawing S-204 missing')
0-4 | Entry logged in system | Classify impact: Schedule/Cost/Both | Project Manager | Contract clause reference + Historical data
4-24 | Impact assessed | Draft formal notification letter | Project Manager | Hindrance log print + Photo evidence + DPR excerpts
24 | Documentation complete | Send to Client/Consultant | Project Manager | Complete evidence package with timestamps
24-hour window is critical for EOT validity in most CPWD/PWD contracts
Generic descriptions like 'delay due to client' will fail in arbitration

## Photo Checklist
Pattern 4: Photo Documentation Legal Checklist
Stage | Required Shot | Metadata Required | Legal Purpose | Common Failure
Before | Existing condition + Benchmarks | Timestamp + GPS + Photographer ID | Baseline evidence / Chain of custody | No measurement reference in frame
During | Concealed work (Rebar/Conduit) | Timestamp + GPS + BOQ Item Ref | Proof of process / Quality verification | Poor lighting / Blurry images
After | Completed quantity + Board | Timestamp + GPS + Dimensions visible | Quantity verification for MB | Stock photos / Old images reused
Issues | Defect/Damage immediate capture | Timestamp + GPS + Description | Dispute resolution / Damage claims | Delayed capture / Lost metadata
Arbitration standard: Original metadata must be intact (no screenshots)
Measurement board must show: Date, Location, BOQ Item, Quantity

## Weekly Reconciliation
Pattern 5: Weekly Reconciliation Worksheet (Three-Way Match)
Work Item / BOQ Ref | Site Progress (DPR) | Billing Status (RA Bill) | Schedule Plan | Variance Analysis | Action Required
Example: Foundation Block A | 100% Complete | 80% Billed | 100% Planned | Site > Billing (20% unbilled) | Prepare supplementary bill immediately
Example: Brickwork L2 | 60% Complete | 60% Billed | 80% Planned | Schedule > Site (20% lag) | Investigate hindrances / Resource shortage
Example: Plastering | 120% Complete | 120% Billed | 100% Planned | Site > Schedule (20% ahead) | Verify data accuracy / Check for errors
Example: Electrical Conduit | 90% Complete | 100% Billed | 90% Planned | Billing > Site (10% over) | Stop billing / Re-measure immediately
Cadence: Friday PM (Site) → Saturday AM (Billing) → Saturday PM (PM Review) → Monday (Submission)
Tolerance threshold: Investigate variances >5% immediately
Cash flow leak indicator: Site > Billing consistently