## Overview
PMC MIS Report Template & Sample Pack
Complete MIS reporting workbook with blank templates, filled samples from a residential high-rise project, and a pre-submission validation checklist. Includes automated variance formulas and standardized formats for Indian construction PMCs.
- All sheets include protection on header rows only; data cells are fully editable.
- Currency formatted for Indian Rupees (₹) throughout.
- Variance formulas auto-calculate; do not overwrite formula cells.
- Compatible with Excel 2016+, Google Sheets, and can be imported into Superwise PMC software.
- Delete sample data rows in Template sheets before inserting your project data.

## 01_Project_Header
Project Information Header
Field | Input_Value | Guidance_Notes
Project_Name | [Enter Project Name] | Must match client ERP naming
Project_Code | [Enter Code] | Unique identifier as per contract
Reporting_Period | [Enter Dates] | e.g., 01-15 July 2025
PMC_Manager_Name | [Enter Name] | Single point of accountability
PMC_Contact | [Enter Phone/Email] | Direct line for queries
Date_of_Issue | [Enter Date] | Date report is issued to client
Weather_Impact_Days | [Enter Number] | Days lost to rain/conditions this period
Fill this section first. Consistency in project naming prevents client confusion.

## 02_Progress_Dashboard
Physical Progress Dashboard
Work_Package | BOQ_Value_Rs | Planned_Pct | Actual_Pct | Variance_Pct | Status
Structural | 42000000 | 75% | 72% | -3% | Amber
Masonry | 18000000 | 45% | 48% | +3% | Green
Electrical | 12000000 | 30% | 25% | -5% | Red
Plumbing | 9000000 | 35% | 35% | 0% | Green
Flooring | 6000000 | 10% | 0% | -10% | Red
Status column: Green (on track), Amber (minor slippage), Red (critical delay). Variance calculated as Actual minus Planned.

## 03_Resources
Resource Deployment Log
Resource_Type | Planned_Count | Actual_Count | Variance | Remarks
Skilled_Labour | 45 | 38 | -7 | Electrical team shortage
Unskilled_Labour | 120 | 135 | +15 | Additional cleaning crew
Tower_Crane | 1 | 1 | 0 | Operational
Concrete_Pumps | 2 | 2 | 0 | Working
Excavator | 1 | 0 | -1 | Breakdown - repair scheduled
Update daily from site attendance logs. Negative variances in skilled labour often impact milestone dates.

## 04_Materials
Material Position Statement
Material | Indent_Qty | Supplied_Qty | Consumed_Qty | Stock_Qty | Unit | Rate_Rs | Stock_Value_Rs
Cement_OPC_53 | 450 | 420 | 398 | 22 | Bags | 385
TMT_Bars_16mm | 12 | 12 | 10.5 | 1.5 | MT | 58000
CPVC_Pipes_12mm | 800 | 600 | 0 | 600 | m | 145
M_Sand | 50 | 45 | 40 | 5 | MT | 1200
Stock Value uses formula. Ensure physical stock verification matches Stock_Qty before reporting. Include materials critical to next 15-day schedule.

## 05_RA_Bills
RA Bill Certification Status
RA_Bill_No | Contractor_Name | Period | Gross_Amount_Rs | Certified_Amount_Rs | Retention_Rs | Status
RA-08 | M/s Sharma Const. | June | 2450000 | 2327500 | 122500 | Certified
RA-09 | M/s Sharma Const. | July P1 | 1875000 | 0 | 0 | Awaiting_MS
RA-04 | Elite Electricals | June | 840000 | 798000 | 42000 | Certified
RA-05 | Elite Electricals | July P1 | 520000 | 0 | 0 | In_Review
Retention typically 5% as per contract. Measurement Sheet (MS) approval required before certification. Link to Work Order completion percentage.

## 06_Cost_Summary
Cost Summary and Variance
Cost_Head | Budget_Rs_Cr | Incurred_Rs_Cr | Committed_Rs_Cr | Variance_Rs_Cr | Variance_Pct
Civil_Works | 8.50 | 6.12 | 1.50 | 0.88 | 10.3%
Electrical | 1.20 | 0.78 | 0.25 | 0.17 | 14.2%
Plumbing | 0.90 | 0.58 | 0.18 | 0.14 | 15.6%
Finishing | 0.60 | 0.20 | 0.10 | 0.30 | 50.0%
TOTAL
Variance % = (Budget - Incurred - Committed) / Budget * 100. Variances >10% require detailed explanation in Issues section.

## 07_Issues
Issues and Action Register
Issue_ID | Description | Raised_By | Target_Date | Owner | Status
ISS-042 | 7th Floor slab approval pending from architect | Site Engineer | 10-Jul-2025 | PMC Manager | Open
ISS-043 | Electrical contractor labour shortage | Project Manager | 20-Jul-2025 | Contractor | Monitoring
ISS-044 | RMC supply delay from Ultratech | Site Engineer | 15-Jul-2025 | Procurement | Resolved
ISS-045 | Drawing revision for 8th floor pending | Site Engineer | 18-Jul-2025 | Client | Open
Use Issue_ID format ISS-XXX for tracking. Every Open item must have a Target_Date within next 30 days. Escalate items crossing Target_Date twice.

## 08_Checklist
Pre-Submission Checklist
Category | Validation_Item | Status_Yes_No_NA | Remarks
Data Integrity | Progress % reconciles across all sections | [Dropdown] | Cross-check Progress vs Cost
Data Integrity | RA bill amounts match certified payment registers | [Dropdown] | Verify with billing engineer
Data Integrity | Material stock values match physical verification | [Dropdown] | Last physical count date:
Data Integrity | Labour numbers match attendance logs | [Dropdown] | Check daily muster
Visual Standards | Company logo and project branding applied | [Dropdown] | Top right corner
Visual Standards | Photos dated and activity-labeled | [Dropdown] | Min 4-6 photos per major activity
Visual Standards | Charts use consistent color coding (Green/Amber/Red) | [Dropdown] | Standard traffic light colors
Visual Standards | Page numbers and version control noted | [Dropdown] | Ver 1.0, 2.0 etc.
Client Focus | Executive summary fits on one page | [Dropdown] | No scrolling required
Client Focus | Variance explanations include root cause | [Dropdown] | Not just numbers, explain why
Client Focus | Action items have clear owners and dates | [Dropdown] | Every open issue assigned
Client Focus | Next period milestones specified | [Dropdown] | Key targets for next report
Compliance | RERA-required disclosures included | [Dropdown] | If applicable to project
Compliance | Carpet area progress tracked separately | [Dropdown] | Required for RERA compliance
Compliance | Quality checklist references attached | [Dropdown] | Inspection dates cited
Compliance | Safety incident report included (even if zero) | [Dropdown] | Zero incident statement if none
Complete this checklist before every submission. All items must be 'Yes' or 'NA' before sending to client. 'No' items require correction.