## Overview
RA Bill Excel Template for Indian Construction
Complete RA Bill workbook with auto-calculating formulas for measurement books, abstract sheets, deductions (retention, TDS, advance recovery), and GST compliance. Ready for CPWD and private construction projects.
- Template uses standard Indian construction industry terminology (CPWD/PWD format)
- All formulas are editable—unlock sheets to modify calculations
- Maintain one copy per project to track cumulative amounts
- Retention cap validation: Ensure total retention never exceeds 5% of total contract value
- TDS rates current as per FY 2024-25 Income Tax Act provisions

## Measurement Book
Joint Measurement Book
Date | Item No | Description | Location | L (m) | B (m) | D (m) | Quantity | Contractor Sign | Client Sign
15-11-2024 | 1.1 | Earthwork excavation | Block A, Footings F1-F12 | 12.50 | 8.30 | 1.50 | 155.63
15-11-2024 | 2.3 | PCC M20 (1:1.5:3) | Block A, Footings F1-F12 | 12.50 | 8.30 | 0.15 | 15.56
16-11-2024 | 4.1 | RCC M25 slab | Block B, Level 3 | 24.00 | 12.00 | 0.20 | 57.60
Record measurements during joint site verification
Attach date-stamped photographs for each entry
Both parties must sign immediately after measurement

## Abstract Sheet
Abstract Sheet
BOQ Item No | Description | Unit | This Period Qty | Cumulative Qty | BOQ Rate (₹) | This Period Amount (₹) | Cumulative Amount (₹)
1.1 | Earthwork excavation | cum | 245.00 | 1245.00 | 320
2.3 | PCC M20 | cum | 15.56 | 45.20 | 4850
4.1 | RCC M25 | cum | 28.00 | 156.00 | 6200
Total
Formulas auto-calculate amounts based on BOQ rates
Cumulative quantity must match previous bill + current claim
Cross-check rates against tender documents

## RA Bill Format
RA Bill Summary
Section | Details | Amount (₹) | Notes
A | Gross Amount (This Period) | Abstract Sheet Total | From abstract calculations
B | Amount Upto Previous Bill | [Carry forward] | Last certified amount
C | Since Previous Bill (A-B) | [Formula] | Current claim
D | Less: Retention @ 5% |  | Max cap 5% of contract value
E | Less: Advance Recovery | [As per contract] | Usually 20-25% of bill
F | Less: TDS @ 2% |  | Section 194C (PAN required)
G | Add: GST @ 18% |  | HSN code 9954
H | Net Amount Due |  | In words: _______________
Enter contract value in cell B2 for retention cap validation
TDS rate is 1% for individual/HUF contractors
Validate HSN codes against current GST circulars

## Deductions
Deductions Calculator
Deduction Type | Base Amount (₹) | Rate | Amount (₹) | Running Balance (₹) | Remarks
Retention Money | Current Bill Gross | 5% |  | Cumulative retention | Cap at 5% of total contract value
Mobilization Advance Recovery | Current Bill Gross | 20% |  | Advance remaining | Until advance fully recovered
TDS (With PAN) | Current Bill Gross | 2% |  | TDS deducted this FY | 1% for individual/HUF contractors
TDS (Without PAN) | Current Bill Gross | 10% |  | TDS deducted this FY | Higher rate for non-compliance
Other Deductions |  |  |  |  | Liquidated damages, penalties, etc.
TDS is calculated on gross amount before retention
Advance recovery stops when balance reaches zero
Maintain running ledger for retention release at project end

## GST Invoice
GST Tax Invoice
Field | Details
Invoice No | RA/2024-25/___
Date | [Bill Date]
Contractor Name | [Registered Name]
GSTIN | [15-digit GST Number]
Client Name | [Owner/Agency]
Client GSTIN | [If registered]
HSN Code | 9954 (Construction services)
Taxable Value (₹) | [Gross Amount]
CGST @ 9% (₹)
SGST @ 9% (₹)
IGST @ 18% (₹)
Total Invoice Value (₹)
Reverse Charge | Applicable/Not Applicable
Use IGST only for interstate supplies
Mention RCM applicability clearly
Attach delivery challans for material supply claims

## Checklist
Pre-Submission Checklist
S.No | Check Item | Verified By | Status | Remarks
1 | MB entries complete and jointly signed | Site Engineer | ☐
2 | Abstract sheet arithmetic double-checked | QS | ☐
3 | BOQ rates cross-referenced with tender | QS | ☐
4 | Previous bill cumulative amounts carried forward correctly | Billing Team | ☐
5 | Retention calculations checked against contract cap | Finance | ☐
6 | GST invoice format validated (HSN codes correct) | Accounts | ☐
7 | Supporting photographs attached with dates | Site Team | ☐
8 | Quality test certificates attached | QA/QC | ☐
9 | Client's previous queries resolved | PM | ☐
10 | Covering letter signed and enclosures listed | Contracts | ☐
Print and attach this checklist to bill before submission
Mark all items complete to avoid rejection
Keep signed copy for internal records