## Overview
Site Reporting SOP Implementation Pack
Complete implementation toolkit for construction site reporting SOPs including RACI matrices, daily compliance checklists, 30-day rollout trackers, escalation matrices, and CPWD/PWD compliance mapping for Indian contractors.
- Customize all templates for your specific project types (CPWD buildings vs PWD roads vs Private infrastructure)
- Laminate the RACI Matrix and Escalation Contact Matrix for site office display
- Review and update backup contacts monthly or whenever personnel changes occur
- Maintain 12-year retention for all records per Indian Limitation Act requirements

## RACI Matrix
RACI Matrix & Role Definitions
Role | Reporting Responsibilities | R (Responsible) | A (Accountable) | C (Consulted) | I (Informed) | Backup Name | Mobile Number
Site Engineer | Daily progress capture, photo documentation, hindrance logging | Yes | No | Yes | Yes | [Enter Backup] | [Enter Mobile]
Project Manager | Review and approve DPRs, escalate delays | Yes | Yes | No | Yes | [Enter Backup] | [Enter Mobile]
Planning Engineer | Update schedules, analyze variance, forecast delays | No | No | Yes | Yes | [Enter Backup] | [Enter Mobile]
Billing Team | Link DPR data to Measurement Sheets and RA Bills | No | No | Yes | Yes | [Enter Backup] | [Enter Mobile]
Contracts Manager | EOT documentation, arbitration evidence preparation | No | No | Yes | Yes | [Enter Backup] | [Enter Mobile]
Client AE/PMC | Receive and verify reports, raise objections | No | No | No | Yes | [Enter Backup] | [Enter Mobile]
Laminate this matrix and display in every site office cabin
Update backup names monthly or when personnel changes occur

## Daily Checklist
Daily SOP Compliance Checklist
Item No. | Checkpoint | Standard/Requirement | Compliant (Y/N) | Evidence/Notes | Verified By | Date
1 | Site work completion captured | All work fronts documented by 5:00 PM |  | Photo count: ___
2 | Photo geo-tagging enabled | All photos have GPS coordinates embedded |  | Device settings checked: ___
3 | Photo timestamp synchronized | Network time sync confirmed (not manual) |  | Time verified against: ___
4 | DPR data entry completed | All fields filled by 6:30 PM |  | Submission time: ___
5 | Hindrance logged (if any) | Delays reported within 24 hours of occurrence |  | Hindrance ref no: ___
6 | Photo upload to central storage | All photos uploaded by 7:00 PM |  | Upload confirmation: ___
7 | File naming convention followed | Format: Location_Activity_Date_Sequence |  | Sample filename: ___
8 | PM review completed | Approved by 9:00 AM next day |  | Approval initials: ___
Complete this checklist daily before leaving site
Non-compliance triggers escalation matrix immediately

## Rollout Tracker
30-Day Rollout Tracker
Phase | Day Range | Key Task | Owner | Status | Completion Date | Notes/Issues
Baseline | Day 1-7 | Audit current reporting across all sites | Project Director | Not Started |  | Count WhatsApp groups and locate missing registers
Setup | Day 1-7 | Customize DPR templates for project types | Planning Engineer | Not Started |  | CPWD vs PWD vs Private requirements
Pilot | Day 8-14 | Run parallel reporting on pilot site | Project Manager | Not Started |  | Old WhatsApp + New SOP system
Training | Day 8-14 | Conduct stakeholder training with real data | Project Manager | Not Started |  | Include photo capture demonstration
Refinement | Day 15-21 | Document edge cases (night shift, remote sites) | Planning Engineer | Not Started |  | 2G connectivity backup procedures
Metrics | Day 15-21 | Measure pilot performance against KPIs | Project Director | Not Started |  | Target: 100% DPR submission by 10 AM
Rollout | Day 22-30 | Deploy to remaining sites (2-3 per day) | Project Manager | Not Started |  | Stagger to manage central team capacity
Verification | Day 22-30 | Verify device geo-tagging settings personally | Site Engineer | Not Started |  | Check every device individually
Compliance | Day 22-30 | Establish client communication protocols | Contracts Manager | Not Started |  | Who emails the AE - define clearly
Update status daily during implementation
Escalate to Project Director if any task delays by more than 2 days

## Escalation Matrix
Escalation Contact Matrix
Scenario | First Response | Escalation L1 | Escalation L2 | Timeline | Backup Contact
DPR not submitted by cut-off | Call Site Engineer | PM intervenes directly | Project Director involved | 2 hours | [Enter Name/Number]
Photo evidence missing | Order re-capture immediately | Deploy professional photographer | Notify client of limitation | 24 hours | [Enter Name/Number]
Hindrance not reported | Immediate corrective entry required | Contracts team assesses EOT impact | Legal review if LD risk exists | 48 hours | [Enter Name/Number]
Client disputes DPR data | Re-verification by PM | Call joint site inspection | Appoint third-party surveyor | 72 hours | [Enter Name/Number]
System failure (digital) | Switch to manual backup | Engage IT support | Client communication on delay | 4 hours | [Enter Name/Number]
Site engineer absent/unavailable | Activate backup assignee | PM covers temporarily | Redeploy from other site | Immediate | [Enter Name/Number]
Post this matrix inside every site engineer's cabin
Update contact numbers monthly or when roles change
Server crashes on billing day = immediate Level 2 escalation

## Compliance Mapping
CPWD/PWD Compliance Mapping
Requirement | SOP Element | Evidence Standard | Compliance Status | Remarks
Daily progress measurement | DPR with quantity records | Signed by site engineer & client AE | Compliant/Partial/Non-Compliant
Hindrance notification | 24-hour reporting trigger | Written communication with acknowledgment receipt | Compliant/Partial/Non-Compliant
Photo documentation | Geo-tagged, timestamped photos | 12-year retention, chain of custody logs | Compliant/Partial/Non-Compliant
Measurement book maintenance | Digital measurement sheets | Sequential entries, no alterations, page numbers intact | Compliant/Partial/Non-Compliant
RA bill supporting records | DPR-to-bill linkage | Cross-referenced quantities with dates | Compliant/Partial/Non-Compliant
EOT claim documentation | Hindrance log with impact analysis | Causal link to critical path demonstrated | Compliant/Partial/Non-Compliant
Safety incident reporting | Immediate notification protocol | FIR copy, photos, witness statements within 24h | Compliant/Partial/Non-Compliant
Quality test records | Checklist integration | Lab reports linked to DPR dates and locations | Compliant/Partial/Non-Compliant
Review compliance status monthly
CPWD contracts may require specific formats (Format 16, etc.) - customize accordingly
Non-compliant items trigger immediate SOP revision

## Hindrance Log
Weekly Hindrance Review
Date | Hindrance Description | Type | Date Reported | Impact (Days) | EOT Eligible (Y/N) | Mitigation Measures | Current Status
[DD/MM/YY] | [Describe delay cause] | Client/Force Majeure/Statutory/Material/Labor | [DD/MM/YY] | [Number] | [Y/N] | [Actions taken] | Open/Closed/Disputed
[DD/MM/YY] | [Describe delay cause] | Client/Force Majeure/Statutory/Material/Labor | [DD/MM/YY] | [Number] | [Y/N] | [Actions taken] | Open/Closed/Disputed
[DD/MM/YY] | [Describe delay cause] | Client/Force Majeure/Statutory/Material/Labor | [DD/MM/YY] | [Number] | [Y/N] | [Actions taken] | Open/Closed/Disputed
[DD/MM/YY] | [Describe delay cause] | Client/Force Majeure/Statutory/Material/Labor | [DD/MM/YY] | [Number] | [Y/N] | [Actions taken] | Open/Closed/Disputed
[DD/MM/YY] | [Describe delay cause] | Client/Force Majeure/Statutory/Material/Labor | [DD/MM/YY] | [Number] | [Y/N] | [Actions taken] | Open/Closed/Disputed
Review every Monday morning
Must link directly to EOT claim documentation
Report within 24 hours of occurrence to maintain validity

## RA Bill Alignment
RA Bill Alignment Worksheet
BOQ Item No. | Description | DPR Date Range | Qty as per DPR | Verified Qty | Photo Reference | Hindrance Impact | Bill Ready (Y/N)
[Item No.] | [Description] | [DD/MM - DD/MM] | [Number] | [Number] | [File refs] | [Days/None] | [Y/N]
[Item No.] | [Description] | [DD/MM - DD/MM] | [Number] | [Number] | [File refs] | [Days/None] | [Y/N]
[Item No.] | [Description] | [DD/MM - DD/MM] | [Number] | [Number] | [File refs] | [Days/None] | [Y/N]
[Item No.] | [Description] | [DD/MM - DD/MM] | [Number] | [Number] | [File refs] | [Days/None] | [Y/N]
[Item No.] | [Description] | [DD/MM - DD/MM] | [Number] | [Number] | [File refs] | [Days/None] | [Y/N]
Update every Monday before billing meeting
Each line item must reference specific DPR dates
Photo evidence must be indexed by BOQ item
Flag hindrance impacts for EOT consideration immediately