## Overview
Weekly Progress Report Template for Indian Construction Projects
CPWD/PWD-compliant weekly progress report workbook with built-in Earned Value calculations (SPI/CPI), hindrance register for EOT claims, BOQ-linked quantity summaries, and RA bill-ready billing impact section.
- All formulas in the Executive Summary sheet are editable. Update Planned Value (PV) and Actual Cost (AC) from your project cost records.
- The Hindrance Register sheet is formatted for arbitration evidence requirements under the Arbitration and Conciliation Act, 1996.
- Maintain sequential report numbering (WPR-YY-NNN) for audit trails.
- Retain WPRs for contract period plus 12 years (limitation period for arbitration claims).
- Billing Impact Summary links directly to Measurement Book entries - ensure quantities match before RA bill submission.

## Project Header
Project Header & Reporting Period
Field | Details
Project Name | Riverside Residences Tower A
Contract Reference | CE(P)/Mum/2024/1847
Reporting Period | Week 23: 03 June – 09 June 2024
Report Number | WPR-24-023
Contractor/PMC Name | Metro Builders Pvt. Ltd.
BOQ Reference | Schedule A – Civil Works
Project Manager
Prepared By
Date of Submission
Fill in all header details before distribution. Contract Reference is mandatory for CPWD/PWD compliance.

## Executive Summary
Executive Summary - Earned Value Snapshot
Metric | Formula | This Week | Cumulative | Target | Status
SPI (Schedule Performance Index) | EV ÷ PV | 0.94 | 0.97 | >0.95 | Behind Schedule
CPI (Cost Performance Index) | EV ÷ AC | 1.02 | 1.01 | >0.95 | On Budget
Week's Earned Value (₹) | Completed work × BOQ rates | 2430000 | - | -
Cumulative Earned Value (₹) | Total value to date | - | 48500000 | vs Budget
Physical Progress % | - | 62% | 64% Planned | - | 2% Behind
SPI >1 = Ahead, <1 = Behind. CPI >1 = Under budget, <1 = Over budget. Update PV and AC from your cost records.

## Work Completion
Work Completion Summary (7-Day Consolidated)
BOQ Item | Description | Unit | Planned Qty (Week) | Achieved Qty (Week) | Cumulative Qty | % Complete | Status
2.1 | PCC M10 | m³ | 45 | 42 | 386 | 62% | On Track
2.2 | RCC M25 (Columns) | m³ | 28 | 28 | 124 | 38% | On Track
3.1 | Brickwork 230mm | m² | 180 | 156 | 890 | 29% | Behind
4.5 | Internal Plaster | m² | 320 | 340 | 1240 | 41% | Ahead
5.2 | External Painting | m² | 0 | 0 | 450 | 12% | Not Started
Achieved Qty must reconcile with Measurement Book entries. This creates the audit trail: daily progress → weekly summary → RA bill.

## Resources
Resource Deployment - Manpower
Resource Type | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Weekly Total | Productivity
Skilled Masons | 12 | 12 | 10 | 12 | 14 | 8 | 0 | 68 | 2.3 m²/day
Bar Benders | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 24
General Labour | 25 | 28 | 25 | 30 | 28 | 20 | 0 | 156
Carpenters | 8 | 8 | 6 | 8 | 8 | 6 | 0 | 44
Supervisors | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 14
Track productivity rates to identify delays early. Compare weekly manday output against planned norms.

## Resources1
Resource Deployment - Machinery & Materials
Resource | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Weekly Total | Remarks
Tower Crane (hrs) | 10 | 10 | 10 | 10 | 10 | 6 | 0 | 56 | Breakdown on Sat
Concrete Pump (hrs) | 4 | 0 | 0 | 4 | 0 | 4 | 0 | 12
Cement Receipt (MT) | 12 | 0 | 18 | 0 | 15 | 0 | 0 | 45
TMT Steel Receipt (MT) | 0 | 8 | 0 | 0 | 12 | 0 | 0 | 20
Bricks (Nos.) | 2000 | 0 | 3000 | 0 | 2500 | 0 | 0 | 7500
Log machinery breakdowns and material shortages here. These impact productivity calculations.

## Hindrances
Hindrances & Delay Register
Date | Hindrance Description | Type | Responsibility | Impact (Days) | Reference Document | Status | EOT Claim Ref
05-Jun | Delay in G+2 slab shuttering release by PMC | Client-Caused | PMC/Client | 2 | SI dated 04-Jun | Resolved 07-Jun | EOT-2024-003
06-Jun | Non-availability of power 14:00-18:00 | External | Discom | 0.5 | Complaint DES-240606-1 | Ongoing
07-Jun | Revised drawing for staircase landing | Design Change | Client/Architect | 1 | Drawing Rev. B dated 06-Jun | Resolved
Critical for arbitration evidence. Type: Client-caused, Contractor-caused, Force Majeure, or Neutral. Always link to formal reference documents.

## QHSE
Quality & Safety Observations
Date | Observation Type | Description | Location | Action Taken | NCR Ref | Status | Closed Date
04-Jun | Quality | Honeycombing in Column C-12 | Grid C-12, G+1 | Removed and re-cast | NCR-2024-047 | Closed | 05-Jun
06-Jun | Safety | Missing guardrail at slab edge | South edge G+3 | Installed immediately | - | Closed | 06-Jun
Link to NCR register. Keep open items visible for follow-up.

## Photo Log
Photo Evidence Grid
Location/Activity | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Photo Ref
Foundation Zone A | [Photo] | [Photo] | - | - | - | - | - | IMG_240603_001
Column Shuttering G+2 | - | [Photo] | [Photo] | - | - | - | - | IMG_240604_015
Slab Casting G+1 | - | - | - | [Photo] | [Photo] | [Photo] | - | IMG_240606_042
Material Storage | [Photo] | - | [Photo] | - | [Photo] | - | - | IMG_240603_008
Safety Walk | - | - | - | - | [Photo] | - | - | IMG_240607_031
Ensure photos are geo-tagged and dated. CPWD/PWD requires photographic evidence for Measurement Book entries.

## Look Ahead
Upcoming Week Plan
Activity | Target Quantity | Unit | Dependencies | Risk/Issue | Responsible | Planned Start
Complete slab shuttering G+3 | 285 | m² | Column concrete curing (72 hrs) | Crane availability confirmed | Site Engg | 10-Jun
Start blockwork G+2 | 120 | m² | Slab shuttering release by PMC | Await PMC inspection | Mason Foreman | 12-Jun
Foundation PCC Zone C | 60 | m³ | Utility clearance from MCGM | Approval pending | Project Mgr | 11-Jun
Electrical conduit laying G+1 | 150 | m | Blockwork completion | Material delivered | Electrical Sub | 13-Jun
Use this to flag dependencies requiring client/PMC action. Creates written record of external delays.

## Billing Summary
Billing Impact Summary (RA-Ready)
BOQ Item | Description | Unit | Rate (₹) | This Week Qty | This Week Value (₹) | Cumulative Value (₹) | Remarks
2.1 | PCC M10 | m³ | 4850 | 42 | 203700 | 1872100 | Ready for RA-6
2.2 | RCC M25 (Columns) | m³ | 8200 | 28 | 229600 | 1016800 | Ready for RA-6
3.1 | Brickwork 230mm | m² | 1450 | 156 | 226200 | 1290500 | Hold - NCR open
4.5 | Internal Plaster | m² | 850 | 340 | 289000 | 1054000 | Ready for RA-6
| TOTAL |  |  |  | 948500
Extract quantities directly from Work Completion Summary. Cross-check with Measurement Book before RA bill submission. 'Hold' items indicate quality issues or incomplete documentation.