# Project Title

SİVASTUR: Urban Laboratory for Circular Tourism in Sivas

## Call and Availability

- Program/Çağrı: DRIVING URBAN TRANSITIONS (DUT) Partnership – DUT Call 2025

- Geçiş Yolu & Konu: Circular Urban Economies (CUE) → Topic #2: Sustainable tourism – circular benefits & challenges

- Type of Approach (R&I): Innovation-Oriented Approach (IOA) – real-life pilot/demonstration, co-design, and rapidly scalable solutions

- Duration: 36 months

- Short Summary: Against the problems of tourism-related waste, water/energy consumption and pressure on cultural heritage sites in Sivas; A circular tourism model will be developed by establishing an urban living laboratory (Urban Living Lab)  with universities, SMEs and NGOs under the leadership of the municipality  . Pilots; It includes waste separation and deposit at source, biodegradable transformation of food waste, water-energy efficiency in hotels/businesses, green/public procurement and digital monitoring panel. Outputs; policy tools, procurement criteria, business models, investment plan and scaling guides.

## Problem and Need (Problem Definition)

- Periodic increase in the number of visitors in Sivas; solid waste (especially single-use plastic), food waste, water and energy consumption increase and historical/ecological areas .

- Circular data and procurement integration between businesses and the public  is limited;  Circularity criteria in public procurement are weak.

- Circular practices in tourism  are scattered and pilotless; measurement and evaluation infrastructure is lacking.

## General Purpose

To develop  a fair and inclusive circular tourism model that reduces resource consumption and waste in the tourism ecosystem in Sivas, strengthens the local economy,  and makes it scalable across the EU.

## Specific Objectives (SMART)

- Waste reduction: Reducing tourism-related mixed waste by 40%  and single-use plastics by 60% in pilot areas  (by 30% per month).

- Food waste circularity Increase by 30% and recovery in biodegradable fraction by 50% in hotels/food and beverage establishments  (month 24).

- Water/energy efficiency: Reducing water consumption by 20% and  energy consumption by 15% in hospitality businesses  (month 30).

- Circular purchasing: 25% of the municipality's tourism-related purchases  are made with circular criteria (month 36).

- Governance and capacity: Participation of  at least 120 stakeholders (businesses, artisans, NGOs, citizens) in the co-design processes within the  Urban Living Lab;Training of 40 public personnel and 80 enterprise employees (month 36).

- Scaling: Replication guidelines and investment plan for 3 EU cities  (month 36).

## Approach and Methodology (IOA + ULL)

- Approach: IOA –  rapid value generation with demo/pilot applications;Co-production  and real-world testing via Urban Living Lab (ULL).

- Co-Design: Design-oriented workshops  with municipalities, businesses, citizens, universities and SMEs  ; principles of inclusivity and gender equality.

- Data and Decision Support: Digital dashboard that collects waste, water, energy and visitor flows; data-driven policy cycle.

- Open Science and DNSH: Open data sets, fair data governance plan; Do No Significant Harm principle.

## Pilots (Sivas Focused)

- Old Town District 'Single-Use Plastic'-Free Tourism

  - Deposit-return system, reusable container/bottle, multi-point segregation, site-appropriate box/marking.

- Food Waste → Bio-cycle

  - Smart weighing and menu optimization in hotels/restaurants; compost/biogas by collecting biodegradable; urban green spaces and use in local production.

- Water-Energy Efficiency Package

  - Smart meters, low flow armature, heat recovery; instant display of results on the dashboard.

- Green Public Procurement

  - Circular set of criteria for tourism events and municipal services, contractual clauses, market dialogue.

- Circular Crafts and Reuse

  - Local product from waste materials;  social employment with a repair/reuse center.

## Study Packages (WPs)

- WP1 – Project Management & Program Activities

  - Consortium management, quality, risk; Budget and time allocated for DUT Program Activities (Knowledge Hub, mandatory activities); tracking/reporting.

- WP2 – ULL Installation and Co-Design

  - Stakeholder mapping, needs analysis, co-production workshops, inclusive engagement plan.

- WP3 – Data Infrastructure and Dashboard

  - Sensor/manual data collection, data governance, panel, and API; open datasets.

- WP4 – Pilot Applications (Plastics, Food, Water/Energy)

  - Design → installation → operation → evaluation cycles; business coaching.

- WP5 – Policy, Procurement, and Business Models

  - Circular public procurement guidance; business model canvases, cost-benefit and investment plan; alignment to standards/labels.

- WP6 – Dissemination, Replication and Sustainability

  - Multilingual communication; Replication  plan in 3 cities in the EU  ; localization of results and institutionalization.

## Main Outputs

- Sivas Circular Tourism Roadmap and Policy Recommendations

- Circular Public Procurement Criteria Set and sample contract clauses

- Digital Instrument Cluster (with open source components)

- Pilot Result Reports (KPI and LCA summaries)

- Business Models and Investment Plan (CAPEX/OPEX, payback periods)

- Training Modules (municipality, business, NGO)

- Replication Guide (for 3 EU cities)

## Expected Impact

- Local impact: Measurable reduction in waste and resource consumption; cost reduction in businesses;  market transformation through public procurement.

- Community impact: Inclusive employment; the craft and repair economy; the preservation of heritage sites.

- EU impact: policy instruments and scaling aligned with CUE Topic #2 outputs; information sharing between cities; evidence base in the "green transition".

## Success Indicators (Example KPIs)

- Waste/recycling: kg/visitor, recovery rate, single-use plastic usage rate

- Food: kg/item and waste reduction to plate , compost/biogas output

- Water/energy: m³/accommodation-night, kWh/visitor

- Public procurement: percentage of tenders with cyclical criteria

- Attendance: ULL number of events and participant profiles

- Engagement: online panel visits, open data downloads

## Consortium and Roles (compliant with minimum requirement)

- Sivas Municipality (TR) – Municipal partner and pilot site owner; public procurement and field operations; citizen participation.

- Sivas Cumhuriyet Technology Transfer Office / Cumhuriyet University (TR) – Coordination (preferably) and impact assessment; data/modeling; training.

- SME (TR) – Waste/IoT/compost/digital panel development and service.

- European Municipality (EU Member/Associated Country) – Co-learning and replication; policy peer review.

- Research Institution/University (EU) – LCA, business model, impact and replication design.

- CSO/Civil Society (EU/TR) – Inclusive participation, community communication.

Note: The distribution of consortium, country and stakeholders will be balanced; the workload of a single partner will not exceed 50%; gender balance will be ensured.

## Timeline (36 months)

- Months 1–3: Consortium agreement, ULL installation, detailed design

- Months 4–9: Panel development and data infrastructure, procurement/installation processes

- Month 7–24: Pilots (plastic, food, water/energy) – consecutive sprints

- Months 18–30: Policy and purchasing practices, business model, interim impact analysis

- Month 28–36: Replication guidelines, investment plan, final evaluation and dissemination

## Budget and Eligible Costs (summary)

- Total project budget (estimated): 1.6–1.9 M€ (all partners, according to agency rules)

- Share for programme activities: A maximum of €30,000 will be allocated  from the general budget of the consortium  (Knowledge Hub, compulsory events, reporting).

- TR National Rules (TÜBİTAK) – summary:

  - For Turkey, a maximum of €230,000 per project can be claimed (excluding PIP and overheads);

  - Public institutions/universities/research hospitals/municipalities: €100,000 per partner, €125,000 if TR coordinator  (excluding PIP and overheads);

  - Private sector: €230,000 per partner;

  - Eligible cost items: personnel, travel, equipment/software, consultancy/service procurement, consumables.

- TR side recommended distribution (example):

  - Sivas Municipality: €100,000 (pilot applications, purchase conversion, participation)

  - SCU/TTO: €100,000–125,000 (coordination/impact/data)

  - TR SME: €0–30,000 (adjusted depending on the overall TR cap)

- The budgets of partners in other countries  will be planned in accordance with the ceilings in their national annexes.

## Management, Quality and Risks

- Management: Coordination board; WP leaders; ethics and data committee; Municipality-oriented decision cycles.

- Quality assurance: Staged deliverables; external peer review; transparent monitoring with dashboard.

- Main risks: Fluctuation in tourism demand, supply delays, decreased stakeholder engagement, data quality; Mitigation plans: phases, alternative procurement, field coaching, data validation.

## Ethics, Open Science, Data and Equity

- Ethics: Data privacy/anonymization; site safety; occupational health and safety in procurement.

- Open Science & DMP: Open access publications; Data Management Plan (FAIR); openly licensed policy and code.

- DNSH: DNSH checklist for impacts on waste, water, energy, biodiversity, and pollution; compensatory measures for adverse impacts.

- Inclusion and Gender: Accessibility at all events; gender/inclusion indicators and reporting.

## Dissemination and Exploitation

- Target audiences: Municipalities, tourism enterprises, regional development agencies, NGOs, citizens, investors.

- Tools: Policy workshops, demonstration days, open data and panel, practical guides, MOOC/short modules, media.

## Sustainability and Scaling

- At the end of the pilots, the solutions embedded in the municipal budget and public procurement processes;  continuity in businesses with  the business model; twinning and investment partnerships with EU cities for replication.

## Eligibility Checklist (Pre-proposal)

- Language and format: English, suitable for template/page restrictions.

- Consortium: At least 3 countries/3 partners and at least one municipality; budget and workload balance; single partner less than 50% workload.

- Duration: 36 months.

- Budget: In accordance with national ceilings and items; allocated for program activities.

- Submission: Submission via UDiManager  in accordance with the pre-bid deadline.

- National annexes: Each partner confirms compliance with national agency rules.

### Contact (draft)

- Coordinator (recommended): Sivas Cumhuriyet TTO / Sivas Cumhuriyet University

- Municipality Partner: Sivas Municipality

- Email: (to be added)

- Web: (to be added)