- Hosted Payload Details (Please fill in yellow items)

  - Payload Details

| Launch Window | Payload Name(s) | Qty | Payload Mass | Volume/Dimensions |
| --- | --- | --- | --- | --- |
| QX-20YY – QX-20YY | (TBC) | X | Up to XX kg | XX U XYZ cm |

  - Operational Orbit Requirements

| Orbit Inclination | Perigee | Apogee | LTDN |
| --- | --- | --- | --- |
| XX +/- YY deg | XX +/- YY km | XX +/- YY km | If applicable |

- Hosted Payload Service (Please fill in yellow items)

Momentus shall provide the Hosted Payload Service as outlined below.

  - Nominal Hosted Payload Service Parameters (Standard offering shown for reference)

| Service offering | Service duration | Orbit Average Power | TT+C Data | Data Storage | Data Interface |
| --- | --- | --- | --- | --- | --- |
| Standard | 6 months | 25 W (28 V +/- 0.5 V Regulated DC) | Uplink: 0.5 MiB/day Downlink: 1 MiB/day | 160 MiB | RS-485 (UART protocol) and/or Gigabit Ethernet |

  - Nominal Hosted Payload Pointing Requirements

| List of Instruments/ Antennas | Pointing Direction* | Pointing Duration | Field of View | Pointing Control | Pointing Knowledge | Pointing Stability |
| --- | --- | --- | --- | --- | --- | --- |
| Eg. Sat Com Antenna | Eg. Nadir/ Zenith / Sun / Ground Station / Other / Not Applicable | Eg. 80% of pass / 3 minutes | +/- XX deg +/- YY deg | Eg. +/- 5 deg | Eg. +/- 1 deg | Eg. <0.2 deg/s |

* Customer shall indicate the cadence and duration of pointing operations, specifically outlining whether sustained vs. Intermittent pointing is required. Ground station latitude, longitude, altitude, and minimum elevation to be provided at a later date.

  - Nominal Hosted Payload Concept of Operations

Both parties agree to refine the concept of operations (CONOPS) to include any, or all, of the following integrated operations capabilities into the Customer Hosted Payload mission aboard Momentus’ OSV:

Briefly describe the objectives and overview of the hosted payload mission.

    - Frequency of operations

Momentus OSV shall perform Hosted Payload CONOPS as defined below with a frequency not greater than one (1) time per week, throughout the Hosted Payload service duration.

    - Operations modes

Primary operational modes of the Customer Hosted Payload shall be activated and deactivated by the Momentus OSV per the CONOPS below, and as defined below: (Existing values are examples only)

| Operation Mode | Description | Power | Thermal | Interface Temperature | Data |
| --- | --- | --- | --- | --- | --- |
| Standby |  | 10 W | 7 W | Max/Min | 0 MiB / 0 Mbps |
| Receive |  | 25 W | 18 W | Max/Min | 10 MiB / 2 Mbps |
| Standby |  | 10 W | 7 W | Max/Min | 0 MiB / 0 Mbps |
| Off |  | 5 W | 4 W | Max/Min | 0 MiB / 0 Mbps |

    - CONOPS overview

| Operation Mode | Notional duration | Operational requirements |
| --- | --- | --- |
| Standby | 10 minutes |  |
| Receive | 60 minutes |  |
| Standby | 10 minutes |  |
| Off | Unless in other modes |  |

Table 2. PROGRAM MILESTONES, REVIEWS AND DELIVERABLES (for reference)

| Schedule | Workstream | Purpose | Customer Deliverables |
| --- | --- | --- | --- |
| - | Agreement signature | Authority to proceed with work | - Signed agreement - Customer point of contact |
| EDC + 2 weeks | Mission Kickoff | Deliverable templates are provided to the Customer General payload information is provided to Momentus to initiate mission planning | - Payload constituents worksheet - Payload mass properties (preliminary) - Initial on-orbit operations inputs |
| L-10 months | Mission Analysis Inputs | Payload technical inputs are provided to initiate mission-level analyses | - Payload inputs to ICD (mechanical, electrical, data) - Payload mass properties (updated) - Payload CAD model - Payload dynamic model - Payload thermal model - Regulatory worksheet - Propulsion/pressure system details (if applicable) - Transmitter verification worksheet |
| L-9 months | Operations Planning | Operational requirements and objectives are provided by Customer | - Inputs to operations plan (pointing profiles, ops cadence, communications) |
| L-8 months | Payload Integration Planning | Detailed steps and equipment for payload integration on to the Momentus host spacecraft are provided by the Customer | - Initial integration procedure - GSE information and/or requirements |
| L-7 months | Range Safety Submission | Range Safety deliverables submitted by the Customer to Momentus for coordination with the launch authority | - Range Safety Checklist - MSPSP Program Introduction |
| L-6 months | Final Payload Integration Planning | Customer and Momentus agreement on integration plan | - Final integration procedure - Facility visitor information |
| L-5 months | Final Mission Analysis Inputs | Final technical inputs are provided by the Customer to complete mission-level analysis | - Payload environmental test report - Verification of ICD compliance - Final mass properties |
|  | Range Safety Submission | Final range safety deliverables are submitted by the Customer | - AFSPCMAN 91-710 tailoring matrix (if applicable) - AFSPCMAN 91-710 compliance letter |
|  | Payload delivery to Momentus for spacecraft integration |  |  |
| L-4 months | Beginning of spacecraft-level environmental testing (includes all hosted payloads) |  |  |
| L-2 months | Operations Planning | Operations plan is finalized, and ground testing is complete | - Final operations plan |
| L-1.5 months | Beginning of spacecraft integration with launch vehicle |  |  |
| L0 | Launch |  |  |
| L+ [TBD] | Beginning of hosted payload operations |  |  |
| L+ [TBD] | End of hosted payload operations |  |  |