## List items (hidden)
Type of Vaccination session
Health Facility
Outreach

## Communication Plan
ADVOCACY,COMMUNICATION AND SOCIAL MOBILIZATION COMMUNICATION PLAN FOR HPV VACCINE INTRODUCTION
OBJECTIVES | ACTIVITIES | KEY MESSAGES | RESOURCE NEEDED | COMMUNICATION CHANNEL | EXPECTET OUTPUT | TIME | RESPONSIBLE
To inform IVD ,regional,district and community levels on Communication needs before National Rollout of HPV vaccines building form the demonstration conducted | Conduct communication and community Aapid Asessment to inform the introduction of HPV vaccine countrywide |  | Funds,Time,HR | Email,Official letters | Assessment report | 2018-02-01 | IVD,UNICEF
| Documentation of Rapid Assessment Findings |  | HR,Funds | Publications,Workshops | Documentation report | 2018-02-01 | IVD,UNICEF,WHO, Partners
To create awareness to key stakeholders for from National to Community Level for smooth introduction of HPV Vaccine | Develop HPV vaccine introduction advocacy orientation Package(Fact sheets,PPT) |  | Funds,Time,HR | Email,Telephone,Official letter | Orientation Package developed | 2017-12-01 | Gadau/Frida
| Draft and share official letters to inform all key stakeholders to fully participate and be involved in HPV vaccine introduction advocacy activities(Link with PORLG and MOEVT) |  | Funds,Time,HR | Email,Letters | Letters drafted and Circulated | 2018-01-01 | Gadau,Maryrose
| Conduct high level advocacy meeting with extended ICC&Partners,Parliamentary health and Social commettee,Religionus leders and media houses) |  | Funds,Time,HR | Email,Telephone,Official letter,Fact sheet | Number of high level meetings conducted,Number members attended | 2018-02-01 | Gadau,Raphael,Maryrose
| Conduct regional stakeholders and Extended District PHC meetings for HPV vaccine inroduction |  | Perdiem,Refreshments,Presentation,Fact sheets,Leaflets | Email,Telephone,Official letter,Fact sheet | Number of extended PHC meeting conducted,Number of PHC members attended | February-March 2018 | Gadau,RMOs,DMOs
| Conduct orientation of Health facility workers on interpersoinal /face to face communication and effective communication methods for delivering Cervical cancer and HPV caccine related message |  | PerdiemTime,HR,Venue,Communication guide | Fact sheets,Leaf letters,vaccination guide, | Number of health facility worekers oriented on HPV IPC methods | 2017-03-01 | IVD,RHMT,CHMT
| Conduct Meetings with Religious and Influential leaders to sentitize them on Benefits of HPV vaccine and solicit their supoport |  | Perdiem,Time,HR,Venue | Fact sheets,Leaf letters,vaccination guide, | Number of Meetings conducted | March-April 2018 | IVD,RHMT,CHMT
| Conduct HPV vaccine introduction meeting with Teachers ,WDC, Village Councils ,CHWs and parents to sensitize them on the benefits of the vaccine and their roles and responsibilities for the successful introduction |  | Funds,HR,Leaflets,Posters,PS systems | Email,Telephone,Official letter | Number of Meeting conductec with Parents,Teachers and Community | 2018-03-01 | DMOs,WEOs,VEOs
To review and update exisiting HPV vaccine IEC materials | Conduct workshop to review and update HPV vaccine introduction IEC materials(Posters,Leaflets,Fact sheet,FAQs, Jingles,TV and Radio Sports and advert) |  | Funds,HR,Refreshments,draft IEC materials | Email,Telephone,Official letter | IEC materials reviewed and updated | 2017-12-01 | Gadau,Partners
| Pre-testing of IEC Materials for HPV vaccine Introduction |  | Funds,HR,draft IEC materials | Email,Telephone,Official letter | IEC Materials for HPV vaccine Introduction Pre-tested | 2018-02-01 | Gadau,HEU,Partners
| Printing and distribution/dessemination HPV vaccine IEC materials |  | Funds, HR,IEC materials | Email,Telephone,Official letter | Reviewed and updated IEC materials printed Availability of IEC materials | 2018-03-01 | Gadau,Parners
To Develop crisis Communication plan to deal with misconception ,myths and AEFI on HPV vaccine | Identify Key/Influencial people and CHWs to detect and trace rumours ,myths,misconception regarding HPV Vaccine |  | Time and HR | Telephones,email,SMS | Key/Influencial people and CHWs to detect and trace rumours ,myths,misconception regarding HPV Vaccine identifiedidentified | 2018-03-01 | DMO,HF i/Cs
| Develop specific messages to adress misconception,myths and AEFI on HPV vaccine |  | Funds,Time,HR | Email,Telephone,Official letter | Specific messages to adress misconception,myths and AEFI on HPV vaccine developed | 2017-12-01 | Gadau,Partners,HEU
| Prepare technical guidance on what,who,when and how to respond to rumours,misconception on HPV vaccines |  | Funds,Time,HR | Email,Telephone,Official letter | Technical guidance on what,who,when and how to respond to rumours,misconception on HPV vaccine developed | 2017-12-01 | IVD,Partners
To engade media on introdution of HPV vaccine | Identify key media houses to be engaged and establish mechanism for collaboration to suport HPV vaccine introction from National to Subnational levels - Lobby for for free airtime |  | Time,HR | Email,Telephone,Official letter | Number of media houses identifief and engaged | 2017-12-01 | Gadau,Patners,MEWATA
| Inform and Sensitize community on availability and benefitst of HPV vaccine through Social media such whatsup,instagram,Facebook etc |  | Time,HR | whatsup,instagram,Facebook etc | Number of Social media such whatsup,instagram,Facebook engaged etc | Feb-May 2018 | HEU,Gadau,Partners
| Prepare schedule for radio/TV programme talk show on HPV vaccine Introduction |  | Time,HR | TV ,Radio | Schedule for radio/TV programme talk show on HPV vaccine Introduction developed | 2018-02-01 | IDV,MEWATA,RMO.DMO
| Air TV and Radio spots for HPV vaccine introduction |  | Time,HR,Funds | TV,Radio | Number of TV and Radio spots for HPV vaccine introduction aired | April -May2018 | IVD,UNICEF/WHO
| Engagement of communication companies such as Vodacom,Tigo,Airtel,Hallotel and lobby for free sms on HVP introduction(Consider Comprehensive messages for cervical cancer prevention-Primary and secondary) |  | Time,HR | Interparsonal,Official Letter,Telephone | Number of communication companies engaged Number of SMS for HPV vaccine sensitizationshare by communication companies | February-April 2018 | IVD,MEWATA,PARTNERS
To prepare and conduct National and Subnational Launching of IPV vaccine Introduction Launch | ACSM subtechnical working group to plan ,organise and prepare roadmap for National Launching for HPV vaccine ; -Agenda,Speeches,Press release,Talking notes,edutainment groups,vaccine administration demonstration |  | Time,HR | Interparsonal,Official Letter,Telephone | Roadmap for National Launching for HPV vaccine ; -Agenda,Speeches,Press release,Talking notes,edutainment groups,vaccine administration demonstration prepared | 2018-02-01 | Gadau,Dr Frida,Partners
| Identify Key Stakeholders to Participate in National and Subnational Launch |  | Time,HR | Interparsonal,Official Letter,Telephone | Key Stakeholders to Participate in National Launch developed | 2018-02-01 | IVD,MEWATA,RMOs,DMOs
| Conduct Launching (National and Subnational Launching) |  | Time,Funds,HR | Interparsonal,Official Letter,Telephone | Launching Conducted | 2018-04-01 | IVD,MEWATA,RMOs,DMOs
| Post Introduction Monitoring and Evaluation of ACSM for HPV introduction |  | Time,Funds,HR | Interparsonal,Official Letter,Telephone,Watsup,Twitter,Facebook | Number of mass media engaged in disseminating messages related to HPV vaccine introduction | 2018-05-01 | IVD,RMOs,DMOs

## Communication timeline
ACTIVITIES | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | RESPONSIBLE(IVD/REGIONS/DISTRICT | RESPONSIBLE(PARTNERS) | STATUS
Conduct community and communication Rapid Asessment to inform the introduction of HPV vaccine countrywide | [7 empty] | Gadau,Frida | UNICEF | TO BE DONE
Documentation of Rapid Assessment Findings | [7 empty] | Gadau,Frida | UNICEF | TO BE DONE
Develop HPV vaccine introduction advocacy orientation Package(Fact sheets,PPT) | [7 empty] | Gadau/Frida | Raphael/Maryrose/Fikiri | DONE
Draft and share official letters to inform all key stakeholders to fully participate and be involved in HPV vaccine introduction advocacy activities(Link with PORLG and MOEVT) | [7 empty] | Gadau | Maryrose/Raphael | DONE
Conduct high level advocacy meeting with Stakeholders(Parliamentary health and Social commettee,Partners,Religionus leders,PORALG,MOF,MEWATA, and media houses) | [7 empty] | Gadau | Maryrose/Raphael/Fikiri | TO BE DONE
Conduct regional stakeholders and Extended Districts PHC meetings for HPV vaccine introduction | [7 empty] | Gadau | Raphael/Maryrose/Fikiri | TO BE DONE
Conduct orientation of Health facility workers on interpersoinal /face to face communication and effective communication methods for delivering Cervical cancer and HPV caccine related message | [7 empty] | Gadau,RIVOs,DIVOs | Raphael,Fikiri | TO BE DONE
Conduct Meetings with Religious and Influential leaders to sentitize them on Benefits of HPV vaccine and solicit their supoport | [7 empty] | Gadau,RIVOs,DIVOs | Raphael,Fikiri,Blessing | TO BE DONE
Conduct HPV vaccine introduction meeting with Teachers ,WDC, Village Councils ,CHWs and parents to sensitize them on the benefits of the vaccine and their roles and responsibilities for the successful introduction | [7 empty] | DMOs/DIVOs/DRCHCOs | Local existing CSOs | TO BE DONE
Conduct workshop to review and update HPV vaccine introduction IEC materials(Posters,Leaflets,Fact sheet,FAQs, Jingles,TV and Radio Sports and advert) | [7 empty] | Gadau | Blessing | DONE
Pretesting of IEC materials for HPV introduction | [7 empty] | Gadau | Fikiri/Raphael/Blessing | TO BE DONE
Printing and distribution/dessemination HPV vaccine IEC materials | [7 empty] | Gadau | Fikiri/Silayo/WHO | TO BE DONE
Identify Key/Influencial people and CHWs to detect and trace rumours ,myths,misconception regarding HPV Vaccine | [7 empty] | Gadau/DIVOs/DRCHCOs/VEOs,VCPs | Immunization Partners | TO BE DONE
Develop specific messages to adress misconception,myths and AEFI on HPV vaccine | [7 empty] | Gadau | Blessing | DONE
Prepare technical guidance on what,who,when and how to respond to rumours,misconception on HPV vaccines | [7 empty] | Gadau | Blessing | DONE
Identify key media houses to be engaged and establish mechanism for collaboration to suport HPV vaccine introction from National to Subnational levels - Lobby for for free airtime | [7 empty] | Gadau | Maryrose,Raphael,Fikiri | DONE
Inform and Sensitize community on availability and benefitst of HPV vaccine through Social media such as whatsup,instagram,Facebook etc | [7 empty] | Gadau | Raphael/Mabwe/Maryrose | TO BE DONE
Prepare schedule for radio/TV programme talk show on HPV vaccine Introduction | [7 empty] | Gadau/Catherine | Maryrose,Fikiri,Raphael | TO BE DONE
Air TV and Radio spots for HPV vaccine introduction | [7 empty] | Gadau | Silayo/Maryrose | TO BE DONE
Engagement of communication companies such as Vodacom,Tigo,Airtel,Hallotel and lobby for free sms on HVP introduction(Consider Comprehensive messages for cervical cancer prevention-Primary and secondary) | [7 empty] | Gadau | Raphael/Maryrose | TO BE DONE
ACSM subtechnical working group to plan ,organise and prepare roadmap for National Launching for HPV vaccine ; -Agenda,Speeches,Press release,Talking notes,edutainment groups,vaccine administration demonstration | [7 empty] | Gadau | Raphael/Maryrose/Silayo | ONGOING
Identify Key Stakeholders to Participate in National Launch | [7 empty] | Gadau/RMOs/DMOs | Raphael/Maryrose | DONE
Conduct Launching (National and Subnational) | [7 empty] | Gadau/RMOs/DMOs | Raphael/Maryrose | TO BE DONE
Post Introduction Monitoring and Evaluation of ACSM for HPV introduction | [7 empty] | Gadau/RMOs/DMOs | Raphael/Maryrose | TO BE DONE

## NovemberDecember timeline (hidden)
ACTIVITIES | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | RESPONSIBLE(IVD) | RESPONSIBLE(PARTNERS)
Develop HPV vaccine introduction advocacy orientation Package(Fact sheets,PPT) | [7 empty] | Gadau/Frida | Raphael/Maryrose/Fikiri
Draft and share official letters to inform all key stakeholders to fully participate and be involved in HPV vaccine introduction advocacy activities(Link with PORLG and MOEVT) | [7 empty] | Gadau | Maryrose/Raphael
Conduct workshop to review and update HPV vaccine introduction IEC materials(Posters,Leaflets,Fact sheet,FAQs, Jingles,TV and Radio Sports and advert) | [7 empty] | Gadau | Blessing
Pretesting of IEC materials for HPV introduction | [7 empty] | Gadau | Raphael/Silayo/Blessing
Develop specific messages to adress misconception,myths and AEFI on HPV vaccine | [7 empty] | Gadau | Blessing
Prepare technical guidance on what,who,when and how to respond to rumours,misconception on HPV vaccines | [7 empty] | Gadau | Blessing
Identify key media houses to be engaged and establish mechanism for collaboration to suport HPV vaccine introction from National to Subnational levels - Lobby for for free airtime | [7 empty] | Gadau | Maryrose
Inform and Sensitize community on availability and benefitst of HPV vaccine through Social media such as whatsup,instagram,Facebook etc | [7 empty] | Gadau | Raphael
Engagement of communication companies such as Vodacom,Tigo,Airtel,Hallotel and lobby for free sms on HVP introduction(Consider Comprehensive messages for cervical cancer prevention-Primary and secondary) | [7 empty] | Gadau | Raphael/Maryrose

## AUDIENCES
AUDIENCES FOR HPV COMMUNICATION INTERVENTIOS
COMMUNICATION OBJECTIVES | AUDIENCE | MESSAGE CONTENTS | RESPONSIBLE PERSON/GROUP | ACTIVITIES | MATERIALS | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-18 | 2018-06-18
To create awareness to key stakeholders and audiences from National to Community Level for smooth introduction of HPV Vaccine | Eligible girls | · Basic facts about cervical cancer | · Teachers | · Sensitization meeting | · HPV leaflet | bar: 2018-02-01; 2018-04-01 to 2018-06-18
|  | · Basic facts about the preventive HPV vaccine | · Health workers | · Distributing materials | · Formal letters | bar: 2018-02-01; 2018-04-01 to 2018-06-18
|  | · Benefits of being vaccinated | · Religious leaders | · Radio and TV message dissemination | · Posters | bar: 2018-02-01; 2018-04-01 to 2018-06-18
|  | · Eligibility | · Parents |  | · Radio and TV spots | bar: 2018-02-01; 2018-04-01 to 2018-06-18
|  | · Their role in HPV vaccination | · CHWs | bar: 2018-02-01; 2018-04-01 to 2018-06-18
· Community leaders | bar: 2018-02-01; 2018-04-01 to 2018-06-18
To create awareness to key stakeholders and audiences from National to Community Level for smooth introduction of HPV Vaccine | Parents | · Facts about cervical cancer and prevention | · Health workers | · Orientation sessions | · HPV leaflet | bar: 2018-02-01; 2018-04-01 to 2018-06-18
|  | · Availability of vaccine | · Community Health Workers | · Distributing materials | · Radio and TV messages | bar: 2018-02-01; 2018-04-01 to 2018-06-18
|  | · Facts about the vaccine | · Teachers | · Radio messages | · Fact sheet | bar: 2018-02-01; 2018-04-01 to 2018-06-18
|  | · Their role & responsibility | · Religious leaders | · Publish information in local media | · Posters | bar: 2018-02-01; 2018-04-01 to 2018-06-18
|  | · Other Primary preventive measures | · Community leaders | · Community film shows | bar: 2018-02-01; 2018-04-01 to 2018-06-18
| School administration, School management and teachers | · Facts about cervical cancer and prevention | · District education officers (primary and secondary) | · Orientation sessions | · HPV leaflet | bar: 2018-04-01
To create awareness to key stakeholders and audiences from National to Community Level for smooth introduction of HPV Vaccine |  | · Availability of preventive vaccine | · Ward education officer | · Distributing materials | · HPV guidebook | bar: 2018-04-01
|  | · Facts about the vaccine | · DIVO | · Radio messages | · Radio and TV messages | bar: 2018-04-01
|  | · Age-appropriate approaches to addressing cervical cancer with children | · School health coordinators | · Publish information in local media | · Fact sheet | bar: 2018-04-01
|  | · Their roles & responsibilities | · District community health coordinators | · Official letter | · Posters | bar: 2018-04-01
· Health workers | bar: 2018-04-01
· CHWs | bar: 2018-04-01
To create awareness to key stakeholders and audiences from National to Community Level for smooth introduction of HPV Vaccine | Community leaders | · Burden of disease | · Health workers | · Orientation sessions | · HPV leaflet | bar: 2018-02-01; 2018-04-01
|  | · Importance and benefits of prevention | · Community Health Workers | · Distributing materials | · HPV guide | bar: 2018-02-01; 2018-04-01
|  | · Availability of preventive vaccine | · Teachers | · Radio messages | · Radio and TV messages | bar: 2018-02-01; 2018-04-01
|  | · Facts about the vaccine | · Religious leaders | · Fact sheets | bar: 2018-02-01; 2018-04-01
|  | · Key messages to help dispel misinformation | · LGA director | bar: 2018-02-01; 2018-04-01
· Their roles & responsibilities | bar: 2018-02-01; 2018-04-01
To create awareness to key stakeholders and audiences from National to Community Level for smooth introduction of HPV Vaccine | Members of PHC committee at District levels | · Burden of disease | · IVD | · PHC meeting | · PPT
|  | · Importance and benefits of prevention | · RIVO |  | · Fact sheet
|  | · Availability of preventive vaccine | · DIVO |  | · Leaflets
· Facts about the vaccine
· Key messages to help dispel misinformation
· HPV vaccine introduction phases in Tanzania
To create awareness to key stakeholders and audiences from National to Community Level for smooth introduction of HPV Vaccine |  | · Their roles & responsibilities
| Stakeholders at regional level | · Burden of disease | · IVD | Stakeholders meeting | · PPT | bar: 2018-02-01
|  | · Importance and benefits of prevention | · RIVO |  | · Fact sheet | bar: 2018-02-01
|  | · Availability of preventive vaccine | · DIVO |  | · Leaflets | bar: 2018-02-01
· Facts about the vaccine | bar: 2018-02-01
· Key messages to help dispel misinformation | bar: 2018-02-01
To create awareness to key stakeholders and audiences from National to Community Level for smooth introduction of HPV Vaccine |  | · HPV vaccine introduction phases in Tanzania | bar: 2018-02-01
· Their roles & responsibilities | bar: 2018-02-01
| National Extended high level advocacy meeting | · Burden of disease | · Permanent Secretary | · Extended high level advocacy meeting | · PPT | bar: 2018-02-01
|  | · Importance and benefits of prevention | · CMO |  | · Fact sheet | bar: 2018-02-01
|  | · Availability of preventive vaccine | · IVD Program Manager |  | · Leaflets | bar: 2018-02-01
· Facts about the vaccine | bar: 2018-02-01
To create awareness to key stakeholders and audiences from National to Community Level for smooth introduction of HPV Vaccine |  | · Modalities of HPV vaccine introduction in Tanzania | bar: 2018-02-01
· HPV vaccine Introduction Phases in Tanzania | bar: 2018-02-01
· Key messages to help dispel misinformation | bar: 2018-02-01
Their roles & responsibilities | bar: 2018-02-01
| MOHCDGEC officials and partners meeting | · Burden of disease | · Permanent Secretary | · MOHCDGEC officials and partners meeting | · PPT | bar: 2017-12-01
|  | · Importance and benefits of prevention | · CMO |  | · Fact sheet | bar: 2017-12-01
To create awareness to key stakeholders and audiences from National to Community Level for smooth introduction of HPV Vaccine |  | · Availability of preventive vaccine | · IVD Program Manager |  | · Leaflets | bar: 2017-12-01
· Facts about the vaccine | bar: 2017-12-01
· Key messages to help dispel misinformation | bar: 2017-12-01
· Introduction phases in Tanzania | bar: 2017-12-01
· HPV vaccine introduction phases in Tanzania | bar: 2017-12-01
· Their roles & responsibilities | bar: 2017-12-01