First Year Work Plan quarterly overview

For salaried posts

| Name of post | Fuse Power-Up Nutrition & Wellbeing Coordinator |
| --- | --- |
| Name of organisation | Fuse Youth Cafe |
| Expected start date (write existing, if the worker is already in post) | January 2019 |
| Hours per week | 25 |

| Time period | Activities the worker will be engaged in e.g. The development and support of a healthy youth steering group and programme of physical activity and healthy cooking sessions. | Key achievements for the worker as you progress through the year e.g., |
| --- | --- | --- |
| Quarter 1 | - Provide support to the existing healthy youth steering group. - Liaise with external agencies who can deliver support and training to complement the programme. - Support the children and young people to design a consultation exercise for their peers and Fuse staff to investigate attitudes towards healthy eating and how Fuse can become healthier. - Work with the Healthy Steering Group and Activities Coordinator to plan the programme of physical activity and healthy cooking sessions. - Provide support to the children and young people to work towards appropriate accreditation e.g. Hi 5; Dynamic Youth; Youth Achievement or Community Achievement Awards. - Collaborate with Activities Coordinator to develop the food and exercise “Journey to Success” diaries. | - Healthy Youth Steering group supported plan of action. - Consultation exercise designed and carried out. - Programme plan for the physical activity and cooking sessions. - Prototype of Food and exercise diary presented to steering group and staff with guidelines. |
| Quarter 2 | - Continue to support the healthy youth steering group. - Collect baseline data for measurement of effectiveness of programme e.g. such as what they eat, meals missed, junk food consumed, how much of their 5 a day fruit & vegetables they eat, cooking and food preparation abilities, participation in exercise and general feelings of health & well-being. - Launch of the food and exercise diaries with guidelines for supporting staff - Set up system of one-to-one support for personal journey to success. - Commence healthy eating sessions. - Continue to provide support to the children and young people with appropriate level accreditation Hi 5; Dynamic Youth; Youth Achievement; Community Achievement Awards. | - Baseline information gathered. - 2 x healthy cooking sessions each week – junior & senior club for up to 15 people - 2 x physical activity/exercise sessions each week – junior & senior club for up to 15 people |
| Quarter 3 | - Continue to support the healthy youth steering group. - Conduct 3 month progress review information to measure changes in attitudes and awareness of healthier lifestyles as well as increased uptake of physical activity, consumption of healthier foods etc. - Continue to publicise the project to the children & young people it is intended to support. - Continue to provide physical activity sessions. - Continue to provide support to the children and young people with accreditation. | - Progress review information collected. - 2 x healthy cooking sessions each week – junior & senior club for up to 15 people - 2 x physical activity/exercise sessions each week – junior & senior club for up to 15 people |
| Quarter 4 | - Continue to support the healthy youth steering group. - Conduct further 3 month progress review (this may be 3 month for participants that were new at last quarter or may be a 6 month review for original participants) information to measure changes in attitudes and awareness of healthier lifestyles as well as increased uptake of physical activity, consumption of healthier foods etc. - Continue to publicise the project to the children & young people it is intended to support. - Continue to provide healthy cooking sessions. Continue to provide support to the children and young people with Hi 5; Dynamic Youth; Youth Achievement and Community Achievement Awards. - Work with healthy youth steering group to evaluate effectiveness of project, using baseline and review data collected. - Plan for 2nd year of project, making appropriate changes as per evaluation. | - Further progress review information collected - 2 x healthy cooking sessions each week – junior & senior club for up to 15 people - 2 x physical activity/exercise sessions each week – junior & senior club for up to 15 people - Evaluation results for 1st year. - Workplan for 2nd year. |