Scope of Work

Organizing the Club Fen Water Cup 2026 – Futsal Tournament

Prepared For: Club Fen / MWSC
Tournament Name: Club Fen Water Cup 2026
Event Month: April 2026

Tentative proposed Date:  23rd April 2026 – 1st May 2026
Number of Teams: 10 (Participating from MWSC)

Purpose of This Document

This Scope of Work is prepared to provide detailed information to interested organizers who wish to undertake the responsibility of organizing the Club Fen Water Cup 2026 futsal tournament. The objective is to ensure a smooth, professional, and enjoyable tournament for all participants and attendees, with clear deliverables and responsibilities.

Scope of Services Required from the Organizer

The selected organizer will be responsible for end-to-end planning and execution of the tournament, including the following:

1. Futsal Ground

- Identify, book, and manage a suitable futsal ground that can accommodate the full tournament schedule and ceremonies.

- Ensure availability of the venue for all match days, including Opening Ceremony, and Closing Ceremony.

- Ground should have basic amenities such as lighting and seating/viewing space.

2. Referees and Match Commissioners

- Arrange qualified referees and match commissioners for each match.

- Maintain neutrality and fairness throughout the tournament.

- Provide official kits and tools for referees if needed.

3. Administrative Work

- Handle all administrative aspects of the tournament, including:

  - Preparation of match fixtures and schedules.

  - Prepare the tournament rules and guidelines

  - Maintenance of official match records and statistics.

  - Match coordination, scorekeeping, and result announcements.

  - Communication with team managers or captains for updates and regulations.

  - Conduct the Match draw

4. Ground Preparation and Event Management

- Prepare the ground before each match day with necessary arrangements:

  - Line marking, nets, cleaning, and safety checks.

- Event management for the entire tournament, including:

  - Printing and Installation of banners, backdrops, and branding materials (all designs will be provided by Club Fen).

  - Cleanliness and upkeep of the ground and surroundings.

5. Opening and Grand Closing Ceremonies

- Organize a professional Opening Ceremony, which may include:

  - Welcome speech, team introductions, guest participation, and brief entertainment if applicable.

- Conduct a vibrant Grand Closing Ceremony, featuring:

  - Presentation of awards and recognitions.

  - Guest speeches and photo sessions.

  - Brief entertainment if applicable.

6. Awards and Recognitions

The organizer must arrange the following awards and ensure they are ready for presentation during the Grand Closing Ceremony. All items should be a customized , good quality and professionally packaged:

- Gold Medals (For all members of the Champion team)

- Silver Medals (For all members of the Runner-up team)

- Player of the Match – Futsal (For each match)

- Best 5 Players – Futsal (Tournament-wide)

- Best Supporters Team

- Fair Play Team

- Top Scorer

- King of the Tournament (Crown and trophy)

- Fair Player

- Fans Player of the tournament

- Any other award (if applicable)

7. Communication and Approvals

- All arrangements must be communicated to and approved by Club Fen before final confirmation or execution.

- The organizer must maintain close coordination with Club Fen throughout the planning and execution stages.

- Regular updates and progress reports are expected.

9. Safety and Medical Arrangements

- Organizer must ensure basic first aid and emergency medical services (e.g., a standby medic or ambulance contact) are available during match days.

10.Opening and Grand Closing Ceremonies

The organizer Shall plan and execute professional and engaging ceremonies to mark the opening and conclusion of the tournament, ensuring a memorable experience for participants and attendees.

a. Grand Opening Ceremony

- Organize a well-coordinated Opening Ceremony prior to the commencement of the first match.

- The ceremony may include:

  - Welcome address

  - Team introductions

  - Guest participation (if applicable)

- Ensure proper sound system, coordination, and smooth flow of the ceremony.

b. Grand Closing Ceremony

- Conduct a vibrant Grand Closing Ceremony at the conclusion of the tournament.

- The ceremony shall include:

  - Presentation of trophies, medals, and individual awards

  - Guest speeches (if applicable)

  - Photo sessions

  - A short  performance or entertainment segment to celebrate the conclusion of the tournament

- Ensure all arrangements are professional, well-timed, and aligned with Club Fen branding.

11. Social Media Coverage, Photography & Videography

The organizer shall be responsible for providing comprehensive media coverage of the tournament to support internal engagement and promotional use by Club Fen / MWSC. This shall include the following:

a. Photography

- Professional photography coverage for:

  - Opening Ceremony

  - Draw Ceremony

  - Match days

  - Key moments (goals, celebrations, crowd support)

  - Grand Closing Ceremony and award presentations

- A curated set of high-quality edited photographs to be delivered after match day (20 photo each match).

- Photos must be suitable for social media, internal communications, and archival use.

b. Videography

- Production of one short highlight video (approximately 1–3 minutes) summarizing the entire tournament.

- The final video should be suitable for social media sharing and internal use.

c. Social Media Content Support

- Provide content support such as:

  - Short match highlight clips (where applicable)

  - Behind-the-scenes moments

  - Key event visuals

- All raw and edited media content shall be shared with Club Fen.

12. Additional Notes

- Organizers are encouraged to propose value-added services or enhancements (e.g., photography, videography, live match updates, refreshments, entertainment segments) during the proposal stage.

- Although value-added services can be included in the proposal, Club Fen will decide which services will be required and approved for implementation.

- Budget and cost estimates must be submitted in detail and will be reviewed separately by Club Fen.