	Week
	Duration
	Activity

	
	
	Mobilization, site setup, safety arrangements, site clearing and demolition

	
	
	Excavation for foundations and trench preparation

	
	
	Lean concrete, foundation concrete, foundation beams and column stumps

	
	
	Formwork, reinforcement installation and concrete curing

	
	
	Block masonry walls, plastering works, waterproofing and backfilling

	
	
	Earth filling, sand blinding and crushed stone sub-base installation

	
	
	Final ground leveling, paving blocks, curb stones and drainage system

	
	
	PVC fencing posts, GI pipe framework and goal fence installation

	
	
	Entrance gate fabrication, goal posts, benches and lighting pole installation

	
	
	Electrical conduits, cable laying, distribution board and wiring works

	
	
	Artificial turf installation, adhesive application, seaming and silica sand infill

	
	
	Court marking, floor painting, wall painting and floodlight installation

	
	
	Testing & commissioning, snag rectification, final cleaning and handover


Work Schedule
