| Week | Duration | Activity |
| --- | --- | --- |
|  |  | Mobilization, site setup, safety arrangements, site clearing and demolition |
|  |  | Excavation for foundations and trench preparation |
|  |  | Lean concrete, foundation concrete, foundation beams and column stumps |
|  |  | Formwork, reinforcement installation and concrete curing |
|  |  | Block masonry walls, plastering works, waterproofing and backfilling |
|  |  | Earth filling, sand blinding and crushed stone sub-base installation |
|  |  | Final ground leveling, paving blocks, curb stones and drainage system |
|  |  | PVC fencing posts, GI pipe framework and goal fence installation |
|  |  | Entrance gate fabrication, goal posts, benches and lighting pole installation |
|  |  | Electrical conduits, cable laying, distribution board and wiring works |
|  |  | Artificial turf installation, adhesive application, seaming and silica sand infill |
|  |  | Court marking, floor painting, wall painting and floodlight installation |
|  |  | Testing & commissioning, snag rectification, final cleaning and handover |

Work Schedule