| Service Development | Aim | Milestones | Lead | Timescale |
| --- | --- | --- | --- | --- |
|  | Engage with volunteers, clinical staff and patients to evaluate the current pilot & deploy continual improvement through PDSA cycles | Implement an evaluation plan using measurement tools such as surveys, interviews, a focus group and observation to analysis patients outcomes | Project Manager/volunteer Coordinator | 04/2019 commence 06/2016 completed PDSA cycles throughout life of the project |
|  | Review Job role and current training provided | Co – design current volunteer role description and training with volunteers and clinical teams and Health Education England | Project Manager | 04/2019 commence 06/2019 completed |
|  | Create and maintain links with key partners and local Charites | Engage with key partners; e.g. Age Uk and charities; to promote the project and share good practises and learning |  | 04/2019 commence 06/2019 review 07/2019 complete |
| Recruitment | To recruit 100 + volunteers to the dining companions role | Hold and attend recruitment fairs to attract volunteers to the role from all backgrounds. | Project Manager/Volunteer recruitment officer | 06/2019 commence Rolling programme 08/2019 target 50 12/2019 target 100 |
|  |  | Continue raising the profile of the volunteers in the local media to attract new recruits |  |  |
|  |  | Liaise with board level directors to implement employer supported volunteering within the trust and at other external organisations e.g. Salford City Councils – 24hours to make a difference campaign. |  |  |
| Training | Implement new training package to volunteers | Work with Health Education England to develop a training package for the dining companions role | Project Manager | 09/2019 commence Rolling programmes |
|  |  | Test out new approaches to training including group training and eLearning |  |  |
| It Systems | Evaluate and redesign current It booking systems | Evaluate the current IT booking systems and redesign a system which can be maintained internally. | Project Manager | 09/2019 |
| Expansion | Roll out project to 5 x new wards | With support of clinical leads identify 5 wards that would most benefit from dining companions and roll out the project across selected wards | Project Manager/Clinical Lead | 09/2019 |
|  |  | Hold engagement sessions with clinical staff to embed the importance of having dining companions on the ward is. Create printed and web based guidance for ward staff on the benefits of having dining companions and how best to support volunteers in their roles |  |  |
|  | Scope for further expansion across the Northern Care Alliance | Identify other key areas across Pennine Acute Trusts sites that would benefit from implementing the Dining Companions and work with their volunteering team to roll the model across their organisations. |  | 12/2019 |
|  | Adopt proposed innovation | Create a test of change for the proposed innovation ‘Home from Hospital’ following models designed by other NHS trusts and piloting the scheme on of our wards |  | 03/2020 |
| Sustainability | Measure impact | Measure impact and generate evidence of impact by using Helpforce’s Insight and Impact Framework |  | 03/2020 -06/2020 |
|  | Sustain the innovation for ongoing future success | Scope for further potential funding opportunities and trust buy in of the project |  | 03/2020 - 06/2020 |