## Timeline
| March |  |  |  |  | April |  |  |  | May |  |  |  |  | June |  |  |  | July |  |  |  | Aug |  |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  |  | Dec |  |  |  | Jan |  |  |  |  | Feb |  |  |  | March |  |  |  | April
Action | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25
Mobilisation and Project Set Up
Secure project leads
Ensure compliance with lone working policy
Engage key community leads (falls prevention, better bones, physio)
Plan induction modules and engage key personnel
Establish steering group
Service Planning
Develop and test inclusion / exclusion criteria. Scope patient cohort size (demand)
Finalise referral process with physio lead
Confirm exit strategy and plan for implementing it
Developing keys resources for the service; role profile, exercise booklets, delivery manual, checklists, onward referral document
Communicate referral process to physio teams on participating wards
Recruitment of Volunteers
Finalise role description and engage relevant stakeholders to advertise recruitment
Advertise volunteer positions
Shortlist candidates
Interview candidates
Training
Secure dates, place and tutors for training
Develop training material
Deliver training
Service Launch
Go live, week 1 of home exercise programme
Gather intelligence on service improvement
Ongoing monitoring of risks, pathways and outcomes
Evaluation
Create outcome model for service
Create data model for service
Develop data collection tools
Engage BI leads
Collect data and share with Helpforce
Analyse data
Develop business case to sustain service
Write final evaluation report
Review final report (steering group page turn)
Close and final assets
Finalising resources for Helpforce Adopt and Adapt Programme