## Slide 1: Drivers for Change
Aim
To increase requests for volunteers by 40%
In first
3 months
1st Drivers
Requests from Staff
Deployment
2nd Drivers
Staff awareness of volunteers role
Staff informed on how to request volunteers
Assessing patients suitability and requirements for volunteers
Complete evaluation
Easy request process
Educating volunteers
Actions
Create information packs for volunteers/ staff
Collect request information from wards
Website / Intranet - Info on how to request volunteers
Raise awareness with leadership / key contacts to cascade to staff
Order phones for volunteers
Matching skills to needs
Volunteer Satisfaction
Recruit and train volunteers (from current and new cohort)
Train Team Leaders
Volunteers
Collect volunteer feedback
Volunteer Steering Group
Organise Masterclass
Assign Contact Person in key areas for volunteers

## Slide 2: PDSA Cycle
Action
Project manager in post
Plan
Revise and finalise Job Description of new role
Do
Interview
Study
Recruitment parameters
Set up interview dates
Appoint
PDSA 1 | Staff Recruitment |  |  |  | 
JD | Nancy Whiskin | GREEN | 0.5 |  | 
Advert | Nancy Whiskin | GREEN | 3 |  | 
Shortlist/Interview | Nancy Whiskin | GREEN | 1 |  | May-24
Complete recruitment of staff to support programme including backfill | Nancy Whiskin | GREEN | 3 |  | Jul-08

## Slide 3: PDSA Cycle
Action
Roll out confirmed tools
Plan
List set of possible evaluation tools
Do
Create tools
Study
Pilot evaluation tools in two locations for 1 month (WXH, RLH)
Discuss
Teach all to use and understand data tools
PDSA 2 | Evaluation Tool and Methodology |  |  |  | 
Plan and create evaluation tools | Nancy Whiskin Vanessa Lodge | GREEN | 3 |  | Apr-26
Discuss, consider and design evaluation tools | Nancy Whiskin, Martin Worwood, Vanessa Lodge, Richard Lee | GREEN | 1 |  | Apr-27
Meet with HF to discuss | Nancy Whiskin, Vanessa Lodge, Richard Lee | AMBER | 1 |  | Apr-27
Finalise Evaluation tools and adopt | HelpForce, Nancy Whiskin, Richard Lee | AMBER | 0.5 |  | 

## Slide 4: PDSA Cycle
Action
Plan
Devise Comms action plan
Do
Study
Evaluate no. of requests for volunteers
Order items
Decide on correct items for delivering the project
Discuss with finance
Discuss with services areas about the project e.g site huddle, site manager
Pplan pathway
Evaluate volunteer response
Evaluate staff response and feedback
Volunteer focus group
PDSA 3 | Infrastructure |  |  |  | 
Communication Plan, Website, promotion cards, | Nancy Whiskin & Marufa Begum | Amber | 3 | Starting June -18 | 
Pathway Mapping of call outs | Nancy Whiskin & Marufa Begum | Amber | 2 | Starting June -18 | 
Devise Training programme and instruction manuals & governance | Nancy Whiskin &Richard Lee | Amber | 4 | Starting June -18 | 
Procurement of capital items | Nancy Whiskin | Amber | 10 | Starting June -18 | Please note this was started in February
Infrastructure in place roll out of project | Nancy Whiskin, Richard Lee, | Amber | 10 | Jul-01 | 

## Slide 5: PDSA Cycle
Action
Plan
Do
Book rooms for training
Study
Discuss training modules with relevant dept
Contact volunteers
Adapt slides accordinglu
PDSA 4 | Recruitment and Training |  |  |  | 
Set up training rooms and placement sessions team leaders and floaters | Richard Lee, Administation support | Amber | 3 | 20 | 
Volunteer training checks | Richard Lee, Marufa Begum | Amber | 10 | Ongoing | 

## Slide 6: PDSA Cycle
Action
Pathway map process of requests to volunteers
Plan
Target current volunteers for
Do
Bulletin
Study
Monitor number of volunteers recruited
Stop recruitment of patient champions
Change Website
Training programmes in place
Training manual
Deploy
PDSA 6 | Recruiting , training |  |  |  | 
Recruit from current volunteers via bulletin | RL |  | Ongoing |  | 3 cycle completed Sept 19
Stop all other recruitment focus AR only | RL |  | Ongoing |  | 
Ensure training rooms are booked | RL | Green | Ongoing |  | Complete
Complete training manual | NW | Green | Ongoing |  | Compete

## Slide 7: PDSA Cycle
Action
Plan
Pathway map
Do
Deploy volunteers
Study
What works what doesn’t
Set up volunteer focus group
PDSA 5 | First Deployment on pilot site |  |  |  | 
Communicate role via website | Nancy Whiskin, Richard Lee, | Green | 3 | 40 | 
Distribute cards advising of service | Admin, volunteers | Green | 5 | 45 | 
Set up call hubs for team leaders | RL NW | Amber | 5 | 50 | 
Attending Huddles | Team Leaders, Sitebased staff | Green | 4 | 51 (ongoing) | 
Deployment of volunteers | All |  | 60 Deployed |  | 

## Slide 8: Communication Plan
Internal Communication
Website - WeShare (Intranet)
Accessible by all staff:
Information for staff on how to “Request an Active Response Volunteer”
Who are Active Response Volunteers?
Action:
A5 Flyer “Do you need help?” contact info for requests
External
Communication
Draft flyer design – June 2019
Website – Barts Health Webpage
Accessible by public
Application to become an AR volunteer
Information on what AR volunteers do
Update Volunteer pages to reflect on new roles
Redesigned flyer after staff feedback - July 2019
Flyer distribution to all critical areas of support - July 2019
Distribute flyer to staff during volunteers week – June 2019
August 2019 – website going live
August 2019 – website going live
Meeting with Communications Team Feb – July (ongoing)
Provide website information, design layout and upload relevant documents – May 2019
Information Packs / Manuals
Provide website information, design layout and upload relevant documents – May 2019
Volunteers Bulletin
Informed current volunteers of new role and how to get involved