## Front cover
Website Redesign Planning Template
Click on the next tab to get started!
Have questions? Need further help during the redesign process? Let's talk about it.

## Instructions
How to Use This Resource
Whether you’re working with an agency or redesigning inhouse, this Excel document will help you thoroughly plan and track the progress of your website redesign.
To help make the many moving pieces of a website redesign a little easier to digest, we've segmented the process into nine stages.
Use the tabs below to navigate to each stage, and be sure to thoroughly complete stages 1 and 2 before moving on. (While stages 1 and 2 primarily involve benchmarking, taking inventory, and answering important questions before you begin your website redesign, the latter stages are for tracking your redesign while it's in progress.)
Stage 1 - Strategy
Stage 2 - Plan
Stage 3 - Sitemap
Stage 4 - Content
Stage 5 - Budget
Stage 6 - Timeline
Stage 7 - Prelaunch
Stage 8 - Launch Day
Stage 9 - Post Launch

## Stage 1 - Strategy
WEBSITE REDESIGN STAGE 1: STRATEGY
A) Benchmark Your Current Metrics. | - Your Data -
Number of visits/visitors/unique visitors (monthly average) | x
Bounce rate (monthly average) | x
Time on site (monthly average) | x
Top performing keywords (in terms of rank, traffic and lead generation) | x
Number of inbound linking domains | x
Total number of new leads/form submissions (per month) | x
Total amount of sales generated (per month) | x
Total number of total pages indexed | x | Three tools to use when planning a website redesign
Total number of pages that receive traffic | x
B) Determine Your Goal(s). | - Your Answer -
What is your primary, overall goal of the redesign? | x
Do you have any secondary or complementary goals related to the redesign? | x
C) Define Your Brand. | - Your Answer -
What is your business's message/unique value proposition? | x
Is it (message and/or branding) changing or staying the same? | x
If it is changing, what about it needs to change? | x
D) Define Your Buyer Persona. | - Your Answer -
Do you currently have a clearly defined target audience? | x
Is this audience changing as part of this redesign? | x
Does your branding and content currently align with that audience? | x | Click here to learn more about creating donor personas for your nonprofit.
Click here to learn more about creating buyer personas for your business.
E) Analyze the Competition | - Your Answer -
Are there competitor sites that you really like? If so, which ones? | x
What are the top 3 most competitive keywords for your industry? | x
Who are your top-ranked competitors? | x
Before you begin planning your redesign, document your current performance metrics using the fields to the left.
If you don’t have access to this information, you'll want to add a tool like Google Analytics for better tracking and visibility into site performance.
TIP: Keep note of which tools you used to determine these benchmarks. Ideally you’ll want to use the same exact tools when collecting post-design metrics – otherwise you’ll be comparing apples to oranges!
Be really clear about why you’re doing the redesign in the first place and tie it to measurable results. Here’s so examples to consider.
Do you want to increase the amount of leads your website generates?
Do you want your website to provide more information to your website visitors?
Do you want to make it easier for users to find information on your site?
Are you adding features to your site like eCommerce, subscriptions or donations?
Once you have a clear set of goals be sure to communicate your goals with your team, designer, or agency.
Before you begin crafting your content, be clear about your branding and messaging so that it’s consistent across your entire website.
A new visitor should immediately understand what you do, how it relates to them, and why they should stay on your website and not flee to your competitors.
Your website is not just about you. When a visitor asks, “what’s in it for me?”, speak to them in their language by designing content around buyer personas.
Buyer personas are fictional representations of your ideal customers, based on real data about customer demographics and online behavior, along with educated speculation about their personal histories, motivations, and concerns.
While we don’t recommend obsessing over your competitors, it helps to know how you compare. Take a look at competitor websites, and note what you like and don’t like about them. This is not meant to copy them, but to uncover what you can do better.

## Stage 2 - Plan
WEBSITE REDESIGN STAGE 2: PLAN
A) Questions to Consider | - Your Answer -
What do I currently like and dislike about my website? | x
What is missing from the current website? (Think are you missing lead generation capabilities, eCommerce, marketing automation, calendar, etc.?) | x
How does your current site compare to your goals? | x
What's the first impression I want to give my target audience? | x
Will this be a whole new website or are there small changes that can be made? | x
What is a realistic timeline for this redesign? (Define a target date.) | x
What is our budget for this project? | x
Can we do this work in-house or do we need to hire someone? | x
B) Website Maintenance Considerations | - Your Answer -
How many people will be managing the website? | x
Will the people managing the website be internal or an external agency? | x
If internal, what are the technical capabilities of your team? | x
C) Taking Inventory of Your Existing Assets | - Your Answer -
What is your most shared or viewed content? | x
What are your most trafficked pages? | x
What are your most ranked pages? | x
As you start planning your website redesign, ask yourself some of the questions listed to the left. Write your answers in the spaces provided.
TIP: You may want to track each of the items to the left in a separate spreadsheet.
You can use a tool like screamingfrog.co.uk/seo-spider/ or xenus-link-sleuth.en.softonic.com to crawl all of the pages of your site and create an exportable inventory.
TIP: Don’t focus so hard on what Content Management System (CMS) to use. Let the website experts proposing solutions to you provide input here.
You focus more on if you want internal or external maintenance after launch, how technical your staff is to handle changes, and what all parts of the website you’d be wanting to edit on a regular basis.

## Stage 3 - Sitemap
WEBSITE REDESIGN STAGE 3: SITEMAP
Site Architecture | - Progress (TBD, in progress, or complete?) - | Due Date | Owner (who's responsible for this?)
Plan the new site architecture/structure. | x | mm/dd/yy
Define which pages will be part of your main/secondary navigation. | x | mm/dd/yy
Put together a draft outline/sitemap of the new website to be designed and built. | x | mm/dd/yy
Example Sitemap
Page Name | Current Location (URL) | New Planned Location (URL)
Home
Our Services
- Service 1
- Service 2
- Service 3
Our Products
- Cart page
- Checkout page
- Shop page
About Us
- History
- Culture
Careers
Contact

## Stage 4 - Content
WEBSITE REDESIGN STAGE 4: CONTENT
A) Define Your Content Plan | - Progress (TBD, in progress, or complete?) - | Due Date | Owner (who's responsible for this?)
Outline which content stays. | x | mm/dd/yy
Outline which content goes. | x | mm/dd/yy
Outline which content needs to be rewritten. | x | mm/dd/yy |  | Three tools to help you when planning content and what needs redesigned
B) Create an Ongoing Content Strategy. | - Progress (TBD, in progress, or complete?) - | Due Date | Owner (who's responsible for this?)
This is a great time to start (or revamp) your business's blog. | x | mm/dd/yy |  | Download our free Content Strategy Workbook
TIP: Planning out your URL mapping can be as simple as listing out your old URLs in a spreadsheet and then noting what the corresponding new URLs will be. (Someone technical will need to apply the 301s later.)

## Stage 5 - Budget
WEBSITE REDESIGN STAGE 5: BUDGET
Design and Development Budget | - Planned Budget -
General website design and development | -
eCommerce integration and development | -
Features (calendars, careers, integration with your current internal systems) | -
Subscription and customer login | -
Marketing automation integration | -
Email marketing integration | -
Rush fee | -
Content Rework and Ongoing Content Development | - Planned Budget -
New content creation | -
Rework existing content | -
Ongoing content optimization for lead generation | -
Ongoing blog content creation | -
Ongoing Maintenance and Promotion | - Planned Budget -
Monthly website maintenance | -
Monthly advertising of website and blog | -
Monthly marketing and advertising services | -
Hosting and Domain Registration | - Planned Budget -
Monthly merchant account (eCommerce) | -
Domain name registration | -
Annual hosting | -
Content delivery network | -
Secure Socket Layer certificate (SSL certificate) | -
Total Planned Budget | 0

## Stage 6 - Timeline
WEBSITE REDESIGN STAGE 6: TIMELINE
A) Timeline Considerations | - Answers -
Is your timeline flexible in order to receive the best solution to your problem? | x
If not, are you willing to pay extra for quicker timelines? | x
Is your timeline realistic? | x
What internal events do you need to plan around? | x
On the day of the launch, be prepared for things to go wrong. (All hands on deck.) | x
B) Plan Dates | - Date -
Project start date | x
Content rough draft date | x
Design review date | x
Content final draft date | x
Development site review date | x
Tentative launch date | x
Any other dates? | x
Consider your internal calendar. How will it affect your ability to internally review project deliverables and provide necessary assets to keep your website project moving?
The typical website project timeline is 1-2 months for smaller sites and 3-6 months for larger companies.

## Stage 7 - Prelaunch
WEBSITE REDESIGN STAGE 7: PRELAUNCH
A) The Basics | - Progress (TBD, in progress, or complete?) - | Due Date | Owner (who's responsible for this?)
Make sure the development site is multi-browser compatible. (Use browsershots.org) | x | mm/dd/yy
Make sure you have custom/user-friendly 404 pages. | x | mm/dd/yy
Make sure all old pages redirect to appropriate new pages. | x | mm/dd/yy
Check for common errors like grammar and misspellings. | x | mm/dd/yy
B) Shareability | - Progress (TBD, in progress, or complete?) - | Due Date | Owner (who's responsible for this?)
Make sure users can easily subscribe to content (e.g. blog, email) | x | mm/dd/yy
Make sure users can easily share pages, posts, photos, etc. | x | mm/dd/yy
C) Analytics | - Progress (TBD, in progress, or complete?) - | Due Date | Owner (who's responsible for this?)
Make sure you analytical tool gets installed on the new site (e.g. Google Analytics) | x | mm/dd/yy
D) Keywords | - Progress (TBD, in progress, or complete?) - | Due Date | Owner (who's responsible for this?)
Are you making clear and meaningful use of keywords throughout your site? | x | mm/dd/yy
Is all of your meta information filled out on the new site? | x | mm/dd/yy
Do your keywords align with the interests of your buyer personas/target audiences? | x | mm/dd/yy
Do your calls-to-action/offers align with the topics covered in your site's pages? | x | mm/dd/yy
E) Navigation | - Progress (TBD, in progress, or complete?) - | Due Date | Owner (who's responsible for this?)
Is there a clear content hierarchy and organization? | x | mm/dd/yy
Is the site structure intuitive and user friendly? | x | mm/dd/yy
F) Design & Layout | - Progress (TBD, in progress, or complete?) - | Due Date | Owner (who's responsible for this?)
Perform an HMTL validation test via a CSS validator (like validator.w3.org). | x | mm/dd/yy
Is the site structure intuitive and user-friendly? | x | mm/dd/yy
G) Mobile | - Progress (TBD, in progress, or complete?) - | Due Date | Owner (who's responsible for this?)
Is your site optimized for mobile viewing? (Check with https://testmysite.thinkwithgoogle.com/) | x | mm/dd/yy
H) Performance | - Progress (TBD, in progress, or complete?) - | Due Date | Owner (who's responsible for this?)
Do your pages load quickly? (Run a test with a tool like https://developers.google.com/speed/pagespeed/insights/) | x | mm/dd/yy
I) Prepare for Launch | - Progress (TBD, in progress, or complete?) - | Due Date | Owner (who's responsible for this?)
Get sign-off from key management. | x | mm/dd/yy

## Stage 8 - Launch Day
WEBSITE REDESIGN STAGE 8: LAUNCH DAY
A) Be Prepared. | - Progress (TBD, in progress, or complete?) - | Due Date | Owner (who's responsible for this?)
On the day of the launch, be prepared for things to go wrong. (All hands on deck.) | x | mm/dd/yy
B) Announce the Launch: | - Progress (TBD, in progress, or complete?) - | Due Date | Owner (who's responsible for this?)
via email | x | mm/dd/yy
via social media | x | mm/dd/yy
via PR | x | mm/dd/yy
via blog(s) | x | mm/dd/yy
other? | x | mm/dd/yy

## Stage 9 - Post Launch
WEBSITE REDESIGN STAGE 9: POST LAUNCH
A) One-Week In: Index Check | - Your Data -
How many pages are indexed? | x
Are all of your important pages indexed? | yes/no
B) One-Week In: Make sure your web company does these items | - Progress (TBD, in progress, or complete?) -
Confirm that your Robots.txt file(s) is/are set up properly. | x
Resubmit your .XML sitemaps(s) via (Google and Bing) webmaster tools. | x
Add a public HTML sitemap (if you haven't already). | x
Make sure your analytics tool(s) is/are working properly. | x
C) Benchmark Your Metrics 1, 3, and 6 Months After Launch | - Month 1 Data - | - Month 3 Data - | - Month 6 Data -
Number of visits/visitors/unique visitors (monthly average) | 1 | 2 | 3
Bounce rate (monthly average) | 1 | 2 | 3
Time on site (monthly average) | 1 | 2 | 3
Top-performing keywords (in terms of rank, traffic and lead generation) | 1 | 2 | 3
Number of inbound linking domains | 1 | 2 | 3
Total number of new leads/form submissions (per month) | 1 | 2 | 3
Total amount of sales generated (per month) | 1 | 2 | 3
Total number of pages indexed. | 1 | 2 | 3
Total number of pages that receive traffic. | 1 | 2 | 3