Current Project Status

Week of June 22nd, 2026

Current Work

- Segment 1 saw cutting operations and installation of temporary asphalt pedestrian pathways are underway between South Biron Drive and Badger Street.

- Additional barricades and pedestrian traffic control measures will be installed upon completion of the temporary pathways.

- Contractor mobilization and site preparation activities continue throughout Segment 1.

Traffic Impacts

- CTH U remains closed to through traffic between South Biron Drive and Badger Street.

- The posted detour route remains in effect.

- Motorists are encouraged to follow all posted signage and traffic control devices.

Construction Progress

- Segment 1 construction activities remain on schedule.

- Preparations are underway for the next phase of utility installation work.

Upcoming Work

Week of June 29th, 2026

Planned Activities

- Begin watermain installation on the west end of Segment 1.

- Remove additional roadway pavement as necessary to provide adequate workspace for water main construction.

- Excavate, clean, and prepare trenches for watermain installation.

- Continue utility-related construction activities as work progresses eastward through the project corridor.

Anticipated Traffic Changes

- No changes to current detour route are anticipated at this time.

Past Project Updates

Week of June 15th, 2026

- Final project mobilization activities completed.

- Final project permits received.

- Construction signage installed.

- Residents notified of upcoming roadway closure and construction impacts.

- Village continued coordination with Westwood and the DNR regarding the SDWL.

Week of June 8th, 2026

- Village continued coordination with Westwood and the DNR regarding the SDWL.

- Construction schedule finalized.

- Detour route established.

Week of June 1st, 2026

- Pre-construction meeting held with the contractor, DOT, Wisconsin Department of Natural Resources (DNR), Wood County, and utility companies.

- Wood County, DOT, contractor, and Village held a Public Involvement Meeting to discuss the upcoming reconstruction of CTH U.

- Utility relocation coordination completed; all utilities confirmed relocated except Village utilities and WE Energies.

- Village continued coordination with Westwood and the DNR regarding the SDWL.

Week of April 20th, 2026

- Contractor executed the construction contract with the Wisconsin Department of Transportation (DOT).

Week of March 9th, 2026

- Bid advertisement period closed.

- Lowest responsible bidder selected and awarded the project.

Week of February 9th, 2026

- Tree removal and clearing activities completed in preparation for construction.

Week of February 2nd, 2026

- Construction bid advertisement published.

2025

- Cranberry marsh culvert replacements completed.

2024

- Wood County and the Village held the second Public Involvement Meeting to discuss design revisions for the proposed reconstruction of CTH U.

- Watermain installation option finalized, and work began on the Safe Drinking Water Loan (SDWL) process.

2023

- Village worked with Westwood and local officials to evaluate options for watermain improvements.

- Wood County coordinated with Village officials and Westwood to evaluate design options for the reconstructed roadway along with a new recreational trail.

- Wood County and the Village held the first Public Involvement Meeting to discuss proposed CTH U reconstruction design revisions.

2022

- Village contracted with Westwood for watermain design and engineering services.

- Wood County coordinated with Village officials regarding reconstruction design and project cost-sharing options.

2021

- Wood County starts planning and working on the CTH U project.