Current Project Status
Week of July 13th, 2026
Current Work
· Water main installation continues in Segment 1. 
· Trenching operations continue, including excavation and preparation for ongoing utility installation. 
· We Energies verified completion of their utility work on Monday. 
· Saw cutting was completed on Badger Street and Center Street to mark the trench limits for upcoming construction. 
· Central Staking completed layout and staking for the upcoming storm sewer installation.
· Crews are working to complete the two 45-degree water main bends at the Badger Street intersection. 
· Following completion of the water main, crews plan to pressure test the system and obtain the required two safe bacteriological water samples. 
· Once water main testing and sampling are complete, crews will begin storm sewer installation.
Traffic Impacts
· CTH U remains closed to through traffic between South Biron Drive and Badger Street.
· The posted detour route remains in effect.
· Pedestrians are encouraged to use the designated temporary walkway and follow all posted signage.
· Motorists are encouraged to follow all posted signage and traffic control devices.
Construction Progress
· Water main installation continues to advance through Segment 1. 
· We Energies has completed its utility work within the project limits. 
· Preparations are underway to transition from water main installation to storm sewer construction following successful testing and water quality sampling.
Upcoming Work
Week of July 20th, 2026
Planned Activities
· Continue storm sewer installation throughout Segment 1. 
· Continue backfilling and compacting completed utility trenches. 
· Place gravel over compacted areas to provide temporary access for Mill Traffic to parking lots off Beaver Street when Badger Street and Center Street are closed for water main installation. 
· Continue preparing the project corridor for upcoming roadway construction activities as storm sewer installation progresses.
Anticipated Traffic Changes
· No changes to current detour route are anticipated at this time. 

Past Project Updates
Week of July 6th, 2026
· Water main installation began in Segment 1. 
· Trenching operations and pavement removal progressed to support ongoing utility construction. 
· Utility work advanced eastward through the project corridor. 
· We Energies continued gas main extension work to homes in Segment 3.
Week of June 29th, 2026
· Tree stump removal was completed throughout the project area. 
· Temporary pedestrian walkway barricades were installed. 
· Boring operations began in preparation for upcoming water main installation.
Week of June 22nd, 2026
· Saw cutting operations began in Segment 1 between South Biron Drive and Badger Street.
· Temporary asphalt pedestrian pathways installed.
· Contractor mobilization and site preparation activities continued throughout Segment 1.
Week of June 15th, 2026
· Final project mobilization activities completed.
· Final project permits received.
· Construction signage installed.
· Residents notified of upcoming roadway closure and construction impacts.
· Village continued coordination with Westwood and the DNR regarding the SDWL.
Week of June 8th, 2026
· Village continued coordination with Westwood and the DNR regarding the SDWL.
· Construction schedule finalized.
· Detour route established.
Week of June 1st, 2026
· Pre-construction meeting held with the contractor, DOT, Wisconsin Department of Natural Resources (DNR), Wood County, and utility companies.
· Wood County, DOT, contractor, and Village held a Public Involvement Meeting to discuss the upcoming reconstruction of CTH U.
· Utility relocation coordination completed; all utilities confirmed relocated except Village utilities and WE Energies.
· Village continued coordination with Westwood and the DNR regarding the SDWL.
Week of April 20th, 2026
· Contractor executed the construction contract with the Wisconsin Department of Transportation (DOT).
Week of March 9th, 2026
· Bid advertisement period closed.
· Lowest responsible bidder selected and awarded the project.
Week of February 9th, 2026
· Tree removal and clearing activities completed in preparation for construction.
Week of February 2nd, 2026
· Construction bid advertisement published.
2025
· Cranberry marsh culvert replacements completed.
2024
· Wood County and the Village held the second Public Involvement Meeting to discuss design revisions for the proposed reconstruction of CTH U.
· Watermain installation option finalized, and work began on the Safe Drinking Water Loan (SDWL) process.
2023
· Village worked with Westwood and local officials to evaluate options for watermain improvements.
· Wood County coordinated with Village officials and Westwood to evaluate design options for the reconstructed roadway along with a new recreational trail.
· Wood County and the Village held the first Public Involvement Meeting to discuss proposed CTH U reconstruction design revisions.
2022
· Village contracted with Westwood for watermain design and engineering services.
· Wood County coordinated with Village officials regarding reconstruction design and project cost-sharing options.
2021
· Wood County starts planning and working on the CTH U project.



