Current Project Status

Week of July 13th, 2026

Current Work

- Water main installation continues in Segment 1.

- Trenching operations continue, including excavation and preparation for ongoing utility installation.

- We Energies verified completion of their utility work on Monday.

- Saw cutting was completed on Badger Street and Center Street to mark the trench limits for upcoming construction.

- Central Staking completed layout and staking for the upcoming storm sewer installation.

- Crews are working to complete the two 45-degree water main bends at the Badger Street intersection.

- Following completion of the water main, crews plan to pressure test the system and obtain the required two safe bacteriological water samples.

- Once water main testing and sampling are complete, crews will begin storm sewer installation.

Traffic Impacts

- CTH U remains closed to through traffic between South Biron Drive and Badger Street.

- The posted detour route remains in effect.

- Pedestrians are encouraged to use the designated temporary walkway and follow all posted signage.

- Motorists are encouraged to follow all posted signage and traffic control devices.

Construction Progress

- Water main installation continues to advance through Segment 1.

- We Energies has completed its utility work within the project limits.

- Preparations are underway to transition from water main installation to storm sewer construction following successful testing and water quality sampling.

Upcoming Work

Week of July 20th, 2026

Planned Activities

- Continue storm sewer installation throughout Segment 1.

- Continue backfilling and compacting completed utility trenches.

- Place gravel over compacted areas to provide temporary access for Mill Traffic to parking lots off Beaver Street when Badger Street and Center Street are closed for water main installation.

- Continue preparing the project corridor for upcoming roadway construction activities as storm sewer installation progresses.

Anticipated Traffic Changes

- No changes to current detour route are anticipated at this time.

Past Project Updates

Week of July 6th, 2026

- Water main installation began in Segment 1.

- Trenching operations and pavement removal progressed to support ongoing utility construction.

- Utility work advanced eastward through the project corridor.

- We Energies continued gas main extension work to homes in Segment 3.

Week of June 29th, 2026

- Tree stump removal was completed throughout the project area.

- Temporary pedestrian walkway barricades were installed.

- Boring operations began in preparation for upcoming water main installation.

Week of June 22nd, 2026

- Saw cutting operations began in Segment 1 between South Biron Drive and Badger Street.

- Temporary asphalt pedestrian pathways installed.

- Contractor mobilization and site preparation activities continued throughout Segment 1.

Week of June 15th, 2026

- Final project mobilization activities completed.

- Final project permits received.

- Construction signage installed.

- Residents notified of upcoming roadway closure and construction impacts.

- Village continued coordination with Westwood and the DNR regarding the SDWL.

Week of June 8th, 2026

- Village continued coordination with Westwood and the DNR regarding the SDWL.

- Construction schedule finalized.

- Detour route established.

Week of June 1st, 2026

- Pre-construction meeting held with the contractor, DOT, Wisconsin Department of Natural Resources (DNR), Wood County, and utility companies.

- Wood County, DOT, contractor, and Village held a Public Involvement Meeting to discuss the upcoming reconstruction of CTH U.

- Utility relocation coordination completed; all utilities confirmed relocated except Village utilities and WE Energies.

- Village continued coordination with Westwood and the DNR regarding the SDWL.

Week of April 20th, 2026

- Contractor executed the construction contract with the Wisconsin Department of Transportation (DOT).

Week of March 9th, 2026

- Bid advertisement period closed.

- Lowest responsible bidder selected and awarded the project.

Week of February 9th, 2026

- Tree removal and clearing activities completed in preparation for construction.

Week of February 2nd, 2026

- Construction bid advertisement published.

2025

- Cranberry marsh culvert replacements completed.

2024

- Wood County and the Village held the second Public Involvement Meeting to discuss design revisions for the proposed reconstruction of CTH U.

- Watermain installation option finalized, and work began on the Safe Drinking Water Loan (SDWL) process.

2023

- Village worked with Westwood and local officials to evaluate options for watermain improvements.

- Wood County coordinated with Village officials and Westwood to evaluate design options for the reconstructed roadway along with a new recreational trail.

- Wood County and the Village held the first Public Involvement Meeting to discuss proposed CTH U reconstruction design revisions.

2022

- Village contracted with Westwood for watermain design and engineering services.

- Wood County coordinated with Village officials regarding reconstruction design and project cost-sharing options.

2021

- Wood County starts planning and working on the CTH U project.