Current Project Status
Week of July 27th, 2026
Current Work
· Storm sewer installation is underway in Segment 1 and will continue over the next week.
· Water service lateral tie-in for the ND Administrative/HR Building was completed on Wednesday.
· Crews will complete water service lateral tie-in for the Sparhawk Building (formerly the R&D Building) if it is determined that the building was not previously connected.
· Backfilling and compaction of completed utility trenches will continue in preparation for placing gravel on the roadway.
Traffic Impacts
· CTH U remains closed to through traffic between South Biron Drive and Badger Street.
· The posted detour route remains in effect.
· Pedestrians are encouraged to use the designated temporary walkway and follow all posted signage.
· Motorists are encouraged to follow all posted signage and traffic control devices.
· Temporary traffic control devices have been installed along North Biron Drive until roadside safety features are restored.
Construction Progress
· Storm sewer installation continues to advance through Segment 1.
· Water service lateral connections continue to be completed for properties within the project limits.
· Utility work continues to progress in preparation for future roadway construction activities.
Upcoming Work
Week of August 3rd, 2026
Planned Activities
· Continue storm sewer installation throughout Segment 1. 
· Begin water main installation on Badger Street and Center Street, weather and construction progress permitting.
· Continue backfilling and compacting completed utility trenches. 
Anticipated Traffic Changes
· No changes to current detour route are anticipated at this time. 

Past Project Updates
Week of July 20th 
· Storm sewer installation began throughout Segment 1. 
· Crews completed water service lateral tie-ins for properties in project area.
Week of July 13th 
· Water main installation continued in Segment 1.
· Trenching, excavation, saw cutting, and construction staking progressed in preparation for upcoming water main and storm sewer installations.
· We Energies completed its utility work within the project limits.
· Crews successfully completed water main pressure testing and bacteriological sampling, with both tests meeting requirements.
· With water main testing complete, crews are preparing to transition to storm sewer installation.
Week of July 6th, 2026
· Water main installation began in Segment 1. 
· Trenching operations and pavement removal progressed to support ongoing utility construction. 
· Utility work advanced eastward through the project corridor. 
· We Energies continued gas main extension work to homes in Segment 3.
Week of June 29th, 2026
· Tree stump removal was completed throughout the project area. 
· Temporary pedestrian walkway barricades were installed. 
· Boring operations began in preparation for upcoming water main installation.
Week of June 22nd, 2026
· Saw cutting operations began in Segment 1 between South Biron Drive and Badger Street.
· Temporary asphalt pedestrian pathways installed.
· Contractor mobilization and site preparation activities continued throughout Segment 1.
Week of June 15th, 2026
· Final project mobilization activities completed.
· Final project permits received.
· Construction signage installed.
· Residents notified of upcoming roadway closure and construction impacts.
· Village continued coordination with Westwood and the DNR regarding the SDWL.
Week of June 8th, 2026
· Village continued coordination with Westwood and the DNR regarding the SDWL.
· Construction schedule finalized.
· Detour route established.
Week of June 1st, 2026
· Pre-construction meeting held with the contractor, DOT, Wisconsin Department of Natural Resources (DNR), Wood County, and utility companies.
· Wood County, DOT, contractor, and Village held a Public Involvement Meeting to discuss the upcoming reconstruction of CTH U.
· Utility relocation coordination completed; all utilities confirmed relocated except Village utilities and WE Energies.
· Village continued coordination with Westwood and the DNR regarding the SDWL.
Week of April 20th, 2026
· Contractor executed the construction contract with the Wisconsin Department of Transportation (DOT).
Week of March 9th, 2026
· Bid advertisement period closed.
· Lowest responsible bidder selected and awarded the project.
Week of February 9th, 2026
· Tree removal and clearing activities completed in preparation for construction.
Week of February 2nd, 2026
· Construction bid advertisement published.
2025
· Cranberry marsh culvert replacements completed.
2024
· Wood County and the Village held the second Public Involvement Meeting to discuss design revisions for the proposed reconstruction of CTH U.
· Watermain installation option finalized, and work began on the Safe Drinking Water Loan (SDWL) process.
2023
· Village worked with Westwood and local officials to evaluate options for watermain improvements.
· Wood County coordinated with Village officials and Westwood to evaluate design options for the reconstructed roadway along with a new recreational trail.
· Wood County and the Village held the first Public Involvement Meeting to discuss proposed CTH U reconstruction design revisions.
2022
· Village contracted with Westwood for watermain design and engineering services.
· Wood County coordinated with Village officials regarding reconstruction design and project cost-sharing options.
2021
· Wood County starts planning and working on the CTH U project.



