Current Project Status
Week of September 7th, 2026
Current Work
· Crews continue working on stormwater installation at the intersection of North Biron Drive and Badger Street.
· Crews began subgrading portions of North Biron Drive yesterday in preparation for upcoming roadway work.
· Working with CWPCo to address and repair the burned-out street light at the intersection of North Biron Drive and Badger Street..
Traffic Impacts
· CTH U remains closed to through traffic between South Biron Drive and Badger Street.
· The posted detour route remains in effect.
· Pedestrians are encouraged to use the designated temporary walkway and follow all posted signage.
· Motorists are encouraged to follow all posted signage and traffic control devices.
· Temporary traffic control devices have been installed along North Biron Drive until roadside safety features are restored.
Construction Progress
· Stormwater work continues at the intersection of North Biron Drive and Badger Street.
· Subgrading has begun on portions of North Biron Drive as crews prepare for the next phase of roadway construction.
· Coordination is underway with CWPCo to repair the burned-out street light at the North Biron Drive and Badger Street intersection.

Upcoming Work
Week of September 14th, 2026
Planned Activities
· Finish storm sewer construction at the intersection of Badger Street and North Biron Drive, if not completed.
· Continue and complete subgrading on North Biron Drive in preparation for the anticipated traffic switch to Beaver Street, which will allow mill traffic to access the parking lot and crews to begin watermain construction on Center Street.
Anticipated Traffic Changes
· The posted detour route will remain in effect, with any changes communicated as work progresses.
Past Project Updates
Week of August 31st
· Watermain installation progressed down Badger Street to the intersection with Center Street, including installation of the hydrant and valves.
· Crews prepared to pressure test the new watermain and collect safe water samples before placing it into service.
· Stormwater work began at the intersection of Badger Street and North Biron Drive.
Week of August 24th 
· Watermain construction continued on North Biron Drive and Badger Street, including the tie-in to the existing tee on North Biron Drive. 
· Crews installed the new watermain underneath the existing watermain on Badger Street and capped the existing main. 
· Crews continued excavation and shaping of the stormwater drainage swale.
Week of August 17th
· Watermain installation continued on North Biron Drive between Badger Street and Otter Street.
· Crews installed the hydrant at the intersection of North Biron Drive and Otter Street in preparation for pressure testing and safe water sampling of the new watermain.
· Crews continued excavation and shaping of the stormwater drainage swale.
Week of August 10th 
· Storm sewer installation continued throughout Segment 1, with crews addressing unforeseen field conditions and utility conflicts.
· Crews completed the water lateral tie-in to the Sparhawk property.
· Excavation began for the stormwater drainage swale, with excavated material being reused throughout the project as needed.
Week of August 3rd 
· Storm sewer installation continued throughout Segment 1.
Week of July 27th
· Storm sewer installation continued throughout Segment 1.
· Crews completed the water service lateral tie-in for the ND Administrative/HR Building and continued water service connection work within the project area.
Week of July 20th 
· Storm sewer installation began throughout Segment 1. 
· Crews completed water service lateral tie-ins for properties in project area.
Week of July 13th 
· Water main installation continued in Segment 1.
· Trenching, excavation, saw cutting, and construction staking progressed in preparation for upcoming water main and storm sewer installations.
· We Energies completed its utility work within the project limits.
· Crews successfully completed water main pressure testing and bacteriological sampling, with both tests meeting requirements.
· With water main testing complete, crews are preparing to transition to storm sewer installation.
Week of July 6th, 2026
· Water main installation began in Segment 1. 
· Trenching operations and pavement removal progressed to support ongoing utility construction. 
· Utility work advanced eastward through the project corridor. 
· We Energies continued gas main extension work to homes in Segment 3.
Week of June 29th, 2026
· Tree stump removal was completed throughout the project area. 
· Temporary pedestrian walkway barricades were installed. 
· Boring operations began in preparation for upcoming water main installation.
Week of June 22nd, 2026
· Saw cutting operations began in Segment 1 between South Biron Drive and Badger Street.
· Temporary asphalt pedestrian pathways installed.
· Contractor mobilization and site preparation activities continued throughout Segment 1.
Week of June 15th, 2026
· Final project mobilization activities completed.
· Final project permits received.
· Construction signage installed.
· Residents notified of upcoming roadway closure and construction impacts.
· Village continued coordination with Westwood and the DNR regarding the SDWL.
Week of June 8th, 2026
· Village continued coordination with Westwood and the DNR regarding the SDWL.
· Construction schedule finalized.
· Detour route established.
Week of June 1st, 2026
· Pre-construction meeting held with the contractor, DOT, Wisconsin Department of Natural Resources (DNR), Wood County, and utility companies.
· Wood County, DOT, contractor, and Village held a Public Involvement Meeting to discuss the upcoming reconstruction of CTH U.
· Utility relocation coordination completed; all utilities confirmed relocated except Village utilities and WE Energies.
· Village continued coordination with Westwood and the DNR regarding the SDWL.
Week of April 20th, 2026
· Contractor executed the construction contract with the Wisconsin Department of Transportation (DOT).
Week of March 9th, 2026
· Bid advertisement period closed.
· Lowest responsible bidder selected and awarded the project.
Week of February 9th, 2026
· Tree removal and clearing activities completed in preparation for construction.
Week of February 2nd, 2026
· Construction bid advertisement published.
2025
· Cranberry marsh culvert replacements completed.
2024
· Wood County and the Village held the second Public Involvement Meeting to discuss design revisions for the proposed reconstruction of CTH U.
· Watermain installation option finalized, and work began on the Safe Drinking Water Loan (SDWL) process.
2023
· Village worked with Westwood and local officials to evaluate options for watermain improvements.
· Wood County coordinated with Village officials and Westwood to evaluate design options for the reconstructed roadway along with a new recreational trail.
· Wood County and the Village held the first Public Involvement Meeting to discuss proposed CTH U reconstruction design revisions.
2022
· Village contracted with Westwood for watermain design and engineering services.
· Wood County coordinated with Village officials regarding reconstruction design and project cost-sharing options.
2021
· Wood County starts planning and working on the CTH U project.



