Current Project Status
Week of October 19th, 2026
Current Work
· Crews have completed all watermain installation in Phases 1 and 2.
· Crews are working on storm sewer installation at the intersection of Bear Street and North Biron Drive and will continue working east.
· Grading operations will follow storm sewer installation as crews complete each section.
· Crews will continue finish grading in preparation for asphalt paving.
· Potholes along the roadway between Short Street and Huffman Road will be filled prior to winter.
Traffic Impacts
· CTH U remains closed to traffic between South Biron Drive and Beaver Street.
· ND Paper traffic will continue to use the detour route of North Biron Drive to Short Street to Center Street, to Badger Street, to North Biron Drive, and to Beaver Street.
· Head Start traffic will use the detour route of North Biron Drive to Short Street to Center Street to Badger Street to Williams Street access the back of the building for parking as needed.
· All other traffic shall continue using posted detour route out to Huffman Road until otherwise noted.
· Pedestrians are encouraged to use the designated temporary walkway and follow all posted signage.
· Motorists are encouraged to follow all posted signage and traffic control devices.
· Temporary traffic control devices have been installed along North Biron Drive until roadside safety features are restored.
Construction Progress
· Watermain installation has been completed in Phases 1 and 2.
· Storm sewer installation is underway at the intersection of Bear Street and North Biron Drive, with work progressing east.
· Grading will continue behind storm sewer installation as crews complete each section.
· Finish grading will be completed in preparation for asphalt paving.
· Potholes between Short Street and Huffman Road will be filled prior to winter.

Upcoming Work
Week of October 26th, 2026
Planned Activities
· Crews will continue storm sewer installation progressing east.
· Grading operations will continue as storm sewer installation is completed in each section.
· American Asphalt is scheduled to begin paving on Monday.
Anticipated Traffic Changes
· ND Paper traffic will continue to use the detour route of North Biron Drive to Short Street to Center Street, to Badger Street, to North Biron Drive, and to Beaver Street.
· Head Start traffic will continue to use the detour route of North Biron Drive to Short Street to Center Street to Badger Street to Williams Street to access the back of the building for parking as needed.
· All other traffic should continue using the detour route out to Huffman Road until otherwise noted.
· Any additional traffic changes will be communicated as work progresses.
Past Project Updates
Week of October 12th 
· Crews continued watermain installation east along North Biron Drive.
· Crews worked toward completing the watermain and fire hydrant installation on Fox Street, followed by pressure testing.
· Crews planned to connect the new watermain to the existing watermain in the alley off Fox Street.
· Sommers poured curb and portions of the sidewalk.
· Crews prepared intersections for asphalt paving by saw-cutting in advance of the following week’s paving work.
Week of October 5th
· Crews tied the new watermain into the existing watermain at the end of Center Street and completed grading in the area.
· Storm sewer work continued between Otter Street and Bear Street, with watermain installation planned for the same area.
· Sommers prepared forms for curb installation.
Week of September 28th 
· Crews completed installation of the new hydrant at the end of Center Street and pressure tested the new watermain.
· Crews completed water sampling and transitioned to storm sewer work between Otter Street and Bear Street while awaiting results.
· Crews completed lateral tie-ins to the two homes at the end of Center Street and Head Start.
Week of September 21st
· Crews completed the tie-in to the existing watermain near the alley and completed the new watermain lateral connection to Head Start.
· Crews began installing new watermain along Center Street.
Week of September 14th 
· Arbor Green mobilized to the project area and began seeding portions of the project area.
· Arbor Green continued repairing and maintaining silt fence along the project limits.
· Crews installed new watermain from the current endpoint at the intersection of Badger Street and Center Street to the alley near the Village Shop.
· The intersection of Badger Street and Center Street will remain closed while watermain work is underway.
Week of September 7th
· Stormwater installation continued at the intersection of North Biron Drive and Badger Street.
· Crews began subgrading portions of North Biron Drive in preparation for upcoming roadway construction.
· CWPCo repaired the burned-out street light at the intersection of North Biron Drive and Badger Street.
Week of August 31st
· Watermain installation progressed down Badger Street to the intersection with Center Street, including installation of the hydrant and valves.
· Crews prepared to pressure test the new watermain and collect safe water samples before placing it into service.
· Stormwater work began at the intersection of Badger Street and North Biron Drive.
Week of August 24th 
· Watermain construction continued on North Biron Drive and Badger Street, including the tie-in to the existing tee on North Biron Drive. 
· Crews installed the new watermain underneath the existing watermain on Badger Street and capped the existing main. 
· Crews continued excavation and shaping of the stormwater drainage swale.
Week of August 17th
· Watermain installation continued on North Biron Drive between Badger Street and Otter Street.
· Crews installed the hydrant at the intersection of North Biron Drive and Otter Street in preparation for pressure testing and safe water sampling of the new watermain.
· Crews continued excavation and shaping of the stormwater drainage swale.
Week of August 10th 
· Storm sewer installation continued throughout Segment 1, with crews addressing unforeseen field conditions and utility conflicts.
· Crews completed the water lateral tie-in to the Sparhawk property.
· Excavation began for the stormwater drainage swale, with excavated material being reused throughout the project as needed.
Week of August 3rd 
· Storm sewer installation continued throughout Segment 1.
Week of July 27th
· Storm sewer installation continued throughout Segment 1.
· Crews completed the water service lateral tie-in for the ND Administrative/HR Building and continued water service connection work within the project area.
Week of July 20th 
· Storm sewer installation began throughout Segment 1. 
· Crews completed water service lateral tie-ins for properties in project area.
Week of July 13th 
· Water main installation continued in Segment 1.
· Trenching, excavation, saw cutting, and construction staking progressed in preparation for upcoming water main and storm sewer installations.
· We Energies completed its utility work within the project limits.
· Crews successfully completed water main pressure testing and bacteriological sampling, with both tests meeting requirements.
· With water main testing complete, crews are preparing to transition to storm sewer installation.
Week of July 6th, 2026
· Water main installation began in Segment 1. 
· Trenching operations and pavement removal progressed to support ongoing utility construction. 
· Utility work advanced eastward through the project corridor. 
· We Energies continued gas main extension work to homes in Segment 3.
Week of June 29th, 2026
· Tree stump removal was completed throughout the project area. 
· Temporary pedestrian walkway barricades were installed. 
· Boring operations began in preparation for upcoming water main installation.
Week of June 22nd, 2026
· Saw cutting operations began in Segment 1 between South Biron Drive and Badger Street.
· Temporary asphalt pedestrian pathways installed.
· Contractor mobilization and site preparation activities continued throughout Segment 1.
Week of June 15th, 2026
· Final project mobilization activities completed.
· Final project permits received.
· Construction signage installed.
· Residents notified of upcoming roadway closure and construction impacts.
· Village continued coordination with Westwood and the DNR regarding the SDWL.
Week of June 8th, 2026
· Village continued coordination with Westwood and the DNR regarding the SDWL.
· Construction schedule finalized.
· Detour route established.
Week of June 1st, 2026
· Pre-construction meeting held with the contractor, DOT, Wisconsin Department of Natural Resources (DNR), Wood County, and utility companies.
· Wood County, DOT, contractor, and Village held a Public Involvement Meeting to discuss the upcoming reconstruction of CTH U.
· Utility relocation coordination completed; all utilities confirmed relocated except Village utilities and WE Energies.
· Village continued coordination with Westwood and the DNR regarding the SDWL.
Week of April 20th, 2026
· Contractor executed the construction contract with the Wisconsin Department of Transportation (DOT).
Week of March 9th, 2026
· Bid advertisement period closed.
· Lowest responsible bidder selected and awarded the project.
Week of February 9th, 2026
· Tree removal and clearing activities completed in preparation for construction.
Week of February 2nd, 2026
· Construction bid advertisement published.
2025
· Cranberry marsh culvert replacements completed.
2024
· Wood County and the Village held the second Public Involvement Meeting to discuss design revisions for the proposed reconstruction of CTH U.
· Watermain installation option finalized, and work began on the Safe Drinking Water Loan (SDWL) process.
2023
· Village worked with Westwood and local officials to evaluate options for watermain improvements.
· Wood County coordinated with Village officials and Westwood to evaluate design options for the reconstructed roadway along with a new recreational trail.
· Wood County and the Village held the first Public Involvement Meeting to discuss proposed CTH U reconstruction design revisions.
2022
· Village contracted with Westwood for watermain design and engineering services.
· Wood County coordinated with Village officials regarding reconstruction design and project cost-sharing options.
2021
· Wood County starts planning and working on the CTH U project.



