2026-2030 Road Work Plan and Budget Projections

Draft for discussion, 22 May 2025.  Revised 17 Sept 2025

2026 Minor Project Year		West Side

- Bellbrook Road “Hill”.  0.4 miles, full wedge @ $60,000/mile	$24,000

- Bellbrook Road, culvert at DNR ground				  $5,000 ???

  - DNR provides culvert, Town installs

- French Town Road, 0.3 miles, pulverize, repave, add gravel, $200,000/mile											$70,000

- Striping, must coordinate with other road work.			$ 10,000

Total							$104,000 to 109,000

Add 10% contingency				$115,000 to 120,000

Striping Candidates for 2026.  (Approx mileage), ($1,000 +/ per mile).

- Lincoln Road, Fish Hatchery Road to Storytown Road, 	1.0 miles

- Sun Valley Parkway, 						1.5 miles

- Glenway Road, CTY A to Lincoln Road,  			1.5 miles

- Hillcrest Road, CTY A to Lincoln Road, 			1.6 miles

- Union Road,							4.5 miles

2027, Major Project Year		East Side

- Rome Corners, 1.1 miles pulverize, repave, add gravel 					@ $200,000/mile						$220,000

- Locust Grove Road, 1.38 miles

  - Engineering investigation, drainage at bridge		  --(TBD)—

  - Pulverize, repave, add gravel @ $200,000/mile		$276,000

  - Correct Drainage issues at Railroad bridge.		   --(TBD)—

  - Coordinate with Dane County Parks, new drive access, water diversion and retention possibilities.

- Apply TRIP grant funds						($17,500)

Total							$478,500

Add 10% contingency				$526,350

2028 Minor Project Year		East Side +

- Fahey Heights, Seal Coating @ $20,000/mi x 1.01 miles =	$21,000

  - Harding (0.37), Johnson (0.21), Tyler (0.10), Coolidge (0.13)				Taft (0.08) Kennedy (0.11)

- Eisenhower, (0.28) mi., wedge @ 60,000/mi			$18,000

- Oregon Trail, Seal Coating @ $20,000/mi x (0.57) mi =		$12,000

  - Oregon Tr. (0.32), French Glen (0.20), French Ct.; (0.05)

- Alpine Road, Seal Coating @ $20,000/mi x 1.6 miles		$32,000

Total							$83,000.

Add 10% contingency				$92,000,

2029 Major Project Year	West Side

- Tipperary Road, South end, 1.6 mi, pulverize, repave, add gravel				@ $200,000 =							$320,000

- Judd Road, (partial share with Montrose), 1.11 miles, Double wedging up to pulverize and overlay, plus 10% contingency.	$74,000 to $244,000

- Marie Road, (0.4 +/-), Needs major work, Wedge ? $24,000 Pulverize ?  $80,000 ?

Total							$414,000 to 644,000

Add 10% contingency				$455-709,000

2030 Minor Project Year  --------- Side

- Seal Coating---but where?

- Striping ---???---

- Wedging ---???---

Grant Options to actively pursue

Judd Road,  1.11 miles, Double wedging up to pulverize and overlay, plus 10% contingency.	$74,000 to $244,000

Bellbrook Bridge, dependent upon deterioration rating.  	$500,000 to $600,000, or big culverts ???, 100% Fed funding, 2029-30 possible with 18-month design and approval process, fees about 10%.

Bellbrook Road, 2.0 miles, work to be determined.

Union Road, from Brooklyn to Tony Lane, In process, $-----  2031 Project ???

ARIP, Agriculture Road Improvement Program, possible candidates

- Purcell Road, in conjunction with Fitchburg

- Bellbrook Road

- Tipperary Road

Transfer TRIP funds, $17,500. to road work before 2029.  Determine if this can be switched from Tipperary to Rome Corners Road.

Investigations

- Coordinate with Fitchburg on schedule of Purcell Road work.

- Cooperation with Town of Montrose, Judd Road, grant possibilities and shared costs.

- Smaller subdivisions, Identify as group(s) conditions

- Value of striping.