## Garden City
Garden City 2022 Prioritization Request Form
Updates include draft FY2021-2025 IFYWP. Programming status is subject to change.
Ranking Instructions:
1. Rank your project request using only one number per project (Please avoid using 2a, 2b, 2c, etc.).
2. Utilize the first column to reevaluate your prioritization ranking. Adjust as needed.
3. Blank lines are provided at the end of each category to add additional projects. Provide a clear description of the project request.
4. Remember to identify projects for removal.
2021 Priority Ranking | 2020 Priority Ranking | Agency Project Name | Agency Project Description | Current IFYWP Programming Status |  |  | ACHD Response | ACHD Implementation Project Name
|  |  |  | Design YR | ROW YR | Construction YR
Projects Programmed
| Programmed | US 20/26 (Chinden Blvd) and 43rd St Pedestrian Crossing | Install an enhanced pedestrian crossing (pedestrian hybrid beacon) on Chinden Blvd at 43rd St. | 2021 | N/A | 2023 | Project to be built in 2023. | US 20/26 (Chinden Blvd) and 43rd St Pedestrian Crossing
| Programmed | Clay St, 34th St / 32nd St; 32nd St, Chinden Blvd / Clay St (Clay, 32nd/37th) | Construct curb, gutter, 5' detached sidewalk, swales, landscaped bulb outs at intersections and illumination on Clay St, from 34th St to 32nd St and on 32nd St, from Chinden Blvd to Clay St. Certain improvements will require partnership with Garden City and the Garden City Urban Renewal Agency. | 2021 | 2022 | 2024 | Project to be built in 2024. | Clay St, 34th St / 32nd St;
|  |  |  | 2021 | 2022 | 2023 | Project to be built in 2023. | 32nd St, US 20/26 (Chinden Blvd) / Clay St
| Programmed | Clay St, 37th St / 34th St; 34th St, Chinden Blvd / Clay St (Clay, 32nd/37th) | Construct curb, gutter, 5' detached sidewalk, swales, landscaped bulb outs at intersections and illumination on Clay St, from 37th St to 34th St and on 34nd St, from Chinden Blvd to Clay St. Certain improvements will require partnership with Garden City and the Garden City Urban Renewal Agency. | 2022 | 2023 | 2025 | Project to be built in 2025. | Clay St, 37th St / 34th St; 34th St, Chinden Blvd / Clay St (Clay, 32nd/37th)
| Programmed | 43rd St Bikeway Connection, Ustick Rd / Greenbelt (Bike Connection 43rd St and Ustick Rd) | Improve 43rd St, (Ustick Rd to Greenbelt), Ustick Rd (Esquire Rd to 43rd St), 43rd St, (Ustick Rd to Greenbelt), and Adams St (43rd St to Veterans Parkway) as a low-stress bikeway connect to include wayfinding and bikeway signage, enhanced crossings, and markings in accordance with the Bike Master Plan. Project may also include enhancement to the existing Ustick Rd bike lanes. Concept design will further clarify project scope. | N/A | N/A | 2025 | Project to be built in 2025. | Bikeway Signage Program (2025)
| Programmed | 35th St, Greenbelt / Brown St | Install curb, gutter, attached 6' sidewalk with landscape bulb-outs, parking, bike facilities, shallow seepage beds (consider permeable pavers) on 35th St from the greenbelt to Brown St. Match 36th St. design. Includes road rehabilitation. Due to significant business access on 35th St, south of Chinden, design should be conducted to 30% and include public outreach to determine the best solution for bike/ped facilities on the southern section. | Not Programmed | Not Programmed | Not Programmed |  | 35th St, Brown St / US 20/26 (Chinden Blvd);
|  |  |  | 2025 | Future | Future | Project to begin design in 2025. | 35th St, US 20/26 (Chinden Blvd) / Greenbelt
Community Programs - Crossings
| 1 | Ustick @43rd | Multiple traffic fatalities have occurred in proximity of this intersections. Due to multiple lanes of traffic, downhill slope, and both speed and volumes necessitate a more visible crossing. Install Pedestrian Hybrid Beacon and overhead lighting at marked crosswalk. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | Ustick Rd and 43rd Pedestrian Crossing
| 2 | 50th St and US 20/26 (Chinden Blvd) | Construct connection on east side of 50th Street to Chinden Blvd intersection so that users have a usable space to cross 50th at Chinden. Project also includes a marked pedestrian crossing at 50th St and Bradley St. | Not Programmed | Not Programmed | Not Programmed | ACHD Traffic Engineering to evaluate crossing at 50th St and Bradley St. No additional improvement planned at 50th and Chinden until sidewalks implemented on Chinden Blvd. | 50th St and US 20/26 (Chinden Blvd)
| 3 | Chinden at Coffey | Crossing to allow regional movement of non vehicular traffic, particulary Capital High students. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | US 20/26 (Chinden Blvd) / Coffey St Pedestrian Crossing
| 4 | 33rd St and Chinden Blvd Pedestrian Crossing | Install an enhanced pedestrian crossing (pedestrian hybrid beacon) on Chinden Blvd at 33rd St. | Not Programmed | Not Programmed | Not Programmed | Scoped. To be evaluated and prioritized for possible inclusion into future IFYWP updates. | 33rd St and US 20/26 (Chinden Blvd) Pedestrian Crossing
5 |  | Millstone Drive- Pedestrian Crossing | Install an enhanced pedestrian crossing (pedestrian hybrid beacon) to facilitate access to the anticipated multiuse path on Chinden. This will facilitate a school route to Capital High, Hyatt Hidden Lakes Reserve, and Boise Bench
6 | 5 | Allworth St and 50th St Pedestrian Crossing | Install an enhanced pedestrian crossing on Allworth St at 50th St. Project request includes landscaping, pedestrian amenities, street lighting, and review if a bus shelter should be located here. | Not Programmed | Not Programmed | Not Programmed | ACHD Traffic Engineering review found current signage and markings appropriate for speeds and volumes in the area. No additional improvement warranted for the crossing. Landscaping and other improvements would be require a cost share from the City. | Allworth St and 50th St Pedestrian Crossing
7 | 6 | Chinden at 38th | Crossing to allow regional movement on non vehicular traffic. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | US 20/26 (Chinden Blvd) and 38th St Crossing
8 | 7 | Marigold and Coffey | Realign curb ramps and crosswalk at intersection as eastern crossing has no clear alignment and exposes pedestrians to unnecessary vehicle exposure time. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | Marigold St and Coffey St Pedestrian Crossing
9 | 8 | State St and Glenwood St Pedestrian Crossing | Improve pedestrian and bike connection through and around this intersection to Greenbelt. It is understood that the Glenwood and State preferred alternative has been selected. As part of this alternative getting transit, bikes, and pedestrians to the neighborhoods in a safe and comfortable manner remains a priority that has not been fully vetted. | Future | Future | Future | Construction timeline pending coordination with ITD on funding. | State St and Glenwood St
10 | 9 | Glenwood intersection redesign at Chinden | The intersection of Glenwood and Chinden does not function well for any mode of transportation, particularly those needing ADA accessible routes, bicyclists, and pedestrians. | Not Programmed | Not Programmed | Not Programmed | This is an ITD intersection. ACHD will share request. | US 20/26 (Chinden Blvd) and Glenwood St
Community Programs - Local Roads
9 | 1 | Arney Lane, Riverside Dr / State St | Construct bike and pedestrian improvements on Arney Ln from Riverside Dr to State St. This request appears to be previously misunderstood. The immeadiate request is to provide space for school children to safely pass the canal with regards to bus services. Garden City understands that a complete build of the sidewalk infrastructure has larger implications. Last year ACHD indicated that they have done an analysis to look at creative solutions and Garden City requested a detailing of those scopes as part of the 2019 IFYWP. Garden City has yet to have those provided to Garden City. Has ACHD looked at increasing the culvert under the road to provide for shoulder space to cross the canal? Thank you | Not Programmed | Not Programmed | Not Programmed | ACHD rescoping in 2020. | Arney Ln (East Side), Riverside Dr / SH 44 (State St)
1 | 2 | Design of roadways East of 43rd Street | Design of all of the public streets east of 43rd Street to identify what type of bicycle facility (if any) will be utilized, sidewalk, street tree, street furniture zone (if any), and lighting so that they are shovel ready. This facilitates three purposes: 1. Installation of predetermined facilites during redevelopment; 2. The ability for Public Works to do work and rebuild to desired standards; 3. Potential advancement of projects if non ACHD funding is identified. | Not Programmed | Not Programmed | Not Programmed | Projects will be designed individually. Multiple roads programmed in draft IFYWP. | N/A
2 |  | Bicycle and Pedestrian Pathway Spine | A bicycle and pedestrian pathway that anticipates hevy recreational bicycle and pedestrican use that has adjacent art and or historical signage
3 | 3 | Kent | Construct sidewalk connection bus stop at Chinden/ Kent to Alworth. | Not Programmed | Not Programmed | Not Programmed | ACHD is scoping in 2020. | Kent St, US 20/26 (Chinden Blvd) / Alworth St
4 | 6 | Riverside Drive to Strawberry Glenn | Fix damaged sidewalks and complete sidewalk network to Glenwood | Not Programmed | Not Programmed | Not Programmed | ACHD is scoping in 2020. | Riverside Dr, Strawberry Glenn Rd / Glenwood St
5 | 7 | Bike Connection Strawberry Glenn Rd and Saxton Dr | See State St and Glenwood Pedestrian Crossing. | Future | Future | Future | Construction timeline pending coordination with ITD on funding. | State St and Glenwood St
6 | 8 | 33rd St, Greenbelt / Brown | Install curb, gutter, attached 6' sidewalk with landscape bulb-outs, parking, bike facilities, shallow seepage beds (consider permeable pavers) on 33rd St from the greenbelt to Brown St. Pedestrian signal across Chinden on east side of 33rd, close coordination with ITD. Includes road rehabilitation. Due to significant business access on 33rd St, south of Chinden, as well as the anticipated development driven rebuild of 34th Street as a mixed use corridor, the design should be conducted to 30% and include public outreach to determine the best solution for bike/ped facilities on the southern section. | 2024 | 2025 | Future | Project to begin design in 2024. | 33rd St, Chinden Blvd / Greenbelt
7 | 9 | Allworth/Adams | Reconfigure roadway to remove the turn lane where possible, to include bulb outs and on-street parking and bike lanes with specific requests for parking at or near 42nd and 50th. | Not Programmed | Not Programmed | Not Programmed | Evaluate bulb-outs in connection with development activity in the area. | Alworth St / Adams St
8 | 57 | Glenwood Chinden to Mountain View | Complete sidewalks in accordance with Garden City Code, a minimum of 5' in width and detached adequately to allow for street trees. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | Glenwood, US 20/26 (Chinden Blvd) / Mountain View Dr
10 | 58 | Coffey Chinden to Mountain view | Complete sidewalks in accordance with Garden City Code, a minimum of 5' in width and detached adequately to allow for street trees. Include design for bicylcle traffic. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | Coffey St, Mountain View Dr / US 20/26 (Chinden Blvd)
11 | 59 | Coffey Chinden to Marigold | Complete sidewalks in accordance with Garden City Code, a minimum of 5' in width and detached adequately to allow for street trees. Include design for bicylcle traffic. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | Coffey St, US 20/26 (Chinden Blvd) / Marigold
12 | 10 | 50th St Redesign | Addition of landscaping, pedestrian scaled lighting, and on-street parking on 50th St. | Not Programmed | Not Programmed | Not Programmed | On-street parking currently exists. ACHD will support a city-let effort to evaluate landscaping and lighting. | 50th St Redesign
13 | 11 | 35th St, Greenbelt / Brown St | Install curb, gutter, attached 6' sidewalk with landscape bulb-outs, parking, bike facilities, shallow seepage beds (consider permeable pavers) on 35th St from the greenbelt to Brown St. Match 36th St. design. Includes road rehabilitation. Due to significant business access on 35th St, south of Chinden, design should be conducted to 30% and include public outreach to determine the best solution for bike/ped facilities on the southern section. | Not Programmed | Not Programmed | Not Programmed | Scoped. To be evaluated and prioritized for possible inclusion into future IFYWP updates. | 35th St, Brown St / US 20/26 (Chinden Blvd);
14 | 12 | Carr St, 41st St / 37th St | Construct a new local street with minimal right-of-way. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | Carr St, 41st St / 37th
15 | 13 | Field St Extension | Extend Field St from its western terminus to 50th St. | Not Programmed | Not Programmed | Not Programmed | Defer. To be considered as properties redevelopment. | Field St Extension
16 | 14 | Brown St, 41st St / 36th St | Construct a new local street with minimal right-of-way. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | Brown St, 41st St / 36th
| 16 | Adams St, 37th St / 36th St | Extend Adams St between 37th and its current terminus west of 36th St. | Not Programmed | Not Programmed | Not Programmed | Defer. To be considered as properties redevelopment. | Adams St, 37th St / 36th St
17 | 18 | Road/Greenbelt Interface Treatments | Improve roadways at the greenbelt connections. | Not Programmed | Not Programmed | Not Programmed | ACHD will support a City-led effort. | Road/Greenbelt Interface Treatments
18 | 19 | Brown Street 30th Street to 36th Street. | Complete sidewalks in accordance with Garden City Code, a minimum of 5' in width and detached adequately to allow for street trees. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | Brown St, 30th St /36th St
18/19 | 20 | 32nd Street Chinden to Brown | Complete sidewalks in accordance with Garden City Code, a minimum of 5' in width and detached adequately to allow for street trees. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | 32nd St, Brown St / US 20/26 (Chinden Blvd)
| 21 | Connection 36th Street to VMP | Provide connection in addition to Adams Street and Chinden between 36th Street and VMP. Roads such as Kay, Zinnia, etc. can connect to adjacent street. | Not Programmed | Not Programmed | Not Programmed | Defer. To be considered as properties redevelopment. | Connection to 36th Street to VMP
20 | 22 | 34th Street Chinden to Brown | Complete sidewalks in accordance with Garden City Code, a minimum of 5' in width and detached adequately to allow for street trees. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | 34th St, Brown St / US 20/26 (Chinden Blvd)
21 | 23 | 37th Street Osage to Adams | Complete sidewalks in accordance with Garden City Code, a minimum of 5' in width and detached adequately to allow for street trees. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | 37th St, Osage St / Adams St
21 | 24 | Reed Street | Complete sidewalks in accordance with Garden City Code, a minimum of 5' in width and detached adequately to allow for street trees. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | Reed St, 40th St / 38th St
| 25 | 39th Street Adams to Chinden | Complete sidewalks in accordance with Garden City Code, a minimum of 5' in width and detached adequately to allow for street trees. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | 39th St, US 20/26 (Chinden Blvd) / Adam St
22 | 26 | 39th Street Chinden to Bench | Complete sidewalks in accordance with Garden City Code, a minimum of 5' in width and detached adequately to allow for street trees. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | 39th St, Bench / US 20/26 (Chinden Blvd)
23 | 27 | 40th Street River to Chinden | Complete sidewalks in accordance with Garden City Code, a minimum of 5' in width and detached adequately to allow for street trees. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | 40th St, US 20/26 (Chinden Blvd) / Boise River
24 | 28 | 40th Street Chinden to Bench | Complete sidewalks in accordance with Garden City Code, a minimum of 5' in width and detached adequately to allow for street trees. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | 40th St, Bench / US 20/26 (Chinden Blvd)
| 29 | 41st Street River to Chinden | Complete sidewalks in accordance with Garden City Code, a minimum of 5' in width and detached adequately to allow for street trees. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | 41st St, US 20/26 (Chinden Blvd) / Boise River
25 | 30 | 41st Street Chinden to Bench | Complete sidewalks in accordance with Garden City Code, a minimum of 5' in width and detached adequately to allow for street trees. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | 41st St, Bench / US 20/26 (Chinden Blvd)
26 | 31 | Carr St, 33rd / 36th | Complete sidewalks in accordance with Garden City Code, a minimum of 5' in width and detached adequately to allow for street trees. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | Carr St, 36th St / 33rd St
27 | 32 | VMP | Complete sidewalk Osage to Adams Street. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | Veterans Memorial Pkwy, Osage St / Adams St
| 33 | 42nd Street River to Chinden | Complete sidewalks in accordance with Garden City Code, a minimum of 5' in width and detached adequately to allow for street trees. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | 42nd St, US 20/26 (Chinden Blvd) / Boise River
28 | 34 | 42nd Street Chinden to Ustick | Complete sidewalks in accordance with Garden City Code, a minimum of 5' in width and detached adequately to allow for street trees. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | 42nd St, Ustick Rd / US 20/26 (Chinden Blvd)
29 | 35 | 43rd Street River to Chinden | Complete sidewalks in accordance with Garden City Code, a minimum of 5' in width and detached adequately to allow for street trees. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | 43rd St, US 20/26 (Chinden Blvd) / Boise River
30 | 36 | 43rd Street Chinden to Ustick | Complete sidewalks in accordance with Garden City Code, a minimum of 5' in width and detached adequately to allow for street trees. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | 43rd, Ustick Rd / US 20/26 (Chinden Blvd)
| 37 | 44th Street River to Chinden | Complete sidewalks in accordance with Garden City Code, a minimum of 5' in width and detached adequately to allow for street trees. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | 44th St, US 20/26 (Chinden Blvd) / Boise River
31 | 38 | 44th Street Chinden to Ustick | Complete sidewalks in accordance with Garden City Code, a minimum of 5' in width and detached adequately to allow for street trees. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | 44th St, Ustick Rd / US 20/26 (Chinden Blvd)
32 | 39 | 45th Street River to Chinden | Complete sidewalks in accordance with Garden City Code, a minimum of 5' in width and detached adequately to allow for street trees. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | 45th St, US 20/26 (Chinden Blvd) / Boise River
33 | 40 | 45th Street Chinden to Stockton | Complete sidewalks in accordance with Garden City Code, a minimum of 5' in width and detached adequately to allow for street trees. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | 45th St, Stockton St / US 20/26 (Chinden Blvd)
| 41 | 46th Street Chinden to River | Complete sidewalks in accordance with Garden City Code, a minimum of 5' in width and detached adequately to allow for street trees. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | 46th St, US 20/26 (Chinden Blvd) / Boise River
34 | 42 | Goodall | Extend to 46th Street and to Ellen. | Not Programmed | Not Programmed | Not Programmed | Defer. To be considered as properties redevelopment. | Goodall St Extension, Ellen St / 46th St
35 | 43 | 47th Street Fenton to River | Complete sidewalks in accordance with Garden City Code, a minimum of 5' in width and detached adequately to allow for street trees. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | 47th St, Fenton / Boise River
36 | 44 | 47th Street Chinden to Goodall | Complete sidewalks in accordance with Garden City Code, a minimum of 5' in width and detached adequately to allow for street trees. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | 47th St, Goodall St / US 20/26 (Chinden Blvd)
| 45 | 48th Street Chinden to Creation | Complete sidewalks in accordance with Garden City Code, a minimum of 5' in width and detached adequately to allow for street trees. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | 48th St, US 20/26 (Chinden Blvd) / Creation St
37 | 46 | Creation 48th to Adams | Complete sidewalks in accordance with Garden City Code, a minimum of 5' in width and detached adequately to allow for street trees. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | Creation St, 48th St / Adams St
38 | 47 | 48th Street Thurman Mill ditch to River | Complete sidewalks in accordance with Garden City Code, a minimum of 5' in width and detached adequately to allow for street trees. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | 48th St, Thurman Mill Ditch / Boise River
39 | 48 | Murray Chinden to Bench | Complete sidewalks in accordance with Garden City Code, a minimum of 5' in width and detached adequately to allow for street trees. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | Murray St, Bench / US 20/26 (Chinden Blvd)
| 49 | Ellen Chinden to Bench | Complete sidewalks in accordance with Garden City Code, a minimum of 5' in width and detached adequately to allow for street trees. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | Ellen St, Bench / US 20/26 (Chinden Blvd)
40 | 50 | Fenton 46th to 50th | Complete sidewalks in accordance with Garden City Code, a minimum of 5' in width and detached adequately to allow for street trees. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | Fenton St, 50th St / 46th St
41 | 51 | Bradley 49th to 50th | Complete sidewalks in accordance with Garden City Code, a minimum of 5' in width and detached adequately to allow for street trees. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | Bradley St, 50th St / 49th St
42 | 52 | Field Creation to Alworth | Complete sidewalks in accordance with Garden City Code, a minimum of 5' in width and detached adequately to allow for street trees. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | Field St, 49th St / Creation St
| 53 | 52nd Alworth to River | Complete sidewalks in accordance with Garden City Code, a minimum of 5' in width and detached adequately to allow for street trees. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | 52nd, Alworth St / Boise River
43 | 54 | Remington 52nd to River | Complete sidewalks in accordance with Garden City Code, a minimum of 5' in width and detached adequately to allow for street trees. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | Remington St, 52nd / Boise River
44 | 55 | 53rd Chinden to Bench | Complete sidewalks in accordance with Garden City Code, a minimum of 5' in width and detached adequately to allow for street trees. | Not Programmed | Not Programmed | Not Programmed | To be evaluated and prioritized for possible inclusion into future IFYWP updates. | 53rd St, Bench / US 20/26 (Chinden Blvd)
45 | 56 | Extend Alworth to Marigold | Connect Alworth to Marigold to provide for a main street that runs through Garden City. | Not Programmed | Not Programmed | Not Programmed | Defer. To be considered as properties redevelopment. | Alworth St / Marigold St Extension
| 60 | Reed St Realignment | Realign Reed St at time of redevelopment of adjacent property. | Not Programmed | Not Programmed | Not Programmed | Defer. To be considered as properties redevelopment. | Reed St Realignment
Other
| N/A | Stockton and Osage Feasibility Study | Complete a feasibility study for redefining Stockton and Osage as a road that can accommodate vehicles, bikes, and pedestrians as well as function as a stormwater facility. Please confirm that ACHD is supportive of Garden City utilizing Stockton and Osage as drainage areas, and supportive of the streets being designated for bikes and pedestrians? | Not Programmed | Not Programmed | Not Programmed | ACHD will support a city-led effort through development. | Stockton and Osage Feasibility Study
| N/A | Bikeway Wayfinding Signage | Install wayfinding signage for bicycles. Per Garden City Transportation Needs List. Wayfinding signs were not evaluated as a part of the Neighborhood Plan. | Not Programmed | Not Programmed | Not Programmed | To be installed in connection with build out of the Bike Master Plan. ACHD to review with City through development of the Garden City Neighborhood Plan in FY2020. | Bikeway Signage Programs
| N/A | ACHD bike map- Online | There are a number of bike air and repair station that Garden City has added along the greenbelt that can be added to the map.
| N/A | ACHD bike map- Paper copy | Thank you for adding a Garden City enlargement to the map. Please redesignate as "East End of Garden City" rather than "Garden City' as it shows only a portion of Garden City. The document still classifies George's Cycle as being in Boise rather than Garden City. It appears that the changes have not been made, or that the map has not been updated on ACHDs website. | N/A | N/A | N/A | Bike Map being updated in 2020-2021. Requested changes have been shared with staff. | N/A
| N/A | Maintenance Request | Please refresh the paint designating bike lanes on VMP. Please report action taken. | Not Programmed | Not Programmed | Not Programmed | Request to be shared with Maintenance Department. | N/A
| N/A | Traffic Considerations | 1. Consider adding Osage and Stockton to designated bike routes. This was not evaluated during the Neighborhood Plan. | N/A | N/A | N/A | To be evaluated as part of Garden City Neighborhood Plan.
|  |  | 2. Retime light at 36th Street/ Orchard/ Chinden to allow more time for pedestrians to cross. Please report action taken. | N/A | N/A | N/A | Comments to be shared with Traffic Operations.
|  |  | 3. Retime light at Glenwood/ Chinden to allow more time for pedestrians to cross. Please report action taken. | N/A | N/A | N/A
|  |  | 4. Retime light at Kent/ Chinden to allow more time for pedestrians to cross. Please report action taken. | N/A | N/A | N/A
|  |  | 5. Retime light at Adams/ VMP to allow more time for pedestrians to cross.Please report action taken. | N/A | N/A | N/A
|  |  | 6. Adjust light at Marigold and Glenwood: The turning light on Glenwood for vehicles traveling north turning on west onto Marigold takes two cycles to change if the vehicle is not in turn lane when the light turns red. Please report action taken. | N/A | N/A | N/A
| N/A | Policy Requests | 1. Allow for early input on design plans within Garden City. If City’s comments cannot be accommodated, provide written response to City as to why not prior to any further design of the project. If plans render lots or roadway noncompliant with Garden City Code, present nonconformities for discussion at a joint meeting with City Council and governing board (ACHD Commission, VRT Board). If plans are redesigned after comment resend new plans to City for additional comments at or before 75%. Please provide Commission's response to City. | N/A | N/A | N/A | Requests shared with ACHD Commission. | N/A
|  |  | 2. Notify City of any construction anticipated by July of the prior fiscal year. Please provide Commission's response to City. | N/A | N/A | N/A
|  |  | 3. Identify what conditions are necessary for ACHD to accept drainage on Chinden Boulevard. Please provide Commission's response to City. | N/A | N/A | N/A