## Timeline
| Phase | Action | Leader | Notes | Timeframe
[5 empty] | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan '21 | Feb '21 | Mar '21 | Apr '21 | May '21 | June '21 | July '21 | Aug '21 | Sept '21 | Oct '21 | Nov '21 | Dec '21 | Jan '22 | Feb '22 | Mar '22
Define | Project Definition | Confirm project purpose and framework, as proposed by MRVPD Staff. | MRVPD Steering Committee | 5/21 Steering Cmt meeting. | bar: Timeframe May to Timeframe June
|  | Commit to provide on-going project leadership and resource contribution, as proposed by MRVPD Staff. | MRVPD Steering Committee | 5/21 Steering Cmt meeting. | bar: Timeframe May to Timeframe June
|  | Discuss Leadership Committee make-up and confirm MRVPD representatives. | MRVPD Steering Committee | 5/21 Steering Cmt meeting. | bar: Timeframe May to Timeframe June
|  | Initiate Leadership Committee. | Leadership Cmt Chair | Potential partners are met with, brought up to speed. | bar: Timeframe May to Timeframe July
| Community Vision & Goals | Create plan for organizing and holding community visioning event(s). | Leadership Committee | Budget, fundtraising needs, recruitment. | bar: Timeframe July to Timeframe Aug
|  | Visioning event fundraising, recruitment, planning | Leadership Cmt (+ any other committees if formed) | Timeframe based on fall event; could alternatively be pushed to spring. | bar: Timeframe Aug to Timeframe Oct
|  | Visioning event held | Leadership Cmt (+ any other committees if formed) | Could be held in conjunction with Tri-Town Mtng? | bar: Timeframe Nov
|  | Spearhead on-going community engagement process, including creating sub-committees as needed. | Leadership Committee | bar: Timeframe July to Timeframe Dec
| Indicator Development | Summarize and share visioning event results. | Leadership Committee | bar: Timeframe Dec
|  | Conduct analysis of community vision and goals to define indicator domains. | Leadership Committee | Based on community-ID'd vision & goals
|  | Research and select indicators to be used. | MRVPD Staff
Measure | Data Collection | Secure quantitative and qualitative indicator data. | MRVPD Staff | bar: Timeframe Sept to Timeframe Oct
|  | Prioritize relationships with data partners through data collection. | MRVPD Staff
|  | Survey refinement and outreach. | MRVPD Staff
| Data Analysis | Analyze and interpret data trends in relation to community vision and goals. | MRVPD Staff
|  | Incorporate new platform for data aggregation, analysis, and communication. | MRVPD Staff
Improve | Data Communication & Engagement | Share and communicate data findings. | MRVPD Staff | Online dashboard, presentations, etc. | bar: Timeframe Nov to Timeframe Dec
|  | Engage and coordinate stakeholders to take action based on data findings. | MRVPD Staff
|  | Conduct on-going evaluations to assess project successes and challenges. | MRVPD Staff | (every couple of years)
* A darker shade indicates significant parter involvement in that task

## Local Resources
| Name | Resource
University of Vermont
Department of Community Development & Applied Economics | Kelly Hamshaw | Surveys, data collection, communications
Center for Rural Studies | Michael Moser | Indicators, data, surveys
Center for Research on Vermont | Richard Watts | Communications, research, project support
Internship Programs |  | Communications, research, project support
Spatial Analysis Lab | Brian Voigt | GIS
Chittenden County Regional Planning Commission | Melanie Needle | Indicators, data
Community Indicators Consortium |  | Indicators
Stone Environmental | Alan Hammersmith | GIS, dashboard platform
Agency of Commerce & Community Development | Richard Amore | MPG potential: application due 10/1/20 | https://accd.vermont.gov/sites/accdnew/files/documents/CD/CPR/MPG/MPG_FY21_ProgramDescription.pdf
Vermont Council on Rural Development | Paul Costello | Community engagement

## Dashboards
Software | Cost/Year | Notes
ArcGIS Hub | 500 | Includes all ArcGIS functionality and programs
Dasheroo | $240+ | Template platform, popular to use integrated with other programs; potentially limited dashboards & functionality?
Infogram | $228+
ClearImpact | 2400 | Scorecard software used by state & CCRPC uses
(still researching)