## Sheet1
VILLAGE OF ONTONAGON
AUDIT EXCEPTIONS TRACKER
UPDATED: 12/16/21
| 0 of 8 completed (0%) |  |  |  | Responsible |  | Expected | Actual | Council
|  |  | Action |  | Employee and/or |  | Completion | Completion | Verification
# | Recommendation: | Source: | Required: | Status/Plan: | Committee: | Documented: | Date | Date | Date
1 | Significant Journal Entries | 2014 & 2016 & 2021 Audit | We recommend that the Village take steps to ensure that all significant journal entries are recorded throughout the year and that the Village maintain supporting documentation for all account balances. |  | Finance Committee & Village Manager
2 | Preparation of Financial Statements in Accordance with GAAP | 2014 & 2021 Audit | We recommend that the Village take steps to ensure that all significant journal entires are recorded throughout the year and that the Village maintain supporting documentation fo all account balances. Additionally, the Village can better utilize its current accounting software to assist with financial reporting (allowing for improved reconciliation of receivables, payables, cash and payroll related liabilities). |  | Village Manager & Village Clerk/Treasurer
3 | Capital Assets and Depreciation Listing | 2014 & 2021 Audit | We recommend that the Village maintain a capital asset listing. The subsidiary list should be updated for new capital additions, disposals and depreciation expense. |  | Finance Committee & Village Manager
4 | General Fund - Fund Balance | 2017 & 2021 Audit | We recommend that the Village adopt a fund balance policy which meets the GFOA recommended guidelines and that the Village continue to seek a long-term solution to funding its net pension liability, including the portion attributable to the former employees of the Ontonagon Memorial Hospital. |  | Village Clerk/Treasurer
5 | Segregation of Duties | 2014 & 2021 Audit | We encourage management to actively seek ways to further strengthen its internal controls by requiring as much independent review, reconciliation, and approval of accounting functions by qualified members of management as possible. |  | Finance Committee, Village Manager & Village Clerk/Treasurer
6 | Timely Bank Reconciliations | 2019 & 2021 Audit | We recommend that the Village Council prepare, approve and institute a reconciliation process that ensures bank reconciliations are performed monthly and reviewed by a Council member. We further recommend that the bank statements and all related documents be maintained in accordance with the Records Retentions Act of Michigan. Lastly, we recommend that the Village discontinue cash using external spreadsheets and begin reconciling all cash accounts within the accounting software. |  | Finance Committee, Village Manager & Village Clerk/Treasurer
7 | Expenditures in Excess of Appropriations | 2016 & 2021 Audit | We direct the Village Council to develop budgetary control procedures which will ensure that expenditures do not exceed amounts authorized in the General Appropriations Act or amendments thereof.
8 | Segregation of Duties | 2014 Audit | We encourage management to actively seek ways to further strengthen its internal controls by requiring as much independent review, reconciliation, and approval of accounting functions by qualified members of management as possible.
8 | Lack of Monitoring (Financial Statements) | 2020 2021 Audit | We recommend that the Village Council review these findings and not only implement policies and procedures related to the Village's internal control structure, but also monitor and oversee the activities of the Village. | Report monthly balance sheets along with budget vs actual reports to the Finance Committee/Village Council on a monthly basis. Also, the Budgetary Control Policy along with the Funds Management Policy are to be implemented. | Finance Committee, Village Manager & Village Clerk/Treasurer

## Sheet2
VILLAGE OF ONTONAGON
DEFICIENCY TRACKER
UPDATED: 6/3/2026
| 2 of 18 completed (11%) |  |  |  | Responsible |  | Expected | Actual | Council
|  |  | Action |  | Employee and/or |  | Completion | Completion | Verification
# | Recommendation: | Level: | Required: | Status/Plan: | Committee: | Documented: | Date | Date | Date
2.1 | General Plans; Updating requirements | Deficiency: | VOO shall submit to EGLE, for review and approval, a General Plan in accordance with Part 16 of the Act 399 adiministrative rules. EGLE will notify VOO, in writing, of approval or any deficiencies in the submittal. | Complete | WD | EGLE email 3/10/26 | 2026-06-01 | 2026-03-10 | 2026-04-27
2.2 | Study of water supply requirements for type I public water supply | Deficiency: | VOO shall submit to EGLE, for review and approval, an updated Reliability Study in accordance with Part 12 of the Act 399 adiministrative rules. EGLE will notify VOO, in writing, of approval or any deficiencies in the submittal. | Submitted 6/24/26 | OHM | ACA 2.2 Ontonagon Water Reliability Study 6-24-26 | 2026-08-31
2.3 | Cross connections prohibited | Deficiency: | VOO shall submit to EGLE, for review and approval, an updated written service agreement between the Village of Ontonagon and regional communities connected to the Village of Ontonagon distribution system. This service agreement shall authorize the implementation of a cross connection control program for the distibution system outside the Village of Ontonagon village limits. |  | WD |  | 2026-08-31
2.4 | Storage tanks generally | Significant Deficiency: | VOO shall replace the damaged vent screen on the White Pine elevated storage tank. VOO shall submit to EGLE, for review and approval, photographic documentation of the completed work. | Submitted 5/28/26 | JG |  | 2026-06-01
2.5 | Distribution system valves | Deficiency: | VOO shall submit to EGLE, for review and approval, a written routine valve turning program for all valves in the regional water system in accordance with R 325.11108 of the Act 399 administrative rules. | Submitted 5/29/26 | OHM |  | 2026-06-01
2.6 | Distribution system valves | Deficiency: | Not later than 90 days from EGLE's written approval of the valve turning program under Paragraph 2.5, and by September 30 every year thereafter for the duration of this Compliance Agreement, VOO shall submit to EGLE, for review and approval, a written annual progress report after the implementation of the valve turning plan under Paragraph 2.5. |  | OHM/WD/JG
2.7 | Filtration and disinfection | Deficiency: | VOO shall complete sludge removal of the settling basin. VOO shall submit to EGLE, for review and approval, photographic documentation not later than 14 days from completion of the sludge removal. | Complete | JG | Picture dated 2/12/2026 | 2026-06-01 | 2026-02-12 | 2026-05-11
2.8 | Cross connections prohibited | Deficiency: | VOO shall submit to EGLE, for review and approval, an updated cross connection control program that includes a provision to address all customer classes, including residential customers, in accordance with Part 14 of the Act 399 administrative rules. | Extension requested 6/24/26 | WD/VC | Ordinance 2026-02: Cross Connection Ordinance | 2026-06-30
2.9 | Cross connections prohibited | Deficiency: | Not later than 90 days from EGLE's written approval of the updated cross connection control program under Paragraph 2.8, and by September 30 every year thereafter for the duration of this Compliance Agreement, VOO shall submit to EGLE, for review and approval, a written mid-year progress report indicating the number of cross connection inspections and re-inspections conducted during the period of January 1 through June 30 of the same year for each customer class for the entire regional area served by the Village of Ontonagon water system. |  | WD/JG
2.1 | Approval of chemicals and other materials | Deficiency: | VOO shall install approved anti-siphon devices to all chemical feed systems in accordance with Section 5.5.5 of the most current version of Recommended Standards for Water Works, prepared by the Great Lakes Upper Mississippi Board of State and Provincial Public Health and Environmental Managers (Ten States' Standards). VOO shall submit to EGLE, for review and approval, photographic evidence of the completed work of description, as appropirate. | Submitted 6/26/26 | JG | Pictures dated 6/23/26 | 2026-06-30
2.11 | Storage tanks generally | Deficiency: | VOO shall install 24-mesh screens on all storage tank overflows. VOO shall submit to EGLE for review and approval, photographic evidence of the completed work. | Submitted 5/27/26 & 5/28/26 | JG | Pictures dated 5/22/26 | 2026-06-30
2.12 | Storage tanks generally | Significant Deficiency: | VOO shall submit to ELGE, for review and approval, an updated plan and schedule to repair or replace the White Pine elevated storage tank. The schedule shall include, at a minimum, the following items: (a) A date to submit the final project plans to repair or replace the White Pine elevated storage tank. (b) A written schedule to obtain funding to repair or replace the White Pine elevated storage tank. (c) A date to submit an administratively complete Act 399 construction permit application, in accordance with section 4 of Act 399 (Michigan Compiled Law 325.1004, to repair or replace the White Pine elevated storage tank). (d) A written schedule to complete construction in accordance with the EGLE-issued Act 399 construction permit. | Submitted 6/24/26 | OHM | Village of Ontonagon ACA 2.12 Elevated Storage Tank Schedule | 2026-06-30
2.13 | Storage tanks generally | Significant Deficiency: | Not later than one (1) year from the EGLE-issued Act 399 constuction permit, in the EGLE-approved plan under Paragraph 2.12, VOO shall complete the repair or replacement of the White Pine elevated storage tank in accordance with the EGLE-approved schedule under Paragraph 2.12. Not later than seven (7) days from completion of the work, in accordance with the EGLE-issued Act 399 construction permit, VOO shall notify EGLE to request a site inspection. |  | Engineer
2.14 | Storage tanks generally | Significant Deficiency: | If funding to repair or replace the White Pine elevated storage tank is not obtained in accordance with the EGLE-approved schedule under Paragraph 2.12, then no later than 30 days from notification of funding rejection, VOO shall submit to EGLE, for review and approval, a written revised plan and schedule to complete the White Pine elevated storage tank project. The plan and schedule shall include, at minimum, any unresolved items listed under Paragraph 2.12. The EGLE-approved schedule shall be incorporated into this Compliance Agreement by reference. |  | Engineer
2.15 | Intake inlet and pipeline | Deficiency: | VOO shall submit to EGLE, for review and approval, a written plan and schedule to have the intake structure and horizontal shaft inspected by a qualified diving contractor in accordance with R 325.10907 of Act 399. The EGLE-approved schedule shall be incorporated into this Compliance Agreement by reference. | FIND 2-3 Companies | WD/JG/OHM |  | 2026-08-31
2.16 | Intake inlet and pipeline | Deficiency: | Not later than one (1) year from EGLE's written approval of the plan and schedule under 2.15, VOO shall complete the inspection of the intake structure and horizontal shaft completed in accordance with EGLE-approved plan. VOO shall submit to EGLE, for review, a copy of the inspection report not later than 60 days after completing the inspection. |  | WD/JG
2.17 | Intake inlet and pipeline | Deficiency: | If any deficiencies or repairs are identified in the inspection report submitted under Paragraph 2.16, then not later than 60 days from EGLE's written notification, VOO shall submit to EGLE, for review and approval, a written plan and schedule to address all deficiencies in accordance with Part 9 of the Act 399 administrative rules. |  | WD/JG
2.18 | Filtration and disinfection | Deficiency: | VOO shall have the sludge vacuum control system and sludge vacuum removal system evaluated and repaired by qualified individual(s) in accordance with state and local building codes and regulations. VOO shall submit to ELGE, for review and approval, written documentation of the completed work. |  | JG/Talsma | Need Quote | 2026-11-01