## burn-up graph
-25% increase | +25% increase | Ideal Burn rate | DATE | SPRINT | Estimated project size | Cumulative total points done | Velocity (burn rate)
34.0125 | 56.6875 | 45.35 | 2024-12-06 | SPRINT 17 | #N/A | 37.5 | 37.5 | Burn rate (velocity) is a measure of how much work the team completes each sprint. It’s self-reported by the team—not assigned by a manager—based on actual completed work. This helps track progress, adjust forecasts, and improve planning accuracy over time.
67.7625 | 112.9375 | 90.35 | 2024-12-20 | SPRINT 18 | #N/A | 110.5 | 73
101.5125 | 169.1875 | 135.35 | 2025-01-03 | SPRINT 19 | #N/A | 148 | 37.5
135.2625 | 225.4375 | 180.35 | 2025-01-17 | SPRINT 20 | #N/A | 204 | 56
169.0125 | 281.6875 | 225.35 | 2025-01-31 | SPRINT 21 | #N/A | 253 | 49
202.7625 | 337.9375 | 270.35 | 2025-02-14 | SPRINT 22 | #N/A | 300 | 47
236.5125 | 394.1875 | 315.35 | 2025-02-28 | SPRINT 23 | #N/A | 360 | 60
270.2625 | 450.4375 | 360.35 | 2025-03-14 | SPRINT 24 | 907 | 395 | 35
304.0125 | 506.6875 | 405.35 | 2025-03-28 | SPRINT 25 | 907 | #N/A
337.7625 | 562.9375 | 450.35 | 2025-04-11 | SPRINT 26 | 907 | #N/A
371.5125 | 619.1875 | 495.35 | 2025-04-25 | SPRINT 27 | 907 | #N/A
405.2625 | 675.4375 | 540.35 | 2025-05-09 | SPRINT 28 | 907 | #N/A
439.0125 | 731.6875 | 585.35 | 2025-05-23 | SPRINT 29 | 907 | #N/A
472.7625 | 787.9375 | 630.35 | 2025-06-06 | SPRINT 30 | 907 | #N/A
506.5125 | 844.1875 | 675.35 | 2025-06-20 | SPRINT 31 | 907 | #N/A
540.2625 | 900.4375 | 720.35 | 2025-07-04 | SPRINT 32 | 907 | #N/A
574.0125 | 956.6875 | 765.35 | 2025-07-18 | SPRINT 33 | 907 | #N/A
607.7625 | 1012.9375 | 810.35 | 2025-08-01 | SPRINT 34 | 907 | #N/A
641.5125 | 1069.1875 | 855.35 | 2025-08-15 | SPRINT 35 | 907 | #N/A
675.2625 | 1125.4375 | 900.35 | 2025-08-29 | SPRINT 36 | 907 | #N/A
709.0125 | 1181.6875 | 945.35 | 2025-09-12 | SPRINT 37 | 907 | #N/A
742.7625 | 1237.9375 | 990.35 | 2025-09-26 | SPRINT 38 | 907 | #N/A
776.5125 | 1294.1875 | 1035.35 | 2025-10-10 | SPRINT 39 | 907 | #N/A
This is where work is shaped and sized. Large projects or requests are broken down into epics—moderately sized, valuable work packets. Estimation is done relatively, using past similar work as a benchmark to quickly gauge effort without deep analysis, providing a rough order of magnitude.
|  | EPICS | SMALL (34) | MEDIUM (55) | Large (89)
|  | Refunds |  |  | 89
|  | Agent comm |  |  | 89
|  | Foundations (data) |  |  | 89
|  | Roles |  | 55
|  | VSL |  | 55
|  | Bulk Inv | 34
|  | Credit notes | 34
|  | Reports (R&A) | 34
|  | Reports (Fin) | 34
|  | Reports (SS) | 34
|  |  | 170 | 110 | 267 | 547
Note the green "ideal" burnup rate means this project should be completed end of August
Note the light blue burnup rate means this project could be completed early July if the team improve velocity by 25%
Note the light purple burnup rate means this project probabaly won't be completed before October if the team decrease velocity by 25%

## Practices and Guidelines
Core Practices for Delivery Assurance When Using a Burn-up
Essential Team Principles
Burn-up charts are team tools for insight, NEVER management tools for control
Maintain team psychological safety when discussing estimates and actuals
Teams own their estimates and velocity - no pressure to increase speed
Create safe spaces for teams to update forecasts based on learned realities
Protect teams from using burn-up data as a performance measure
Epic Slicing
Value-stream based breakdown of large initiatives
Focus on achieving consistent batch sizes
Minimize dependencies between epics
Slice based on business value delivery
Maintain granularity suitable for reliable estimation
Estimation Practices
Top-down relative sizing of complex epics
Reference class forecasting using past delivery data
Cross-functional input from architects, devs, and business
Challenge and validate initial estimates
Regular calibration against actuals
Required Workshop Skills
Large-group estimation facilitation
Epic slicing workshop orchestration
Technical and business stakeholder alignment
Risk and dependency identification
Scope refinement techniques
Key Outputs
Consistently sized epic slices
Reliable initial estimates
Clear delivery sequence
Identified risks and dependencies
Realistic burn-up forecasts
Supporting Data
Historical velocity trends
Past epic delivery patterns
Team capacity data
Dependency maps
Risk logs
Data Collection & Automation
Burn-up should be automated from your work management system (Jira, Azure DevOps, etc.)
Manual data entry creates unnecessary overhead and risks errors
Export automation and reporting tools should handle the heavy lifting

## ...or use ChatGPT
Using a combination of Excel tables that you maintain and ChatGPT (or similar) you could update you graph more easily. But a bot can't slice and facilitate staekholders in a workshop (at least not yet!)