## 6-Week Calendar
Day # | Date (edit) | Phase | Task | Owner | Category | Channel/Location | Deliverable/Asset | Priority (H/M/L) | Dependency | Status | Notes
-42 | 2025-08-15 | W-6 | Define campaign goal (streams vs tickets vs email subs) & KPI targets | Manager | Strategy |  | Campaign brief | M |  | To-Do | Pick ONE North Star metric
-42 | 2025-08-15 | W-6 | Confirm team roster, roles, approvals SLA, and calendar lock | Manager | Ops |  | Contact sheet | M |  | To-Do
-41 | 2025-08-16 | W-6 | Finalize masters, alt versions (radio edit, instrumental, clean) | Producer | Audio | DAW/Distributor | WAV Masters | M |  | To-Do | Print at 16/44.1 & 24/48
-40 | 2025-08-17 | W-6 | Split sheets signed; PRO registrations; MLC/SoundExchange prep | Manager | Legal/Admin |  | Signed splits | M |  | To-Do
-39 | 2025-08-18 | W-6 | Artwork approved (3000x3000); thumbnail variants for shorts | Marketing | Creative |  | Cover + thumbs | M |  | To-Do
-38 | 2025-08-19 | W-6 | EPK refresh (bio, photos, quotes, live shots) | Manager | PR |  | EPK link | M |  | To-Do
-35 | 2025-08-22 | W-5 | Shoot hero content: performance MV or live room cut | Videographer | Content | YouTube/Shorts | Final MP4 4K + Vertical | M |  | To-Do
-34 | 2025-08-23 | W-5 | Cut 6 vertical hooks (A–F) + captions | Marketing | Content | TikTok/Reels/Shorts | Hook clips | M |  | To-Do | Test different first frames
-33 | 2025-08-24 | W-5 | Smart link build (Linkfire/ToneDen) + UTM scheme | Marketing | Web/Tracking | All | Smart link URL | M |  | To-Do | Define utm_source,utm_campaign
-32 | 2025-08-25 | W-5 | Radio servicing plan (non-com/college/online) | Manager | Radio |  | Station list & schedule | M |  | To-Do
-31 | 2025-08-26 | W-5 | Tour/show alignment: confirm on-sale or anchor dates | Tour Manager | Live | Venues | Tour one-sheet | M |  | To-Do
-28 | 2025-08-29 | W-4 | Distributor upload: audio, metadata, ISRC/UPC, lyrics, credits | Manager | DSP | Distributor | Delivery receipt | M |  | To-Do | Target ≥21 days lead time
-27 | 2025-08-30 | W-4 | Spotify Canvas & Apple Motion Art drafts | Marketing | Creative | Spotify/Apple | Canvas mp4 | M |  | To-Do
-26 | 2025-08-31 | W-4 | Press list build: Tier 1–3 + local + niche blogs (150+) | PR | PR | Email | Press tracker | M |  | To-Do | Tag by vertical & city
-25 | 2025-09-01 | W-4 | Playlist map: editorial pathways + user curators (200) | PR | Playlists |  | Playlist tracker | M |  | To-Do
-24 | 2025-09-02 | W-4 | Influencer & scene leaders list (50) + value angles | Marketing | Influencer | TikTok/IG | Creator tracker | M |  | To-Do
-21 | 2025-09-05 | W-3 | Press pitch – round 1 (story angle A) with private stream | PR | PR | Email | Pitch v1 | M | EPK | To-Do | Personalize with timestamp fit
-20 | 2025-09-06 | W-3 | Playlist pitch – user curators wave 1 | PR | Playlists | Email/DM | Playlist pitch v1 | M |  | To-Do
-19 | 2025-09-07 | W-3 | Hook test: post clips A–C; read watch-through & saves | Marketing | Content | TikTok/Reels | Performance notes | M |  | To-Do | Pin winner
-18 | 2025-09-08 | W-3 | Street team recruit 25 ambassadors; issue UTM links | Street Team | Community | Discord/IG | UTM codes sheet | M |  | To-Do | Offer exclusive perks
-17 | 2025-09-09 | W-3 | Radio intro email + EPK to MDs/PDs; add to distro sched | Manager | Radio | Email | Servicing plan | M |  | To-Do
-14 | 2025-09-12 | W-2 | Editorial pitch via S4A/AM4A (≥7 days) | Manager | DSP | S4A/AM4A | Pitch form submitted | M |  | To-Do | Highlight hook + story
-13 | 2025-09-13 | W-2 | Press follow-up #1 (angle B if no response) | PR | PR | Email | Follow-up v1 | M | Pitch v1 | To-Do
-12 | 2025-09-14 | W-2 | Influencer outreach with clip + idea (duet/stitch prompt) | Marketing | Influencer | DM | Creator pack | M |  | To-Do
-11 | 2025-09-15 | W-2 | Teaser email to list; pre-save incentive | Marketing | Email | MailerLite/Klaviyo | Email #1 | M |  | To-Do
-10 | 2025-09-16 | W-2 | Finalize live session/acoustic for W+1 | Producer | Audio/Video | YouTube | Alt version | M |  | To-Do
-7 | 2025-09-19 | W-1 | Countdown series begins (7→1) + pin hero clip | Marketing | Content | All socials | Countdown posts | M |  | To-Do
-6 | 2025-09-20 | W-1 | Playlist wave 2; radio follow-up; local press calendar | PR | PR/Radio | Email | Follow-up v2 | M |  | To-Do
-5 | 2025-09-21 | W-1 | Set paid tests ($10–$25/day) to best hook clip | Marketing | Ads | TikTok/IG | Ad set v1 | M |  | To-Do
-4 | 2025-09-22 | W-1 | Tour announce or show announce (if aligned) | Tour Manager | Live | IG/FB/Email | Show announce | M |  | To-Do
-3 | 2025-09-23 | W-1 | IG/TikTok Live rehearsal; pin pre-save | Lead Vocal | Live | IG/TikTok | Live run-through | M |  | To-Do
0 | 2025-09-26 | W0 | Release at 12:01am local; post hero clip + smart link | Marketing | Launch | All | Launch post | M |  | To-Do | Reply to first 100 comments
0 | 2025-09-26 | W0 | Press ‘out now’ note; playlist wave 3; street team push | PR | PR/Playlists | Email/DM | Update note | M |  | To-Do
1 | 2025-09-27 | W0 | Fan reaction montage #1; stitch/duet best ones | Marketing | Content | Reels/Shorts | Montage v1 | M |  | To-Do
2 | 2025-09-28 | W0 | Radio servicing add date; track spins & reports | Manager | Radio |  | Spin log | M |  | To-Do
3 | 2025-09-29 | W0 | Band AMA Live (30 min) with save/add CTA | Lead Vocal | Community | IG/TikTok | AMA | M |  | To-Do
5 | 2025-10-01 | W0 | Ads optimization: shift budget to best-performing hook | Marketing | Ads |  | Ad set v2 | M | Ad set v1 | To-Do
7 | 2025-10-03 | W+1 | Acoustic/live room version drop + behind-the-song clip | Producer | Content | YouTube/Shorts | Alt upload | M |  | To-Do
8 | 2025-10-04 | W+1 | Press follow-up #2 (performance proof + angle C) | PR | PR | Email | Follow-up v3 | M | Stats | To-Do
10 | 2025-10-06 | W+1 | Influencer wave 2 + fan UGC contest | Marketing | Influencer | TikTok/IG | Contest rules | M |  | To-Do
12 | 2025-10-08 | W+1 | Micro-playlists: create/maintain scene lists & add peers | Marketing | Playlists | Spotify | 3 micro-playlists | M |  | To-Do
14 | 2025-10-10 | W+2 | Open-verse challenge + stem drop | Producer | Content | TikTok | Stems pack | M |  | To-Do
16 | 2025-10-12 | W+2 | Tour promo integration: offer bundle (ticket + single) | Tour Manager | Live/Commerce | Ticketing | Bundle link | M |  | To-Do
18 | 2025-10-14 | W+2 | Write 5 learnings; lock next single plan | Manager | Strategy |  | Post-mortem | M |  | To-Do

## Asset Inventory
Asset | Status | Owner | Location/Link | Notes
WAV Master (16/44.1) |  | Producer
WAV Master (24/48) |  | Producer
Instrumental |  | Producer
Clean/Radio Edit |  | Producer
Lyrics (timed) |  | Manager
Cover Art 3000x3000 |  | Marketing
Thumbnails (Vertical) |  | Marketing
Spotify Canvas (3–8s) |  | Marketing
Apple Motion Art |  | Marketing
EPK (bio/photos/quotes) |  | Manager
Vertical hooks A–F |  | Marketing |  | A/B test
Smart Link + UTM scheme |  | Marketing
Press Photos (landscape/portrait) |  | Videographer

## Legal & Admin
Item | Owner | Status | Notes
Split sheets (all writers/producers) | Manager
Producer agreements / work-for-hire | Manager
Samples cleared (master & publishing) | Manager
ISRC assigned / UPC generated | Manager
PRO registration (ASCAP/BMI/SESAC etc.) | Manager
Publisher registration (if applicable) | Manager
MLC registration (mechanicals) | Manager
SoundExchange (non-interactive digital) | Manager
Neighboring rights (if intl focus) | Manager
Artwork/photo licenses | Manager
Credits/roles finalized (DAP, liner) | Manager

## Press-Playlist Tracker
Type (Press/Playlist/Influencer) | Tier (1/2/3) | Outlet/Playlist | Contact/Handle | Region | Fit Notes | Pitch Variant | Date Sent | FU #1 | FU #2 | Result | Link | Owner | Notes

## Radio Tracker
Station | Type (College/Online/Non-Com) | MD/PD | Email | Add Date | Status | Spins/Wk | Market/City | Notes

## Street Team & UTM
Ambassador | Handle | UTM Source | UTM Campaign | Unique Link | Clicks | Saves | Email Subs | Notes

## Budget & ROI
Category | Planned $ | Actual $ | Notes
Artwork | 150
Video (hero) | 600
Shorts (editing) | 150
Ads (test/opt) | 250
PR (tools/subs) | 50
Radio Servicing | 100
Merch/Bundle samples | 100

## Analytics Dashboard
Week | Unique Listeners | Saves | Saves/Listener % (calc) | Early Skip % (est) | Playlist Adds (Alg/Ed/User) | Repeat Listeners | Email Subs (Δ) | TikTok Views (Top Clip) | YT Shorts Views (Top Clip) | IG Reels Views (Top Clip) | Ad Spend $ | CPC (calc) | Notes/Learnings
1 |  |  | #ERROR! | [8 empty] | #ERROR!
2 |  |  | #ERROR! | [8 empty] | #ERROR!
3 |  |  | #ERROR! | [8 empty] | #ERROR!
4 |  |  | #ERROR! | [8 empty] | #ERROR!
5 |  |  | #ERROR! | [8 empty] | #ERROR!
6 |  |  | #ERROR! | [8 empty] | #ERROR!
7 |  |  | #ERROR! | [8 empty] | #ERROR!
8 |  |  | #ERROR! | [8 empty] | #ERROR!

## Content Matrix
Theme | Persona | Format | Prompt | Owner | Cadence
Hook Highlight | New listener | 15–20s vertical | The line that converts saves | Lead Vocal | 2x/wk
Player POV | Musicians | Guitar/bass/drums POV | Riff breakdown/bar 1–8 | Guitar | 1x/wk
Live Energy | Scene fans | Crowd clip | Chorus drop live | Tour Manager | 1x/wk
Behind the Mix | Producers | DAW screen | Vocal chain 10s | Producer | 1x/wk
Story Bite | Casual | Face-to-cam | Why we wrote it | Lead Vocal | 1x/wk
Community Lift | Peers | Micro-playlist | 3 bands we love | Marketing | biweekly

## Version Strategy
Version | Length | BPM/Key | Use Case | Status
Album/Single Master |  |  | DSP main
Radio Edit |  |  | Radio/Video
Clean Edit |  |  | Family-safe/Sync
Instrumental |  |  | Press/Sync/UGC
Acoustic/Live |  |  | W+1 content
Stems Pack |  |  | Open-verse/remix

## Live-Tour Integration
Date | City/Venue | Cap | Event Type (Headliner/Support) | On-Sale URL | Promo Asset | Bundle (Y/N) | Notes

## Roles & Approvals SLA
Role | Owner | Approval SLA (hrs) | Decisions
Manager |  | 24 | Budget, release date, final assets
Lead Vocal |  | 24 | Vocal takes, messaging tone
Producer |  | 24 | Mix/master sign-off
Marketing |  | 24 | Ads, captions, thumbnails
PR |  | 24 | Press targets & angles
Tour Manager |  | 24 | Show/tour alignment
Street Team Lead |  | 24 | Ambassador tasks & tracking