## Slide 1: St Johns County Comprehensive Plan Update
Timeline and Actions for the St. Johns County Civic Roundtable
Beth Tate
Vice Chair, St. Johns County Civic Roundtable

## Slide 2: March 21 Update from Growth Management
Plan must be evaluated every 7 years
  Letter of determination due to State by 8/2024
  Comprehensive plan transmittal due 1 year later, 7/2025
An update is recommended by Growth Management
  State regulations
  Population increases and other changes in the county have impacted all required elements

## Slide 3: Process
Board of Commissioners direction on whether to update
A “Broad Process Review”
  Legal – what is required
  Policy – approach to goals/objective/policies and other elements
Internal review of each element
  Updates to goals ,objectives, policies for each element
  Update Map Series
Draft Comprehensive Plan Update for public review.

## Slide 4: After Draft for Public Review
Public Review and Comment – suggested 30 days, Commissioners agreed to 60 days
  Submit comments via web/email/mail
  Public comment meetings (proposed 5 Town Halls, one in each district)
  Established public review
Staff analysis of public comments
  Categorization
  Quantification
Update the draft in response to public comments

## Slide 5: Final Comprehensive Plan Update
Board of Commissioners review
  Public Hearings

## Slide 6: Milestones
August 2024 – Letter of determination to the Florida Department of Economic Opportunity
June 2025 – Latest date for transmittal (PZA Hearing)
July 2025 – Latest date for transmittal (BOCC Hearing)
State requires 60-day review after transmittal
Adoption Hearings
  Approximately October 2025

## Slide 7: Direction to Staff
Proceed with comprehensive plan review process with 3 specific directions
  Engage an Independent Faciliator to proceed with the process of working with all the stakeholders
  Extend the comment period from thirty to sixty days
  Conduct at least five town hall meetings, one in each district prior to any final action by the Board on the Comprehensive Plan recommendations

## Slide 8: Elements of the Comprehensive Plan
Land Use
Transportation
Housing
Infrastructure
Coastal Conservation
Recreation and Open Space
Intergovernmental Coordination
Capital Improvement
Property Rights

## Slide 9: Proposed Actions for the Roundtable
Update the Long-Range Plan/Vision Points for the Civic Roundtable
  Align the Vision Points to the elements of the Comprehensive Plan
Help prepare the community for the Town Hall meetings
  Volunteers to help lead discussions on elements of the Comprehensive Plan
  Conduct community meetings in each district
  Focus in each District on the elements of the plan most crucial to that District
Roundtable Leadership to attend each of the Town Hall Meetings
  Help present the Round Table positions

## Slide 10: Discussion