# Summary

### Attendees:

| ### Name | Title | Representing |
| --- | --- | --- |
| Bruce Vogen | Resident |  |
| Elise Semonian | Planning Director | Town of San Anselmo |
| Javier Trujillo | Chief Assistant Director | County of Marin |
| Jonathan Logan | VP Community Engagement | Marin Community Foundation |
| Liza Massey | Chief Information Officer | County of Marin |
| Michael Frank | Executive Officer | Marin General Services Agency |
| Ross Millerick | Trustee | Novato Unified School District |
| Rebecca Woodbury | Resident |  |
| Jeff Daniel | Project Manager | Marin IST |
| Nina Bell | Project Administrator | Marin IST |

### Location:

MS Teams Virtual Meeting

### Agenda:

- Announcements

- Public Outreach

- Draft Plan Outline

- Next Steps

### Notes:

- Announcements

(see slide 5 below)

- Public Outreach

- Focus Groups

- Fire Chiefs and Clerks focus groups have met.  The input has been good and we are getting new information.   We have a Fire Chief who has volunteered to be on the Gov/Emer Working Group.

  - The combination of a short Digital Marin overview followed by discussion on open ended questions is working well.

  - Facilitators should ask focus groups for names of additional people we should interview.

- Surveys

  - We are already getting SurveyMonkey surveys in

  - The Business and Residents surveys supported by Magellan should be ready in a few days.

  - We continue to get inquiries over GoDigitalMarin.org

  - Graphics or messaging we can send other to promote Business and Residents so the groups we contact don't have to do it.  (Rebecca will have examples ready by Jan 27th)

- Omar Carrera (Canal Alliance) has joined the Residents group.  He offers to help with translation.

- Transparency:

  - Work Groups will have minutes and a recording posted on the website.

  - We will not be publishing Focus Groups because we want participants to feel free to raise sensitive items.

  - Focus Group minutes will be on the MS Teams site for all Work Groups to view.

  - Survey questions and results will also be posted on MS Teams for Work Groups to view.

  - Residents may participate in Focus Groups on a case by case basis.  We want to ensure the participants don’t perceive any risks that might limit their openness and participation.  The promise of anonymity is vital for information to flow.

  - Transparency is achieved by Residents team members on each Work Group.  They will have access to the same data (survey results, focus group notes, interview summaries as the other Work Group members.   The Work Group, including Residents, can then identify where more information, analysis, or transparency is needed.   Similarly the drafts and final plan will be approved by the ESC which has Residents representatives.

- Draft Table of Contents

- We came up with a draft to make sure we are communicating with Magellan on what we expect to produce.

- There was consensus that the format should be brief with the interesting recommendations up front.   Details can then be shared later in the plan.

- (see slides 11-14 below)

- Discussion

  - Magellan’s Data Collection Questions:

  - The questions going out right now are about what they (i.e. schools) have now. The needs outreach comes later.

  - Ross recommended we invite them up front to give us their requirements.  This might help inspire them to share asset information.

  - Providers and potential providers were discussed:  Zayo, Sonic, WebPerceptions, Common.net, Dish, CBRS wireless, and Starlink.   Michael shared how the Fire Chiefs had mentioned an interest in satellite communications because they aren’t susceptible to terrestrial disasters.

- Next Steps

  - Next Meeting Feb 4th at 3pm

# Recording

This meeting was recorded and can be viewed on our MS Teams Channel:

1/21/21 Digital Marin ESC meeting

# Slide Deck

Slide 1

Slide 2

Slide 3

Slide 4

Slide 5

Slide 6

Slide 7

Slide 8

Slide 9

Slide 10

Slide 11

Slide 12

Slide 13

Slide 14

Slide 15

Slide 16

Slide 17