## Workplan
Item # | Goal | Objective | Description | Lead | Support | Status | Status | Staff Recommendation | Cost | Time | Staff Notes
1 | A City that Works | Fiscal & Org Sustainability | Develop a fiscal sustainability plan with the community that balances City services with available revenues and integrates policies and identifies potential revenue sources that can ensure long-term financial health and effectiveness of the City. | FIN | CMO | Complete | COMPLETE | Complete
2 | A City that Works | Fiscal & Org Sustainability | Continue implementing strategies to reduce pension costs and unfunded liabilities. | FIN |  | Complete | COMPLETE | Complete
3 | A City that Works | Fiscal & Org Sustainability | Develop a budget-in-brief to provide the City’s financial information in an understandable, accessible format. | FIN | EDOG | Complete | COMPLETE: Rolled out with FY 20-21 Budget and available on the City's web page. Will continue to be rolled out with the annual budget. | Complete
4 | A City that Works | Fiscal & Org Sustainability | Review and update the City’s Development Impact Fees where appropriate. | CMO | CDD | In Progress | IN PROGRESS: Staff has continued to do annual increases for those fees with annual increase provisions incorporated into the individual fee increases. However, a more comprehensive review of impact fees is needed to address the lack of annual increase provisions in certain fees (including housing in lieu fees), respond to VMT transition, reconsider fee structure to incentivize affordable housing, discuss assessment and collection procedures, update nexus studies, (PW&U - consider storm water impact fee), and overall update and streamline the City's impact fee structure. | Green | 1 | 1 | I think the time and cost could vary significantly on this task depending on how far we take it. There will be a more comprehensive reconsideration of impact fees as part of the GP update. However, there are also facets of our existing impact fee structure that are dysfunctional and do not facilitate the type of development we want to see. Some level of update is critical and a deeper dive may be able to be postponed to coincide with the GP update.
5 | A City that Works | Fiscal & Org Sustainability | Improve the responsiveness and efficacy of the City to its residents by examining potential changes and updates to the City Charter. | CAO | CMO | Not Initiated | NOT INITIATED | Yellow | 2 | 3 | Consider surgical approach to making specific updates or full Overhaul of entire charter.
6 | A City that Works | Fiscal & Org Sustainability | Become a Helen Putnam Award of Excellence City. | CMO | EDOG | Ongoing | ONGOING: Applications submitted on April 8, 2021 for the CCS Partnership Intergovernmental Collaboration Award (Emergency Fire Response) and Community Services and Economic Development Award (COVID Business Response). | Ongoing
7 | A City that Works | Fiscal & Org Sustainability | Leverage local, regional, and state programs and resources to maximize city revenues. | FIN | FINANCE | Ongoing | ONGOING: received grant awards through state housing grants, including SB 2 funds, LEAP funding. Staff also partnered with SMART and Danco to submit for a grant funding through the Affordable Housing Sustainable Communities funding. New Priority Development Area designation around the Corona SMART station and expansion of the Downtown SMART station PDA will create grant funding opportunities to seek in the coming years. Additionally, applying and receiving Certified Local Government status will open up funding opportunities for historic preservation items. Additionally we should have an on demand grant writer by the end of Spring. | Ongoing
8 | A City that Works | Fiscal & Org Sustainability | Recruit, hire, retain, and advance a workforce that is diverse, representative, skilled, talented, and prepared to meet the demands of a full-service City. | HR | CMO | Ongoing | ONGOING: Updated recruitment materials to appeal to a more diverse audience. We have initiated internal training programs to focus on diversity, equity and inclusion. | Ongoing
9 | A City that Works | Fiscal & Org Sustainability | Study the feasibility of developing a City-wide Fellowship Program with Sonoma State and/or other institutions of higher education. | HR |  | In Progress | IN PROGRESS: The police department currently has a robust internship program with both schools. The city is actively hiring interns in various departments to provide career development opportunities and to enhance future candidates for recruitment and enhance relationships with educational institutions. Initial discussions with Sonoma State University regarding a master’s level Fellowship Program have taken place and further discussions are needed prior to establishing a program. | Green | 1 | 2
10 | A City that Works | Fiscal & Org Sustainability | Make the City of Petaluma a model employer, encouraging creativity and innovation, and enhancing connections between our staff and the community. | HR |  | Ongoing | ONGOING: The City is focusing on diverse hiring and professional / leadership development. After the city is reopened we will be evaluating a city-wide telecommuting program that will allow greater work/life balance. | Ongoing |  |  | HR to work on this - flesh out work completed and goals to prioritize. Review this item to create tangible goals and add them to the list. Add info about repopulating and staff transition into working onsite. Rebuilding org culture.
11 | A City that Works | Fiscal & Org Sustainability | Institute staff training programs to enhance staff expertise and advancement. | HR | CMO | Ongoing | ONGOING: Identify standard training for new supervisors, and professional development minimum standards for all positions. Once the standards have been identified, a training program will be developed for employees. | Ongoing |  |  | Consider combining with staff employer item.
12 | A City that Works | Fiscal & Org Sustainability | Host staff trainings in compliance with federal / state regulations including harassment prevention, workplace security, as well as other relevant staff trainings which will be identified through a needs-assessment. | HR | CMO | Ongoing | ONGOING: Citywide Harassment training was completed. Ongoing, annual training will continue. | Ongoing
13 | A City that Works | Fiscal & Org Sustainability | Establish a new employee orientation program. | HR | CMO | Not Initiated | NOT INITIATED | Green | 1 | 2
14 | A City that Works | Safe, Sustainable, Smart Infrastructure | Identify funding options to complete Petaluma’s planned cross-town connectors. | PWU | CMO | In Progress | IN PROGRESS: Progress continues with traffic analysis on evaluating crosstown connectors with level of service and vehicles miles traveled, additional planning work has been completed including Caulfield Bridge with flood impact analysis and additional cost estimation, soils borings for geotechnical report. On the Lynch Creek Trail a project to improve the surface of the trail from Payran to the Lynch Creek crossing went out to bid in April 2021 for completion of construction in early summer 2021. Funding sought for additional improvements to the Lynch Creek Trail. Is there anything with the VMT discussion that could be incorporated here as an updated way to look at our cross town connectors plans? | Green | 3 | 2 | While there are not sufficient Traffic Impact Fees (TIF) to complete the two larger Cross Town Connectors, Caulfield Bridge and Rainer. The preparatory work, planning and EIR on Caulfield should continue to get it close to ready in case augmented funding can be obtained in the coming years. Rainer cross town connector planning and environmental work should also be kept fresh. There is some TIF available for the Lynch Creek Trail, it is limited to ~33% of total cost of the project, but some significant improvements could be made with the TIF and preparatory work for additional future phases of upgrading that cross town connector and access to it.
15 | A City that Works | Safe, Sustainable, Smart Infrastructure | Identify funds and develop plan to improve Petaluma’s streets and roads. | PWU |  | In Progress | IN PROGRESS: Following the passing of the Measure U sales tax measure, presented an option to complete upfront investment of an additional $25M in the City's street infrastructure improving pavement condition and configuration to support Active Transportation and mutli-modal transportation. | Green | 3 | 3 | A, if not, THE Top priority for PW&U
16 | A City that Works | Safe, Sustainable, Smart Infrastructure | Complete the reconstruction of Maria Drive, Sonoma Mountain Parkway, and N. McDowell Blvd. | PWU |  | In Progress | IN PROGRESS: Maria Drive construction is completed. Design contract for designing N.McDowell as a 'complete street' has been awarded. A $550,000 grant of SB1 funds added to allocated street maintenance funding to fund a ~$3M construction project in Fee 21/22. Additional grant funding being sought to complete additional work along the N.McDowell Corridor from Sunrise Parkway to Old Redwood Highway to make additional improvements for bike, pedestrians, and transit. Designs and work to be e coordinated with new SMART station and affordable housing project that is being planned at Corona and N. McDowell. | Yellow | 3 | 3 | For North McDowell staff needs to make sure recently received rough order magnitude cost estimate of ~$10M is communicated out to Council and community and outlay the plan and funding to reach the end vision. Additional funding request part of AHSC grant application with SMART and Danco.
17 | A City that Works | Safe, Sustainable, Smart Infrastructure | Upgrade traffic signal management by re-establishing full-time traffic engineer position. | PWU |  | Complete | COMPLETE | Complete
18 | A City that Works | Safe, Sustainable, Smart Infrastructure | Establish and improve paths, as useful transportation options, and make walking and biking easy, fun and safe. | PWU |  | In Progress | IN PROGRESS: Continue to require trail, sidewalk, and bike facility segments are part of development projects even if incremental segments to ultimately achieve the full network as envisioned in the General Plan. I believe approximately 10% of traffic impact fees are earmarked for bike and ped amenities and may be a good thing to look at with development projects to see if the City can contribute beyond what nexus we have with private development to further help close gaps in the existing network. Additionally, look at local mitigation options through creating a citywide vat program to increase citywide improvements in our bike and ped infrastructure. | Green | 1 | 2
19 | A City that Works | Safe, Sustainable, Smart Infrastructure | Implement community bike share system and explore other multi-modal transportation offerings. | PWU |  | In Progress | IN PROGRESS: Community survey completed and outreach in progress. Multi-jurisdictional agreement will be brought before Council in Q4 in FY21. Expected program rollout in Q1-Q1 FY22. | Green | 1 | 1
20 | A City that Works | Safe, Sustainable, Smart Infrastructure | Better integration of multi-modal transportation with street designs. | PWU |  | In Progress | IN PROGRESS: Updating bus stop design standards. Earlier integration of multimodal transportation in earlier corridor design process to help better create complete streets. Significant change in focus and increased priority placed on bicycle, pedestrian, and transit facilities when streets are reconstructed, initial completed examples include Maria Drive and Sonoma Mountain Parkway, projects in design include Petaluma Boulevard South Road Diet and the N. McDowell Complete Streets project. Additional, low cost measures are being looked at to complete in conjunction with pavement resurfacing projects. Consultant under contract to assist with quick designs that will help implement changes that support Safe Routes to School and the bicycle and pedestrian plans in the General plan. | Yellow | 2 | 2
21 | A City that Works | Safe, Sustainable, Smart Infrastructure | Create a more efficient corporation yard at Hopper Street, including addressing the decommissioning of the existing water plant facilities and integrate uses including the adjacent COTS and Animal Shelter facilities. | PWU |  | In Progress | IN PROGRESS: Phase 1 of demolition of existing water plant facilities complete. Phase 2 of demolition to be completed in 2021. | Yellow | 3 | 3 | Initial demolition phases, and initial planning effort commenced. Phase 2 demolition design being worked on, nearing completion. Could be an item that is post-postponed due to resources. Master planning effort needs a more comprehensive look at other locations, and better understanding of long-term program requirements of other tenants, COTS and animal services, and compatibility with adjacent planned development.
22 | A City that Works | Safe, Sustainable, Smart Infrastructure | Complete the second SMART station at Corona. | CMO | CDD | In Progress | IN PROGRESS: City continues to work with the housing developer on Corona property; SMART has prioritized Petaluma 2nd Station in it's FY 22-29 CIP. SMART is preparing to submit a joint application in June to the State’s Affordable Housing Sustainable Communities for funding our Petaluma North Station at Corona Road. The project proposal will also include a menu of other active transportation investments, as well as support for a City of Petaluma 131-unit affordable housing project adjacent to the future SMART station. SMART’s proposed partners in the application process include the City of Petaluma, including Petaluma Transit, and the affordable housing project developer Danco Communities, who has agreed to donate 1.272 acres to SMART for the construction of parking facility for this rail station. We expect to have the results of this grant in the October November 2021 time frame. | Green | 3 | 3 | Staff continues to work closely to prepare the joint application with Danco and SMART for the AHSC funding cycle. Application is due on June 8th and funding awards should be announced in October 2021. The City will participate through $2M in TIF funding for SMART, and potential award of housing funds to help fund the Danco affordable housing project if other funding is awarded.
23 | A City that Works | Safe, Sustainable, Smart Infrastructure | Expand transit service on primary corridors. | PWU |  | Not Initiated | NOT INITITATED | Yellow | 2 | 3 | Additional transit routes and services identified for expansion and improvement. Most were tabled due to decreased ridership and uncertain fiscal situation during Covid (now returning to normal). Will be further refined including cost estimates as part of 2021 Short Range Transit Plan Update
24 | A City that Works | Safe, Sustainable, Smart Infrastructure | Provide additional real-time schedule information and infrastructure for Petaluma Transit. | PWU |  | In Progress | IN PROGRESS: Petaluma Transit now integrated with Google real-time transit feeds and regional 511 real time information. Currently working towards installation of real-time signs at additional bus stop locations | Yellow | 2 | 1
25 | A City that Works | Safe, Sustainable, Smart Infrastructure | Inventory and promote all road paving and reconstruction projects with funding sources and dates of completion, made in the last five years. | PWU |  | Complete | COMPLETE | Complete
26 | A City that Works | Safe, Sustainable, Smart Infrastructure | Update the City’s Bicycle and Pedestrian plan and realize opportunities for crosstown connections for all modes of transportation. | PWU |  | In Progress | IN PROGRESS: This will be a key component of the General Plan update process over the next 2-3 years. Opportunities to increase bike and ped opportunities through VMT mitigation considerations. Staff will look for opportunities to apply for grant funding. | Green | 2 | 2
27 | A City that Works | Safe, Sustainable, Smart Infrastructure | Encourage transit use through expanded service, pass programs, partnerships, and promotion. | PWU |  | Ongoing | ONGOING: continue community outreach to promote transit. Continued to offer SRJC Student Pass Program. Provided free transit service for ten months during COVID-19 pandemic. Started to offer the Clipper Start means-based fare program in February 2021. Multiple transit collaboration projects undertaken in conjunction with nearby transit agencies (SCTA, MTC). (Planning) as we move forward lets also think of this through the lens of VMT mitigation options. | Ongoing | 1 | 1 | Barrier to progress in this area is Transit Staffing. Currently staff is without Transit planner positions which the added bandwidth is key in moving these programs forward. May have synergy as part of citywide VMT mitigation development.
28 | A City that Works | Safe, Sustainable, Smart Infrastructure | Consider a program to make some downtown streets pedestrian-only. | PWU |  | In Progress | IN PROGRESS: Started Petaluma Slow Streets initiative to better balance space for alternative and vehicular modes. Implemented Petaluma Free Range outdoor dining and parklet pilot program, which included focused and expedited city staff review and hands on facilitation and tent purchases to help transition to winter weather. Water Street included as part of the Slow Street program. | Red | 2 | 3 | Currently have staff bandwidth issues to move this program forward. Stalled out in a pilot program. Traffic Engineer has lead but is running several critical CIP projects, including pavement management program, a top priority.
29 | A City that Works | Engaged, Activated, Connected Community | Establish a centralized, citywide community engagement and communications program that emphasizes two-way, ongoing communications and robust community engagement. | EDOG | CMO | Ongoing | ONGOING: We hired a contract employee to support City communications. The division completed daily updates in English and Spanish during the early part of the Covid Stay at Home Quarantine; that update now goes out weekly. In addition, social media posts in English and Spanish go out weekly to all social channels. We established a text based notification system. We've updated many web pages, redesigned the home page and added slider campaigns to the home page. We have also developed new website sections focused on Climate Action; Diversity, Equity, and Inclusion; Emergency Preparedness; and Public and Private projects. We are coordinating citywide communications so that city communications are unified, in a consistent voice, and easy to understand by the public. Communications staff completed advanced training courses in public engagement (Pepperdine University) and emergency communications (CAL OES). | Ongoing
30 | A City that Works | Engaged, Activated, Connected Community | Engage and support all City committees and commissions, allowing opportunities to cross-pollinate with each other and to better integrate and provide recommendations for improved City decision-making. | CLERK | CAO | In Progress | IN PROGRESS: Continued work on City bikeshare subcommittee of Transit and Pedestrian Advisory Committees. Had multiple members (staff and public) from existing committees join new committees (Climate Action , General Plan, and Vehicle Miles Traveled Committees) and present on cross committee projects (i.e. Climate Action Framework) (CAO) have begun providing all committees and commissions Brown Act training and will be providing additional training on public records and ethics. | Green | 1 | 3 | Staff training, streamlining, cross politization tasks. New board management software coming online.
31 | A City that Works | Engaged, Activated, Connected Community | Provide post-meeting summaries of all City Council and Planning Commission meetings and promote on all City communication platforms. | CLERK | EDOG | Ongoing | ONGOING: Staff is including a summary of upcoming City Council agendas and past meeting decisions in the weekly updates. | Ongoing
32 | A City that Works | Engaged, Activated, Connected Community | Coordinate and enhance cross-departmental social media collaboration. | EDOG |  | Ongoing | ONGOING: Staff completed a social media communications plan and has a team in place to post to, and monitor, social media channels including: Facebook, Instagram, Twitter, and Nextdoor. | Ongoing
33 | A City that Works | Engaged, Activated, Connected Community | Develop and publish public record request guidelines on City website. | CAO | CAO | Complete | COMPLETE | Complete
34 | A City that Works | Engaged, Activated, Connected Community | Promote outreach, inclusion, and involvement of Petaluma’s diverse communities through expanded translation and interpretation services in City information and programs, recruitment strategies, and developing leadership opportunities. | EDOG | HR | Ongoing | ONGOING: New "Ayuda en Español" page complete. All newsletters and social media currently translated. Live translation of City meetings are underway. Creating a working group / task force to continue to develop and implement Latinx outreach programs to continue and improve effective outreach. | Ongoing
35 | A City that Works | Technology, Org Effectiveness | Develop a citywide IT Masterplan that identifies and prioritizes City technology needs, funding, and implementation strategies. | EDOG |  | Complete | COMPLETE: The plan is complete and implementation is underway. | Complete
36 | A City that Works | Technology, Org Effectiveness | Implement an online permitting system. | EDOG | CDD | In Progress | IN PROGRESS: This is on track for full implementation on July 1, 2021. | Green | 3 | 1 | This is almost complete. Staff continues to work closely with Energov to prepare for the transition which is anticipated for August 2021.
37 | A City that Works | Technology, Org Effectiveness | Implement agenda management software system to improve the efficiency of electronic meeting packet preparation and to increase public engagement. | CLERK | EDOG | In Progress | IN PROGRESS: We determined that the selected software would not meet our needs. A new software solution has been selected and will be implemented in calendar year 2021. | Green | 1 | 1
38 | A City that Works | Technology, Org Effectiveness | Complete the roll-out of an updated City website that creates a more user-friendly, accessible, and interactive information resource and online experience for the community. | EDOG |  | Complete | COMPLETE | Complete
39 | A City that Works | Technology, Org Effectiveness | Leverage technology to improve efficiency including improved use of meeting and conferencing technologies. | EDOG |  | Ongoing | ONGOING: City Council Chamber upgrades will be planned to allow for in person and virtual participation. (Planning) during COVID we made all meetings accessible remotely to ensure the opportunity to participate even during shelter in place and significantly increased regular participation in public hearings. (Clerk) we are expanding public comment methods for public meetings. | Ongoing
40 | A City that Works | Technology, Org Effectiveness | Enhance mobile technology to increase efficiency of field staff. | EDOG |  | Ongoing | ONGOING: Computer fleet replacement is underway and expected to be complete by the end of the fiscal year. Mobile working is a permanent part of ongoing fleet management programs. | Ongoing
41 | A City that Works | Technology, Org Effectiveness | Encourage the expansion of internet fiber by carriers to provide access to our community. | EDOG | PW&U | In Progress | IN PROGRESS: City contracted with Sonic to install fiber between City facilities. This will provide a fiber optic backbone to support more fiber optic installations throughout the City. Staff have integrated this work into the Technology Advisory Committee agenda. | Yellow | 1 | 3 | Staff is working to incorporate new Fiber installations as part of new roadwork. Technology Advisory Committee is working on limited, small cell and tower recommendations for the City.
42 | Environmental Legacy | Climate Ready | Find ways for City operations to reduce greenhouse gas emissions, conserve water, decrease waste, and minimize use of fossil fuels and investigate and pursue options for carbon sequestration. | CMO | PWU | In Progress | IN PROGRESS: Acquired multiple grants to help fund the next wave of electric Petaluma Transit buses, have cycled out older vehicles for new/more efficient, electric, or hybrid vehicles depending on availability (if they exist) Adopted Climate Emergency Framework which set a goal of carbon neutrality by 2030 and contained goals in the subjects of Equity, Mitigation and Sequestration, Adaptation, and Engagement. Implementation of action items is ongoing. | Green | 2 | 3 | This goal is too broad. Much of this is ongoing; some tasks be quick and inexpensive (e.g. installing solar on City facilities), while others are very expensive and long-duration (e.g. redesigning all roads for active transportation)
43 | Environmental Legacy | Climate Ready | Consider adopting energy codes that exceed current requirements. | CDD | CAO | Complete | Complete: (CAO) All electric ordinance being presented to the City Council 5/3/21. (Planning ) All electric in new construction ordinance presented to the CAC on 4/8/2021 and PC on 4/13/2021. | Yellow | 1 | 3 | Petaluma took a huge step toward this goal by adopting new code requirements that all new construction and significant remodels and expansions will be all-electric. Additional code updates may look at additional efforts to decarbonize existing buildings, increase EV and solar, mandate greywater systems, etc. | Create new workplan item for future work and mark this item as complete
44 | Environmental Legacy | Climate Ready | Consider and move forward to adopt City’s participation in Sonoma Clean Power’s Evergreen program. | CMO | FINANCE | Complete | COMPLETE. City will transition to Evergreen July 2021. | Complete
45 | Environmental Legacy | Climate Ready | Consider requiring new development to participate in Sonoma Clean Power’s Evergreen program. | CDD | CAO | Not Initiated | NOT INITIATED: While not able to require private consumers to opt into Evergreen, staff has been initiating discussion with applicants and in several occasions applicants have voluntarily agreed to conditions for Evergreen | Red |  |  | While the City of Petaluma has opted into Evergreen, there are legal challenges with requiring private consumers to opt into Evergreen.
46 | Environmental Legacy | Climate Ready | Establish and promote a citywide sustainability program leading with exemplary environmental practices. | CMO | PWU | In Progress | IN PROGRESS: Many measures are ongoing. One of the next steps is to share our plans in the various program areas with the community, and continue to increase sustainability. Staff could present to Climate Action Commission on what the department is doing to keep them informed. Staff proposes the creation of a Sustainability Officer within the City Manager's Office in addition to the Citywide Senior Management Analyst to further support sustainability efforts and implement effective climate policy. | Green | 1 | 1 | Climate Ready 2030 initiative has begun with staff/Climate Action Commission assistance. Climate Action Coordinator/Manager position will assist with additional program implementation
47 | Environmental Legacy | Climate Ready | Adopt a Zero Waste ordinance. | CMO | CAO | In Progress | IN PROGRESS: We have adopted a polystyrene ban and a Zero Waste resolution. Other waste reduction ordinances related to SB 1383 are forthcoming. | Green | 1 | 1 | SB 1383 ordinances required to be implemented before January 1, 2022. Targeted single use products ordinance could be implemented in a similar timeline.
48 | Environmental Legacy | Climate Ready | Adopt an ordinance creating and empowering a City Climate Commission. | CMO | CAO | Complete | COMPLETE | Complete
49 | Environmental Legacy | Climate Ready | Install solar panels on city-owned properties where appropriate and work with Sonoma Clean Power on a solar program for potential revenue generation. | PWU |  | In Progress | IN PROGRESS: The Forefront project had made significant progress with the detailed designs of the Sites. FY22 proposed budget includes projects to identify additional sites that are opportunities for solar projects, including exploring floating solar at Ellis Creek. | Green | 2 | 3
50 | Environmental Legacy | Climate Ready | Engage the Regional Climate Protection Agency, City Council, staff, and community members in the development of a city-wide Climate Action Plan. | CMO |  | In Progress | IN PROGRESS: The Request for Proposals for the General Plan consultant included a request for a Climate Adaptation and Action Plan (CAAP). The contract with Raimi + Associates includes the CAAP as part of the General Plan Update process. Initial presentation with CAC scheduled for 5/13/2021. Initial kick off meetings with staff have begun and existing conditions is underway. The CAAP will be adopted simultaneously with GP adoption. Staff has also proactively met with RCPA staff to discuss climate action framework, county framework, and further CAAP adoption planned in Petaluma to sync efforts and work collaboratively with regional partners. | Green | 3 | 3 | This effort has been initiated as part of the GP update process.
51 | Environmental Legacy | Climate Ready | Complete Biomass to Biofuel project at the City’s Ellis Creek Water Recycling Facility. | PWU |  | In Progress | IN PROGRESS: The Biomass to Biofuel project is nearly complete. An, agreement with Recology for sale of the compressed natural gas that comes from the new system is pending. Staff is working out issues with Start-up and Air board permits. | Yellow | 2
52 | Environmental Legacy | Climate Ready | Develop a framework to move the City and transit vehicle fleet from fossil-fuel based to hybrid, renewable compressed natural gas, and/or electric vehicles and continue pursuing grant funding opportunities for electric vehicles. | PWU |  | In Progress | IN PROGRESS: Purchase of four fixed route buses will continue in FY22. Applied for and received multiple grant funds for electric transit buses. Funding included in FY22 City budget for transit yard electrification capital improvement design work. Have added an additional three electric vehicles in FY21 along with two hybrid Explorers and one hybrid F-150, looking to add more electric and hybrid vehicles where applicable in FY22 . | Green | 3 | 3 | Develop a fleet policy and vehicle transition roadmap
53 | Environmental Legacy | Climate Ready | Continue to expand recycled water services to support local agriculture and groundwater and surface water resources. | PWU |  | In Progress | IN PROGRESS: Staff completed additional urban water pipeline installation along Maria Drive in conjunction with road reconstruction. We are also working on next phase to connect this pipeline to the system. Contract for design for Adobe Road expansion for agricultural use to go before Council in May for award. Tertiary expansion project delayed 18 months to minimize disruption to Ellis Creek plant so it doesn't coincide with the needed major repair projects for the Ellis Creek Outfall and 40+ year old chemical systems. Water Conservation Plan being updated along with the Urban Water Management Plan. | Yellow | 3 | 3
54 | Environmental Legacy | Climate Ready | Consider requiring electric vehicle charging stations and solar energy in new or substantially-upgraded housing and commercial structures. | CDD |  | In Progress | IN PROGRESS: In addition to Triennial code updates, adoption of EV streamlining regs is scheduled for Fiscal Year 2021. Following adoption of all electric code updates staff is already considering next steps for ways to increase eve and solar requirements beyond new construction and to trigger for modifications to existing building stock. | Yellow | 1 | 2 | While there have been code updates and there are solar and EV requirements through the City's Cal Green Tier 1 requirements, there may be additional reach codes that the City should consider for additional adoption. Alternatively, the City may want to track state requirements for the next triennial update which is anticipated to more fully focus on electric.
55 | Environmental Legacy | Climate Ready | Make the City’s water distribution system more resilient, by repairing and replacing leaking water pipes, and implementing the water/sewer masterplan. | PWU |  | Ongoing | ONGOING: Modeling update efforts are underway of both the Water distribution and Sewer collection systems which will roll into Master Plan updates. | Ongoing
56 | Environmental Legacy | Climate Ready | Update Implementing Zoning Ordinance (IZO) to ensure ability to provide full environmental review for all discretionary projects. | CDD | CAO | In Progress | IN PROGRESS: Proposed modifications to Petaluma Zoning Ordinance (IZO) Chapter 24 are in process and including updates to Site Plan and Architectural Review findings in response to the McCorkle case. We anticipate bringing the updates to Planning Commission in June 2021 and CC in July 2021. | Green | 1 | 1 | In process, scheduled for PC consideration on 6/21
57 | Environmental Legacy | Climate Ready | Improve integration of transit in planning and land-use related processes and decision-making. | PWU | PLANNING, Transit | Ongoing | ONGOING: Enhanced integration of transit into development review and forward planning efforts. Including DRC, project routing, and most recent initiation of internal quarterly transit planning meetings. | Ongoing | 1 | 1
58 | Environmental Legacy | Climate Ready | Increase organic diversion from landfills and explore composting site opportunities. | CMO |  | Ongoing | ONGOING: The new franchise agreement with Recology provides free commercial food waste collection. Additional ordinances related to SB 1383 (organic material waste reduction and food recovery) will need to be adopted. Staff are working with Recology and Zero Waste Sonoma on outreach and education programs to help businesses meet requirements. | Ongoing
59 | Environmental Legacy | Climate Ready | Install consistent three stream receptacles at all City facilities. | PARK&REC |  | In Progress | IN PROGRESS: Staff are looking for grant funding to install standard receptacles in the Parks. Staff will also examine composting service needs at City facilities as they are repopulated. | Yellow | 2 | 2 | The main barrier here is staff resources to research and best standard set up, and how the receptacles will be emptied regularly. Then purchasing and installing.
60 | Environmental Legacy | Climate Ready | Adopt a citywide single-use plastic and polystyrene ban. | CMO | CAO | Not Initiated | NOT INITIATED: Single use ordinance not initiated during pandemic. | Green | 1 | 1 | Significant crossover with Goal 47
61 | Environmental Legacy | Climate Ready | Ban the use and sale of Glyphosate. | PWU | CAO | In Progress | The City has stopped using Glyphosate for City parks and properties. We will be updating the Integrated Pest Management Plan to address ongoing City use of Glyphosate. Legal has to research the City's authority to ban the sale and / or use of Glyphosate within City limits. | Yellow | 1 | 2 | Consultant under contract for IPMP update, now need to schedule kick off meeting. Public Outreach will take some time.
62 | Environmental Legacy | Climate Ready | Examine Urban Growth Boundary expiration date beyond 2025 via ballot measure and develop a white paper on options. | CDD | CAO | In Progress | IN PROGRESS: Was incorporated into scope of GP update process and scope of work with Raimi + Associates. | Yellow | 3 | 3 | Will be part of the GP update process to look at the UGB
63 | Environmental Legacy | Climate Ready | Reimagine maintenance practices for managing City parks and open spaces. | PARK&REC | CMO | In Progress | IN PROGRESS: Currently updating the City's Pest Management plan to formalize a policy of how the City maintains its parks, trails, open spaces, streetscape, creeks, landscape assessment districts, and other City’s properties in a more sustainable way that is better for the environment, the community, and the health of the public and staff. Upgrading Irrigation Controllers Systemwide maximizing water use efficiency. In progress of GHG baseline assessment and adopt parks maintenance standards that reflect Climate Action Goals and priorities. Tree Technical manual has been drafted which identifies priorities for strengthen the urban tree canopy. | Yellow | 2 | 3 | This work item seems to be speaking to a larger examination of how our parks are landscaped and maintained. There are many facets to this and each park is different. Developing the framework to evaluate each park, do public outreach, and prioritize this for the parks should be the goal here. Perhaps the Recreation, Music, and Parks committee can be a force to lead this effort with guidance from staff.
64 | Environmental Legacy | Climate Ready | Create tool / dashboard that tracks City progress on reducing greenhouse gas emissions and carbon sequestration. | CMO |  | Not Initiated | NOT INTITATED. Need to establish GHG baseline to measure against for future progress | Green | 2 | 2 | The barrier here is staff resources to research and implement this. Perhaps a consultant to augment the team.
65 | Environmental Legacy | Climate Ready | Research and pursue grey water use and rain/storm water catchment options for new development. | CDD |  | Ongoing | ONGOING: A greywater valve requirement was codified as part of the triennial code update. | Ongoing | 1 | 1 | Currently reviewing drought ready construction model ordinance including dual water system.
66 | Environmental Legacy | Climate Ready | Educate our community and provide sustainability tools for City staff, developers, employers, property owners and all residents. | CMO | EDOG | In Progress | IN PROGRESS: We created a dedicated Climate Ready Petaluma 2030 Webpage. The upcoming Climate Action Committee (CAC) agenda will include speakers and educational components by topic at each meeting. Education and incentives for all electric will be a follow up item after adoption of all electric code. | Green | 1 | 1 | The City's climate ready webpage is a great place to start providing resources. The upcoming launch of the SCP innovation center and the new financing options through SCP and SCEIP are great ways to encourage change to more sustainable options.
67 | Environmental Legacy | Climate Ready | Work with Recology to increase the diversion of waste away from the landfill. | CMO |  | Ongoing | ONGOING: This will be ongoing and is standard practice. Free food composting is available to all residential and commercial customers as of February 2021. Additional outreach will be performed by Recology and supported by staff. | Ongoing
68 | Environmental Legacy | Climate Ready | Implement sustainable building practices that go above and beyond basic code requirements. | CDD |  | In Progress | IN PROGRESS: All electric code update scheduled for CC consideration on 5/3/2021. Follow up for modifications to existing building stock, incentives, and education to bring increased sustainability and to work toward climate neutrality in building sector. | Yellow | 1 | 2 | While the initial all electric code is adopted, there are additional code updates that the City could consider to work toward decarbonization of existing buildings.
69 | Environmental Legacy | Climate Ready | Investigate ways to allow homeowners to use the public right of way for EV Charging. | PWU | CAO | Not Initiated | NOT INTIATED: While a pilot program was initially identified, this has not moved forward due to competing priorities and shifting attention to address COVID. | Yellow | 1 | 2 | Pilot programs to model after are available. Needs staff (public works, planning, legal) time to create program.
70 | Environmental Legacy | Climate Ready | Continue focus on water conservation and urban recycled water expansion. | PWU |  | Ongoing | ONGOING: Completed additional urban water pipeline installation along Maria Drive in conjunction with the road reconstruction. We are working on the next phase to connect this pipeline to the system. A tertiary expansion project is delayed 18 months to minimize disruption to Ellis Creek plant so it doesn't coincide with the needed repair projects for the Ellis Creek. | Ongoing
71 | Environmental Legacy | Climate Ready | Revisit flood plain management practices to address climate change and sea level rise. | PWU |  | In Progress | IN PROGRESS: Staff scoped out a project to update the City's flood modeling. The needed funds have been submitted to Zone 2A for review. Floodplain management will also be discussed during the General Plan update. | Green | 2 | 3 | Initiated but will take time to secure funding and run the models.
72 | A Safe Community | Safety & Emergency Prep | Assess current staffing levels and adjust public safety staffing to ensure rapid response times and the safety of our first responders. | CMO | HR | Ongoing | ONGOING: Additional public safety staffing is proposed to be added with Measure U funds for the FY 21/22 budget. Analysis of Police and Fire staffing levels is ongoing. Staff are also proposing to hire a consultant to analyze public safety facility needs, response times and locations to inform future Measure U investments in new / renovated facilities. | Ongoing
73 | A Safe Community | Safety & Emergency Prep | Restore Public Safety specialty units when possible. | PD | HR | In Progress | IN PROGRESS | Yellow | 2 | 1
73.1 | A Safe Community | Safety & Emergency Prep | b. Prioritize youth safety through education and community resource officers. | PD |  | In Progress | IN PROGRESS: Currently conducting social media educational campaigns on traffic/bicycle safety, and distracted driving. Funding restored for two additional CSO's to help achieve education and public awareness objectives. | Green | 1 | 1 | The Ad Hoc committee established to review police policies may offer a recommendation on this item.
73.2 | A Safe Community | Safety & Emergency Prep | c. Restore the Homeless Outreach Services Team. | PD | CDD | In Progress | UPDATED: We will evaluate when core staffing and specialty assignments stabilize. Measure U funding proposal for FY22 would restore these services. | Green | 2 | 2 | The City is increasing the funding for COTS and DST to increase the level of street outreach services
73.3 | A Safe Community | Safety & Emergency Prep | a. Re-establish bicycle teams downtown. | PD |  | Not Initiated | NOT INITIATED: We will evaluate when core staffing and specialty assignments stabilize. | Yellow | 2 | 3
74 | A Safe Community | Safety & Emergency Prep | Evaluate all city facilities, including our police and fire stations, and corporation yard facilities, and develop maintenance and replacement recommendations. | PWU |  | In Progress | IN PROGRESS: A facilities condition assessment was completed. Work needs to be prioritized as there is very limited funding to apply towards the $32M backlog in deferred maintenance. | Yellow | 2 | 3 | This is marked Yellow, because of staff resources needed to move the Public Safety Facility Assessment and the Corp Yard Master Planning efforts forward. CIP has several vacancies and also needs to grow to support many of these initiatives, even if a consultant is doing the bulk of the work there are PSA's, communications, and information that needs to be gathered and reviewed. There is still a level of effort from staff required to make these studies a success.
75 | A Safe Community | Safety & Emergency Prep | Create an Emergency Operations Center (EOC) that is appropriately equipped and staffed to better respond to all emergencies and disasters. | FIRE | EDOG | In Progress | IN PROGRESS: A new EOC will be included in new fire station. | Yellow | 3 | 3
76 | A Safe Community | Safety & Emergency Prep | Adopt a Care and Shelter operations manual to improve City logistics planning during emergencies. | PARK&REC | HR | In Progress | IN PROGRESS: Staff has initiated an effort to expand staff depth to respond to Care and Shelter opportunities and provide advance training to better anticipate and respond in case of emergency. We have also collected increased supplies to utilize in future emergency situations. Staff is working to address outstanding issues and to increase partnership and collaboration efforts with Sonoma County. | Green | 1 | 2
77 | A Safe Community | Safety & Emergency Prep | Assist the community, with special focus on those with special needs, through outreach and training, to ensure resiliency and emergency preparedness. Plan for natural disasters and all emergencies by providing safe places for the community to shelter (e.g., fairgrounds, faith community/churches, city facilities). | FIRE | REC | Ongoing | ONGOING: The Fire Department has experienced an increase in demand for services. As a result, there is little capacity to conduct robust community outreach. The City has hired a consultant to help the City update its procedures and practices for emergency management as well as to make recommendations about additional needed efforts. The City Activated the EOC for COVID and 2020 wildfires. We also opened and staffed shelters during the Glass Fire. We created a more consistent template for After Action Reports (AAR) of future emergency events to help streamline lessons learned and future improvements needed. | Ongoing
78 | A Safe Community | Safety & Emergency Prep | Improve public safety through proactive crime and fire prevention activities. | PD | FIRE | Ongoing | ONGOING: The 2021 7th grade CPR training was postponed due to COVID. Staff completed priority/mandated business inspections. Fire safety education for kids was completed virtually due to COVID. The City is working to establish a CAHOOTS program to provide mental health crisis services. The City also funded a Downtown Streets Team to help Petaluma's unsheltered live a safer and more dignified life. Cost-3 Time- 2 | Ongoing | 3 | 2
79 | A Safe Community | Safety & Emergency Prep | Improve traffic safety through proactive education, engineering, and enforcement strategies. | PD | PWU | Ongoing | ONGOING: PW&U - Engineering measures are continuing to be rolled out with every paving, road reconstruction, sidewalk repairs, curb ramp installations, crosswalk upgrades, bicycle infrastructure, and traffic signal upgrade projects. Current projects include downtown sidewalk upgrades and mid-block crosswalk upgrades. | Ongoing
80 | A Safe Community | Safety & Emergency Prep | Assess and identify traffic needs and develop organizational structure to support needs, including the possibility of restoring a full-time City Traffic Engineer position. | PWU |  | Complete | COMPLETE | Complete
81 | A Safe Community | Safety & Emergency Prep | Promote emergency preparedness and resiliency strategies to our residents and businesses. | FIRE | EDOG | Complete | COMPLETE: The Fire Department has experienced an increase in demand for services. As a result, there is little capacity to conduct robust community outreach. The City has hired a consultant to help the City update its procedures and practices for emergency management as well as to make recommendations about additional needed efforts. The City Activated the EOC for COVID and 2020 wildfires. We also opened and staffed shelters during the Glass Fire. We created a consistent template for After Action Reports (AAR) of future emergency events to help streamline lessons learned and future improvements needed. Staff created an emergency preparation section on website and regularly sends out information about how to sign up for emergency alerts, through social media and community updates. Staff also engaged businesses and residents in emergency preparation and response activities related to COVID, including accessing local, state, and federal relief programs. | Complete
82 | A Safe Community | Safety & Emergency Prep | Promote neighborhood policing and fire safety with beat assignments, community engagement, and multilingual outreach. | PD | EDOG | Ongoing | ONGOING: The Fire Department has experienced an increase in demand for services. As a result, there is little capacity to conduct robust community outreach. The City has hired a consultant to help the City update its procedures and practices for emergency management as well as to make recommendations about additional needed efforts. The City Activated the EOC for COVID and 2020 wildfires. We also opened and staffed shelters during the Glass Fire. We created a more consistent template for After Action Reports (AAR) of future emergency events to help streamline lessons learned and future improvements needed. Cost- 2 Time -1 | Ongoing | 2 | 1
83 | A Safe Community | Safety & Emergency Prep | Consider a firework and use sales ban, or other modification to current ordinance; assist the non-profits who rely on these sales to identify alternatives for fund raising. | FIRE | CMO | Complete | COMPLETE: City Council passed ordinance that banned all fireworks. | Complete
84 | A Safe Community | Safety & Emergency Prep | Enhance pavement management program to improve the safety and serviceability of our roads and to protect drivers, cyclists and pedestrians. | PWU |  | Ongoing | ONGOING: Presented proposal to implement an additional $25M investment program in street infrastructure over the next 5 years through bond funding. The passing of Measure U allowed for this possibility. Working on planning and resources to execute this program. Will integrate Active transportation improvements with this work. | Ongoing
85 | A Safe Community | Safety & Emergency Prep | Implement City Vision Zero plan with a focus on pedestrian and cyclist safety with improvements to uncontrolled crosswalks, curb ramps, sidewalk, and bicycle infrastructure. | PWU | PD | In Progress | IN PROGRESS: This is a multi-faceted and in-depth project that will take several years to implement. Progress to date includes attending Sonoma County's kick-off working toward Vision Zero in December 2019. Many public works projects are in design, planning, and design that incorporate facets of pedestrian and bicycle safety. Also, an update to the City's Bicycle and Pedestrian plan has been initiated and expected to be completed by the end of 2021. | Red | 3 | 3 | Implementing a legit City focused Vision Zero program is a large undertaking. One that has barriers in staffing resources and funding resources. The City is taking action on many of the aspects of a Vision Zero program and joining the County-wide Vision Zero effort to move the community towards this goal.
86 | A Safe Community | Diverse & Affordable Housing | Develop programs that provide affordable rental and ownership housing for the missing middle including but not limited to public safety, municipal employees, teachers, and non-profit employees. Support and partner with organizations that help the housing insecure and unsheltered population find health care & supportive services. | CDD | CMO | Ongoing | ONGOING - The City Council continues to support and approve housing projects that provide needed units affordable to low-income families to achieve homeownership. The City works in partnership with the Housing Land Trust of Sonoma County. The City received a grant from the County from the Homeless Emergency Aid Program (HEAP) and improvements will be completed by June of 2020 at the Mary Isaac Center and Kids First Family Shelter. Staff Continues to work with the Downtown Streets Team an organization that provide outreach and community service initiatives for unsheltered members of the community. The River City Senior Housing development is under construction and will provide 54 affordable housing units for seniors and veterans. The City funded the site acquisition for 414 Petaluma Blvd North, a MidPen development that will provide 42 units of affordable housing. The City team is working in partnership with Danco and Affordable Housing Developer on a HCD program application to the Affordable Housing Sustainable Communities Program. If successful this will provide much needed funding for the proposed Meridian Crossings development that will provide 132 units of affordable housing. The funding will also provide funding for infrastructure, and off-site improvements, in addition to funding for the 2nd SMART Station. Staff is considering development opportunities for the COTS site expansion adjacent the Mary Isaac Center located at 900 Hopper Avenue at the City Corp Yard. | Ongoing | 3 | 3 | This section should be restructured to reflect specific, tangible goals - this should include a section for project and programs Implementation of IH program in partnership with HLT- Housing Strategy for the Missing Middle Deed Restricted AH Development Projects PEP, MidPen, and Danco - focused on permanent supportive housing for households at 30%, 50% and 80% AMI. Preservation - Question of existing rental properties - convert to Deed Restricted COTS- HEAP Project will be completed by June 30, 2021 Programs - These can be listed as ongoing - with Green, 1 for cost and 1 for time Rental Assistance / Homeless Prevention Fair Housing Meals/Public Services
87 | A Safe Community | Diverse & Affordable Housing | Work with service providers and countywide agencies to coordinate response and solutions to the City’s unsheltered population including transitioning homeless Petalumans into shelter and housing. | CMO | CDD | Ongoing | ONGOING - Staff to develop a City Homeless Services Plan in partnership with community service providers and City staff from multiple departments. We will continue to work in partnership with Committee on the Shelter less (COTS) and Downtown Streets Team (DST) on program implementation to serve the unsheltered members of the community. | Ongoing | 1 | 2 | Staff has retained a consultant to support the development of a City Homeless Services Plan that will identify short, mid and long term program goals and funding sources. The Plan will be community based and aligned with regional systems and solutions. This will include strategies specific to the State HDC Project Home key COTS Campus Expansion - not sure we want to mention this - Alternative short term housing solutions - safe parking, pallet homes, sanctioned encampments - not sure if we want to list specific approaches
88 | A Safe Community | Diverse & Affordable Housing | Facilitate construction of Accessory Dwelling Units. | CDD | BLDG | In Progress | IN PROGRESS: We are pursuing permit ready ADU plans with SB 2 grant funds and in partnership with the Sonoma Napa County ADU Accelerator Program. | Green | 1 | 2 | Staff has secured grand funding and explored regional partnerships. Next step to release an RFP for Petaluma specific plans to offer at reduced or no cost to facilitate production of ADUs
89 | A Safe Community | Diverse & Affordable Housing | Consider establishing a Housing Commission. | CMO | CAO | Not Initiated | NOT INITIATED | Red |  |  | No staff level discussions at this time
90 | A Safe Community | Diverse & Affordable Housing | Create a 5-year strategic housing plan to provide inclusive housing solutions that are affordable, ADA compliant, age friendly, and ensure the continuity of City services to a growing residential population. | CDD |  | In Progress | IN PROGRESS - In May of 2021, staff will be conducting a housing workshop to be focused on meeting the City RHNA goals over the next two years. The workshop will include a snapshot of affordable and market rate housing as it relates to the City RHNA allocation, housing programs and funding sources with examples from communities with similar demographics, housing development 101 to provide an overview of the housing development business model and examples of housing policy from other jurisdictions. Staff is in the initial stages of working on the Housing Element for the 6th Cycle. This will provide a housing workplan for the next 7 years. | Yellow | 2 | 3 | While staff will continue to proactively seek housing production, especially at the lower income levels, the creation of a five year housing plan will be an effective way to implement the 6th cycle housing element which is under way and anticipated for adoption in 2022. The plan will address strategies related to production, preservation and protections.
91 | A Safe Community | Healthy Community | Collaborate with the Health Care District and other service providers to identify and promote wellness programs and policies. | PARK&REC |  | Ongoing | ONGOING | Ongoing
92 | A Safe Community | Healthy Community | Work with the County to adopt a Tobacco Retail Licensing ordinance and re-evaluate the City’s smoking policy to include e-cigarettes/vaping. | PD | CAO | Not Initiated | Not Initiated: Put on hold due to COVID response; Cost 1- Time 2/3 | Yellow | 1 | 2
93 | A Safe Community | Healthy Community | Create and promote multi-cultural and multi-generational recreation and wellness programs that support community connection, physical well-being, and opportunities for play. Focus on public health in planning processes—including air quality, walkability, childcare incorporated into larger developments, including revisiting zoning around sensitive receptors (e.g. schools, health care facilities. | PARK&REC |  | Ongoing | ONGOING: Multi-generational/cultural wellness programming is at the ethos of a Parks and Recreation department's mission. | Ongoing
94 | A Safe Community | Healthy Community | Develop fee structure for Alcohol-Related Nuisance Ordinance for sustained management and enforcement of license alcohol establishments. | PD | CAO | Not Initiated | NOT INITIATED | Yellow | 1 | 2
95 | A Safe Community | Healthy Community | Adopt a “visit ability” ordinance to provide accessibility in new single-family home construction. | CDD | CAO | In Progress | IN PROGRESS: This is in progress with initial research and, provisions and options outlined. Staff anticipates this moving to CC in summer/fall 2021. | Green | 1 | 1 | Staff has drafted a visitabiity ordinance that is currently being internally reviewed and refined for bringing forward for adoption later in 2021
96 | A Safe Community | Healthy Community | Improve access to healthy, sustainable food throughout the community, including consideration of community garden sites and farmers market locations (e.g., fairgrounds), and events; explore opportunities to incorporate elements of County Food Action Plan. | CMO | EDOG | Ongoing | ONGOING: Community garden amenities have been incorporated into private developments such as Burbank and Danco. We are also looking for flexible space for things like additional farmers market space or CSA drop off as part of Danco project. | Ongoing
97 | A Safe Community | Healthy Community | Improve integration of transit to all demographics by partnering with social service agencies and non-profit organizations. | PWU |  | IN Progress | ONGOING: continued work with nearby social service agencies in order to provide them with discounted passes for employees. Stakeholder on the 2020/21 Connected Communities Transportation Study helping to identify public transportation needs for Sonoma County residents. | Ongoing | 2 | 2 | Additional staffing will allow for additional integration with these services on a regular basis and allow for better leveraging of cross-agency resources.
98 | A Safe Community | Healthy Community | Create more diverse recreational, social, and cultural opportunities for youth. | PARK&REC |  | Ongoing | ONGOING: The Climate Action Commission has added youth members. | Ongoing
99 | A Safe Community | Healthy Community | Secure designation as an Age Friendly City. | REC |  | Complete | COMPLETE | Complete
100 | A Safe Community | Healthy Community | Increase efforts to help seniors remain engaged, active, and independent. | PARK&REC |  | Ongoing | ONGOING: The Senior Center continues to offer a variety of programing. Programing includes but is not limited to partnership with the Senior Advocacy Services – who advise seniors on Medicare. The Redwood Empire Foodbank bi-monthly food distribution, weekly dementia support groups, monthly Earl Balm ear and sight support group. Legal consultants meet four times monthly to provide free consolations. Disaster Preparedness workshops were held this past year by City staff. Presentations by Sonoma County Library regarding available resources and programming. Partnership with the SRJC to offer two active lifestyle classes, five times a week focusing on chair exercise, brain healthy stretching. A number of discussion groups (writers groups, quilters, knitting group, Parkinson group) each meet monthly. Special events incorporating intergenerational activities and themes are offered in tandem with holidays, membership awards, and birthdays. | Ongoing
101 | Economy that Prospers | Biz Attraction / Retention | Create and promote business-friendly city operations such as zoning, permitting, and licensing. | CDD | EDOG | Ongoing | ONGOING: This is an ongoing effort to continually improve work flow, streamlined review, and customer service. We are actively working on permit center improvements funded by SB 2 grant funds to improve public engagement, customer service, and facilitate one stop shop options, in addition to holding weekly DRC meetings. A new temporary program, Free Range, was launched in response to COVID and enabled 58 businesses to operate and/or increase capacity outside while indoor operations were restricted. | Ongoing
102 | Economy that Prospers | Biz Attraction / Retention | Update Implementing Zoning Ordinance (IZO) and look for ways to consolidate, simplify, and streamline for more flexibility in reviewing. | CDD | EDOG | Ongoing | ONGOING: Gas Station prohibition, extension of SPAR expiration provision, Changes to IZO Chapter 6 to match FEMA requirements. Modifications to Chapter 24 in process. Objective Design standards in progress with PC study session scheduled for April 27th. Parking study session being planned for summer/fall. Updates to inclusionary housing and housing land use provisions possible direction out of housing workshop on May 17, 2021 | Ongoing
103 | Economy that Prospers | Biz Attraction / Retention | Prioritize and incentivize sustainable infill development. | CDD | EDOG | Ongoing | ONGOING: Continuing discussion with applicants early in process to encourage sustainable design. VMT implementation measures in process to focus location and type of development to minimize impacts. All electric code update in process. GP Update scope focused on climate initiative and sustainable development | Ongoing
104 | Economy that Prospers | Biz Attraction / Retention | Create programs to support start-up businesses by expediting permits and providing in-person permit consultations. | EDOG | CDD | Ongoing | ONGOING: This concierge support is provided and ongoing as needed. Permit center updates are in process, including concierge station. Increasing CDD role to increase coordination with Building division. | Ongoing | 1 | 1 | Develop a program to expedite identified small and start up businesses when possible.
105 | Economy that Prospers | Biz Attraction / Retention | Establish City minimum wage ordinance. | EDOG | CAO | Complete | COMPLETE | Complete
106 | Economy that Prospers | Biz Attraction / Retention | Enhance information on licensing and permitting guidelines to be accessible and understandable to all. | EDOG | CDD | Ongoing | ONGOING | Ongoing
107 | Economy that Prospers | Biz Attraction / Retention | Work with regional workforce agencies to attract talent for local businesses. | EDOG |  | Ongoing | ONGOING: During Covid, this was not a focus. Moving forward, during recovery, we will work with businesses needing help finding talent. | Ongoing
108 | Economy that Prospers | Biz Attraction / Retention | Update the City’s Economic Development Strategy. | EDOG |  | Not Initiated | NOT INITIATED: Instead of focusing on a new strategy, we recommend moving the Fairgrounds and General Plan projects forward with a lens towards Economic Development. | Yellow | 2 | 3
109 | Economy that Prospers | Biz Attraction / Retention | Complete Airport re-zoning as a catalyst to new business opportunities. | PWU | CDD | In Progress | IN PROGRESS: Reinitiated review with Airport Commission to review previous rezoning direction. Commission no longer supports previously vetted rezoning changes. | Red |  |  | Planning effort in coordination with airport. Limited resources from PW&U to pursue currently
110 | Economy that Prospers | Biz Attraction / Retention | Retain businesses that support local agriculture (e.g. processing, product development). | EDOG | CDD | Ongoing | ONGOING: Key initiatives complete. This is an ongoing goal for continued improvements. | Ongoing
111 | Economy that Prospers | Biz Attraction / Retention | Incentivize, support, and incubate small, start-up businesses. | EDOG |  | Ongoing | ONGOING: COVID support efforts that included Free Range and Shop Petaluma will be ongoing through October 2021. (Planning) looking for ways to incentivize creativity in development for alternative commercial concepts in response to changes in economy, encourage small scale local businesses, and provide flexibility for different types of retail/commercial. | Ongoing
112 | Economy that Prospers | Destination Promotion | Support tourist-oriented events with police and public works staffing. | PWU | PD | Ongoing | ONGOING: The City supports tourist oriented activities as needed. There were no events held during the Covid shelter in place requirements. | Ongoing
113 | Economy that Prospers | Destination Promotion | Facilitate the development of an additional hotels where appropriate. | CDD | EDOG | In Progress | ONGOING: Hotels were not initiated during COVID shelter in place requirements. We will continue to work with interested hotels as projects present themselves. | Red |  |  | The Marriott at Riverfront is under construction and close to occupancy. The Home 2Suites hotel is approved and ready for permit issuance to begin construction. The City recently removed the FEIA requirement for hotels. Staff will continue to work with interested hotels as projects present themselves.
114 | Economy that Prospers | Destination Promotion | Identify potential parking and transportation alternatives for downtown. | PWU | CDD | In Progress | IN PROGRESS: Parking study session planning in process and targeted for summer/fall 2021 | Green | 1 | 1 | In depth parking study session being developed by staff for fall 2021 to identify alternatives and priorities for modifying parking regs.
115 | Economy that Prospers | Destination Promotion | Support and leverage promotional efforts of the Petaluma Tourism Improvement District. | EDOG | CMO | Ongoing | ONGOING: We are continuously partnered with Petaluma's PTID to support events and outreach. | Ongoing
116 | Economy that Prospers | Destination Promotion | Maximize use of current parks and recreation infrastructure, and other City-owned facilities and properties for the hosting of recreational, sports, cultural and entertainment events that attract visitors to Petaluma. | PARK&REC |  | Ongoing | ONGOING: Staff has spent significant time working with park users during the Covid Shelter in Place requirements. As rules changed, staff altered signage, messaging and practices. While large group gatherings and special events were prohibited over the past year, outdoor athletic fields and shared play areas became a critically important asset to provide physical and mental support for local residents eager for opportunities to play. In person pre-school was offered during the academic year as well as a variety of summer day camps and specialty camps were offered in the Summer of 2020. | Ongoing
117 | Economy that Prospers | Healthy River | Identify short and long-term funding solutions for dredging of the Turning Basin and federal channel by coordinating with other dredging efforts in the Bay Area; dredge the City Marina coordinate with Bay Area wide dredging efforts. | PWU | CMO | In Progress | IN PROGRESS: Dredging of the Federal Channel and turning Basin is complete, dredging of the Marina to occur if American Rescue Plan funding backfills lost City revenues. Continue to seek the funding for the Marina dredging ($2.4M partial dredge and $3.6M for full dredge) . | Yellow | 3 | 2 | Work with other agencies with shallow-draft channels in the North Bay to coordinate reoccurring maintenance dredging program.
118 | Economy that Prospers | Healthy River | Support Federal dredging efforts of the river channel by maintaining a viable dredge disposal site option at Shollenberger and explore sustainable long-term beneficial reuse sites for disposal. | PWU | CMO | In Progress | IN PROGRESS: Dredging of the Federal Channel and Turning Basin is complete, and staff ensured Shollenberger was ready to receive the dredge spoils. Continuing long term planning efforts for future dredging cycles. | Yellow | 3 | 3 | Working on the Long term plan for dredging with beneficial re-use of dredge material, Sea level rise, and coordination with USACE, non-profits, and other regional stakeholders in maintaining the shallow draft channels of the North Bay
119 | Economy that Prospers | Healthy River | Establish bicycle and walking paths and other river access amenities along the Petaluma River as identified in the River Access and Enhancement Plan. | PWU | CDD | Ongoing | ONGOING: Significant upgrade to surface and pathway access out to bid for Lynch Creek Trail section that is along the Petaluma River from Payran Bridge to Lynch Creek. | Ongoing | 3 | 3 | Progress is continuing on Lynch Creek Trail. This is a long term project in building out projects in accordance with the Petaluma River Access and Enhancement Plan. The Rivertrail from Riverfront to the Marina is a significant portion of this trail, that we have an initial design on, but continue to look for funds to execute. The pocket park at C St. is also an element of this as is the float house, docks and Cavanaugh landing.
120 | Economy that Prospers | Healthy River | Robust focus on the riverfront and river-oriented development, including redevelopment potential of the Golden Eagle Shopping Center and Water Street. | CDD | EDOG | In Progress | IN PROGRESS: Water street was partially closed to support outdoor dining. There is an opportunity to explore closing the street permanently to cars and creating a pedestrian only gathering space. (Planning) Construction of Water Street North in process. Concept discussion with interested developer for Golden Eagle shopping center which was recently put on the market. | Green | 2 | 3 | The General Plan update will have a robust focus on the Petaluma river and appropriate river oriented development. As part of ongoing processes, staff will continue to provide development input in line with adopted policy documents and meet with prospective developers to encourage appropriate redevelopment of key sites along the river.
121 | Spaces & Places | Safe & Vibrant Neighborhoods | Identify and prioritize projects to upgrade and improve the downtown, alleyways, and public spaces. | PWU | EDOG | Ongoing | ONGOING: The City contracted with the Downtown Streets Team to provide services to Petaluma's unsheltered population. The teams cleaned up downtown as part of their work. Keller Street Garage mural was completed with an expanded scope approved. Free Range efforts were implemented to utilize public right-of-way for downtown businesses in response to shelter in place orders. Staff team is meeting monthly with the business improvement district group to identify priority projects. Lighting has been identified as a priority project that is early design and budgeting. | Ongoing | 2 | 2
122 | Spaces & Places | Safe & Vibrant Neighborhoods | Review downtown zoning to identify ways to balance entertainment venues with retail and services and to incorporate Smart Code principals where feasible. | PWU | EDOG | Not Initiated | NOT INITIATED | Red |  |  | This does not appear to be an ongoing issue and therefore unsure if still a top priority for staff resources.
123 | Spaces & Places | Safe & Vibrant Neighborhoods | Fund and support a Downtown Streets Team to assist in beautification of Downtown and outreach to Petaluma’s unsheltered population. | CMO |  | Complete | COMPLETE | Complete
124 | Spaces & Places | Safe & Vibrant Neighborhoods | Assess and review accessibility to public restrooms in the downtown area and develop a plan to address identified needs. | PWU | CDD | Not Initiated | NOT INITIATED: Covid delayed this action, will engage in summer 2021. | Red | 2 | 2 | Staff resources are the barrier to moving this forward.
125 | Spaces & Places | Safe & Vibrant Neighborhoods | Develop and implement a Downtown maintenance and beautification plan in partnership with the Petaluma Downtown Association. | PWU | EDOG | In Progress | IN PROGRESS: A partnership between Petaluma Business Improvement District (PBID) and the Petaluma Public Art Committee expanded the scope of Keller Street Garage mural. Looking to set up quarterly meetings with PBID, and various departments to regularly discuss and prioritize Downtown maintenance and beautification opportunities. | Red | 1 | 2 | Additional staff resources needed for this initiative.
126 | Spaces & Places | Safe & Vibrant Neighborhoods | Begin planning for update of the City’s General Plan 2025. | CDD |  | Complete | COMPLETED: We have officially kicked off the General Plan Update, including the Housing Element and Climate Adaptation and Action Plan. General Plan Advisory Committee (Pac) formed, consultant team selected. | Complete
127 | Spaces & Places | Fairgrounds Planning | Work with Fair District board and agricultural stakeholders to find creative ways to promote and support Petaluma’s agricultural heritage. | CMO | EDOG | In Progress | IN PROGRESS: This project was put on hold during Covid Shelter in Place. Currently staff is focused on completing due diligence for the property including a hazardous materials study, Facility assessment, tenant report etc. The General Plan visioning effort will include a specific look at how the Fairgrounds could be re envisioned. | Green | 3 | 3 | This effort should run concurrently with the General Plan update effort.
128 | Spaces & Places | Fairgrounds Planning | Engage the community to envision and adopt a master plan for the fairgrounds property. | CMO | EDOG | In Progress | IN PROGRESS: Initial outreach will be completed as part of General Plan Visioning. General plan consultant will be meeting with Fair board to begin visioning this Spring. Initial community visioning will take place later this summer once initial property due diligence is more complete. | Green | 3 | 3 | This effort should run concurrently with the General Plan update effort.
129 | Spaces & Places | Fairgrounds Planning | Identify partners and funding for developing the fairground property. | CMO | EDOG | In Progress | IN PROGRESS: Due diligence review underway to understand current conditions of the property including hazardous materials, leases, facility conditions, maintenance needs among other issues. | Green | 1 | 1
130 | Spaces & Places | Inspirational Spaces/Public Art | Celebrate existing public art by completing an inventory and develop promotional materials. | CDD | EDOG | In Progress | IN PROGRESS: All existing pieces in city's public art collection have been photographed and artwork data compiled. Next step to load onto public art webpage. | Green | 1 | 1 | Partially completed. A new public art specialist is coming on board and this will be a top priority to complete this task.
131 | Spaces & Places | Inspirational Spaces/Public Art | Engage the City’s Art Commission and the community to review the City’s Public Art Masterplan to ensure goals and objectives are current and reflective of the community and public art installations are spread throughout the City. | CDD | CMO | Not Initiated | NOT INITIATED: Focused on other art related priorities and development of grant programs to further public art opportunities in the community. | Yellow | 1 | 2 | The cost and time could significantly change based on community outreach and engagement as part of this effort. The PAMP was adopted in 2013 and is overdue for a strategic review and update.
132 | Spaces & Places | Inspirational Spaces/Public Art | Explore including a Council liaison on the City’s Art Committee. | CDD | CMO | Not Initiated | NOT INITIATED | Red |  |  | As previously discussed, the unique expertise and experience of PPAC members is focused on art. Consider whether Councilmember will be an asset to the PPAC.
133 | Spaces & Places | Inspirational Spaces/Public Art | Consider climate change themes in public art including living walls, river focus, etc. | CDD |  | Ongoing | ONGOING: Discussed with potential applicants but no new public art pieces commissioned | Ongoing
134 | Spaces & Places | Inspirational Spaces/Public Art | Continue to look for opportunities for smaller, community oriented public art projects. | CDD |  | In Progress | IN PROGRESS: Currently developing grant program with regular opportunities to award funds to facilitate additional small artworks and fund art opportunities with partnership organizations. | Green | 1 | 1 | Staff and the PPAC is developing grant programs to provide opportunities for funding of small local art projects and/or community partnerships.
135 | Spaces & Places | Inspirational Spaces/Public Art | Encourage temporary art installations and other types of public arts celebrations and partnerships with other arts and community organizations. | CDD |  | In Progress | IN PROGRESS: Currently developing grant program with regular opportunities to award funds to provide seed monthly for local art organizations and events. | Yellow | 1 | 1 | Staff and PPSC is developing grant programs to provide opportunities for funding temporary installations, festivals, etc. thorough community partnerships. Temporary art installations and installations involving other organizations raise first amendment forum issues in terms of art selection. Also moral rights of the artists may be implicated. This will need legal review and discussion before it is implemented.
136 | Spaces & Places | Inspirational Spaces/Public Art | Ensure ongoing and proactive maintenance of Petaluma’s public art. | CDD |  | In Progress | IN PROGRESS: New contract with Preservation Arts to provide regular maintenance, specific rehab options, and as needed damage response. Recently completed substantial rehab of Cherry Soda. | Green | 2 | 3 | Cost and time vary on rehab needs of specific artwork.
137 | Spaces & Places | Inspirational Spaces/Public Art | Explore opportunities for more murals and art installations citywide. | CDD |  | Ongoing | ONGOING: First phase of Keller Street Garage mural completed. Design and funds awarded for phase two expansion to be completed summer/fall 2021. | Ongoing
138 | Spaces & Places | Accessible, Sustainable Public Spaces | Capital maintenance and upgrades to City facilities to provide places and spaces for community dialogue, public meetings, and customer service. | PWU |  | In Progress | IN PROGRESS: Cavanaugh Center roof repairs completed. Additional funding for Community Center upgrades proposed in FY22 budget. Current budget allows for building envelope (i.e.. roof, windows,) maintenance work and some safety related work with interior doors, additional budget will allow for interior renovations of carpet, ceiling tiles, lighting, etc. | Yellow | 3 | 3 | This is a large program of improvements to community spaces, priority has been placed on Community Center and Cavanaugh Center. There is a long term effort, funding and resources need to continue this program of improving our places of community gathering, dialogue, and City staff customer service.
139 | Spaces & Places | Accessible, Sustainable Public Spaces | Develop a rehabilitation/reconfiguration plan for City Hall which includes a lobby area, expansion into County-wing, and wayfinding signage. | PWU | CMO | In Progress | IN PROGRESS: Actively reviewing and discussing plans for new permit center with funding from SB 2 grant funds. | Green | 2 | 2 | Ongoing refinement of plans. SB 2 grant funds must be spent by February 2022.
140 | Spaces & Places | Accessible, Sustainable Public Spaces | Expand the use of Transit Oriented Development (TOD) principles in new development, including greater massing allowances to facilitate thoughtful infill development proximate to TODs. | CDD | PWU | Ongoing | ONGOING: While there are not specific regulations dealing with Transit Oriented Design per se, staff urges application of TOD principles early and often for projects being developed in areas in proximity to the SMART stations. Additionally, staff encourages increased massing through the use of density bonus, Smart Code, etc. in an effort to maximize infill development sites close to transit and increase density. Development design elements such as pedestrian friend designs, designs that prioritize reduced building setbacks from streetscape, increased usage of mixed-use zoning in high service transit areas, etc. | Ongoing
141 | Spaces & Places | Connections to History & Each other | Consider a 1% development fee for historic preservation to increase funding opportunities to facilitate preservation efforts. | CDD | CAO | Not Initiated | NOT INITIATED | Red |  |  | Additional fees on new development may not be desired at this time given other priorities. Any additional fee must be studied for nexus and appropriate fee structure.
142 | Spaces & Places | Connections to History & Each other | Explore potential historic district designation of the Riverfront Warehouse District as referenced in the Central Petaluma Specific Plan. | CDD |  | Not Initiated | NOT INITIATED | Yellow | 2 | 3 | Requires comprehensive survey of area for local designation.
143 | Spaces & Places | Connections to History & Each other | Consider designating historic railroad tracks in central Petaluma as a local landmark to ensure protection and preservation. | CDD |  | In Progress | IN PROGRESS: Request from HCPC forwarded to the City Council. No additional discussion initiated. | Red |  |  | Unsure of compatibility with a host of other things prioritized along the rail corridor through downtown.
144 | Spaces & Places | Connections to History & Each other | Finalize Certified Local Government designation process and recommend next steps. | CDD |  | In Progress | IN PROGRESS: Final application materials compiled for Mayor signature. Materials will be submitted to State Historic Preservation Office (SHPO) by end of June 2021. | Green | 1 | 1 | Almost complete
145 | Spaces & Places | Connections to History & Each other | Develop a plan to rehabilitate the Trestle, which will include funding options. | PWU | CDD | In Progress | IN PROGRESS: Engineering consultant completed review of previous plans and alternatives developed and being internally discussed prior to bringing forward for consideration. | Yellow | 3 | 3 | Need funding $6M
146 | Spaces & Places | Connections to History & Each other | Consider conducting a citywide inventory of historic resources. | CDD |  | Not Initiated | NOT INITIATED: However, Certified Local Government application is in process. Historic Preservation discussion initiated with consultant team as part of General Plan Update process. | Red | 2 | 2 | Great priority but necessitates resources
147 | Spaces & Places | Connections to History & Each other | Maximize opportunities that encourage preservation and adaptive re-use of historic structures (e.g. Mills Act, tax credits, State Historic Building Code, façade improvement program). | CDD |  | Not Initiated | NOT INITATED: due to other demands and priorities associated with COVID and EOC | Yellow | 2 | 2 | Great tools to explore. Necessitates resources to complete.
148 | Spaces & Places | Connections to History & Each other | Explore funding mechanism to maintain historic features in public spaces. | PWU | CDD | Not Initiated | NOT INTIATED | Red |  |  | Requires more specificity. Include cost option and time option as unknown
149 | Spaces & Places | Improve/Reimagining Parks | Develop a plan to prioritize playground upgrades/replacement and accessibility improvements. | REC |  | In Progress | IN PROGRESS: Bond and Grant Park scheduled to be replaced in Fall 2021. Anna's Meadows is scheduled in Spring of 2022. Identifying those playgrounds and play equipment in tier 2 of the replacement queue is a priority during the Winter 2021. | Green | 2 | 2
150 | Spaces & Places | Improve/Reimagining Parks | Repurpose existing amenities to promote recreational opportunities, including initial phases of tennis court rehabilitation citywide and pickleball courts. | PARK&REC |  | In Progress | IN PROGRESS: Re-construction of the tennis and pickleball courts at Lucchesi, McNear, and Del Oro Courts and LED lighting upgrades are underway. Estimated completion in June 2021. | Green | 2 | 2 | Estimated Completion of Lucchesi, July 2021. Del Oro, August, McNear, September 2021
151 | Spaces & Places | Improve/Reimagining Parks | Upgrade parks facilities including restroom repairs, new benches, and trash receptacles; lighting improvements including LED sports lighting project at Lucchesi Park. | PARK&REC |  | In Progress | IN PROGRESS: Adopt City standard waste and recycle receptacles and coordinate with Recology to replace existing units throughout city parks and facilities. The remaining items would be considered ongoing with the exception of LED lighting which should be included in a standalone project along with the Lucchesi Turf Replacement. | Red | 3 | 3 | This is a very big program of upgrading the Parks, it will take years to complete, defining the scope and prioritization is key to moving this forward strategically with the limited resources we have for staff resources and funding.
152 | Spaces & Places | Improve/Reimagining Parks | Improve existing trails and park pathways to increase accessibility and promote intergenerational use, including Lynch Creek Trail and Prince Park. | PWU | REC | In Progress | IN PROGRESS: incorporation of trail segments as part of development review process. Improvement of section of Lynch Creek Trail from Payran Bridge to Lynch Creek trail is out to bid. Prince Park trail rehabilitation design complete. | Yellow | 3 | 3 | First phase (LCT from Washington Creek to Lynch Creek) is under construction, but the larger trail-wide improvements project will take additional staff resources. Traffic Impact Fees identified for partial project funding in 22/23; balance of project to complete in out years 24-26 Funding TBD.
153 | Spaces & Places | Improve/Reimagining Parks | Complete improvements for Lynch Creek Trail including lighting, wayfinding, benches, and safety; and promote the trail via map for users and digital promotions (e.g. web, social, advertising). | PWU | EDOG | In Progress | IN PROGRESS: Staff has made significant progress in developing the overall design plan for Lynch Creek Trail (LCT). The first LCT segment to be upgraded will be used to evaluate overall design. The budget for FY22 includes a proposal to invest significantly in upgrading the Lynch Creek Trail. Staff plans to create a trail map and coordinate contracted trail maintenance. | Yellow | 3 | 3 | First phase (LCT from Washington Creek to Lynch Creek) is under construction, but the larger trail-wide improvements project will take additional staff resources. Traffic Impact Fees identified for partial project funding in 22/23; balance of project to complete in out years 24-26 Funding TBD.
154 | Spaces & Places | Improve/Reimagining Parks | Prioritize completion of all phases of the Petaluma Community Sports Field project. | PARK&REC | REC | In Progress | IN PROGRESS: Design has been updated in Spring of 2021 to reflect available funds. | Green | 3 | 3 | Would like to have a roundabout on Washington entrance to the fields but that may be a latter phase for the project (Transit)
155 | Spaces & Places | Improve/Reimagining Parks | Refine proposed trail network and begin guided tours for interim access on Lafferty Ranch; consider incorporation into City. | CMO | CAO | In Progress | IN PROGRESS: pilot program/guided hikes for Petaluma students, Latinx, and other Petaluma community members | Green | 1 | 1 | Guided Tours with Land Paths have begun, and discussions for future hikes are underway. Steps to incorporate Lafferty Ranch have not been initiated
156 | Spaces & Places | Improve/Reimagining Parks | Explore acquisition of parcels adjoining existing parks (e.g. Cavanagh Landing Park, McNear Peninsula) to increase opportunities for public access to the river. | CMO | PWU | In Progress | IN PROGRESS: Initial discussions with property owner adjacent to Cavanagh Landing about potential acquisition. Ongoing discussion with Petaluma River Park non profit to support and partner park development opportunities. | Yellow | 1 | 3 | Staff continues to look for opportunities. Cost and timing will depend on development opportunities, etc. Staff has initiated discussion with both Basin Street and Scannell to acquire riverfront after development of path and passive seating areas along the River.
157 | Spaces & Places | Improve/Reimagining Parks | Work with the community to ensure a balanced program of investments for Measure M—a 10-year, voter-approved 1/8 cent tax measure to support County and city parks and open spaces. | CMO | REC | Ongoing | ONGOING: Current practice is to review investment priorities annually as part of the Commission and Council budget review process. | Ongoing
158 | A City that Works | Engaged, Activated, Connected Community | Engage the community to improve race relations and make recommendations on City and policing policies. | CMO | PD | In Progress | IN PROGRESS: Completed 2 workshops and established a temporary Ad Hoc Community Advisory Committee to help direct staff on how best to move forward and improve race relations in Petaluma. | Green | 1 | 1 | Initial 6 month effort will be complete September. We may need to consider an extension if more time is needed to complete recommendations.
159 | A City that Works | Engaged, Activated, Connected Community | Update the Citywide Records Retention Schedule whereby reducing the City’s exposure and liability and reducing the cost of storing outdated records. | CLERK | CAO | In Progress | IN PROGRESS: Updated retention schedule is set to go to Council for approval in Summer 2021. Staff will be trained and schedule will be implemented in 2022. Auditing and cleaning up off-site records and electronic records will be a momentous project, will require additional staffing to complete. | Green | 1 | 3 | Core staffing position for Records Coordinator is proposed. Upon approval and hiring, Records Coordinator will be tasked with implementing updated schedule and auditing all existing records citywide.
160 | A City that Works | Engaged, Activated, Connected Community | Implement participation in Council, Committee, Commission, and Board meetings through online platforms | EDOG |  | Complete | COMPLETE: Transitioned to Zoom webinars in 2020 due to COVID-19 concerns. Online participation is expected to be ongoing post-COVID restrictions. | Complete
161 | A City that Works | Engaged, Activated, Connected Community | Increase community engagement through programs that attract new followers. Complete Latinx outreach strategy and begin implementing recommendations from the strategy. | EDOG |  | In Progress | IN PROGRESS: Focus group established to meet and discuss best practices for City engagement and communications. A Report identify the best practices will be in complete in late 2021. | Green | 1 | 2
162 | A City that Works | Fiscal & Org Sustainability | Hire a consultant to identify the requirements for a new enterprise management system. Next steps would be to use the identified requirements to issue a meaningful RFP and select a system for future use by the City. | EDOG |  | Not Initiated | NOT INITIATED | Yellow | 2 | 2
163 | A City that Works | Fiscal & Org Sustainability | Review and Finalize five (5) existing city-wide administrative rules. | HR | CAO | In Progress | IN PROGRESS: Policies are drafted. Next steps are taking the policies to the bargaining units. | Green | 1 | 2
164 | A City that Works | Fiscal & Org Sustainability | Maintaining and enhance our commitment to training of professional staff | HR | CAO | Ongoing | ONGOING: Agenda management system upgrade; DEI work with PW&U and Directors to expand citywide; Staff liaison training for Committees and Commissions; Purchasing, Agenda Reports, Resolutions, Ordinances, Public Records, Open Meetings, Management and supervisory training, etc.) | Ongoing
165 | A City that Works | Safe, Sustainable, Smart Infrastructure | Update the City's Urban Water Management Plan and Water Shortage Contingency Plan to reflect City's most current needs, the climate crisis, and expected increase intensity of wet and dry weather. | PWU |  | In Progress | IN PROGRESS: Nearing completion and will be brought to Council in May for Public Hearing, feedback and approval. | Green | 1 | 1
166 | A City that Works | Safe, Sustainable, Smart Infrastructure | Make the City’s Wastewater collection system more resilient, by repairing and replacing damaged sewer mains, and implementing the sewer masterplan. | PWU |  | Ongoing | ONGOING: Sewer main replacements completed with projects at B St., San Carlos, and replacements in the McNear Park Neighborhood are in progress. Sewer system modeling is underway and will feed into Sewer Master Plan Development. | Ongoing |  |  | CIP projects in construction every year to repair and replace mains - that part is ongoing; sewer master plan is longer term but also getting underway now and is Green.
167 | A City that Works | Safe, Sustainable, Smart Infrastructure | Complete a Public Safety Facilities Assessment | PWU |  | In Progress | IN PROGRESS: Staff reviewing prior police facility assessment from 2008 and evaluating potential consultants for consideration. | Green | 2 | 2 | Part of Workplan Item #__
168 | A City that Works | Safe, Sustainable, Smart Infrastructure | Develop a Property Asset Management System to track the status of City owner property, assure that those properties are maintained and managed proactively. | PWU | EDOG | Not Initiated | NOT INITIATED | Red | 1 | 2 | Staff is needed before this task can start.
169 | A City that Works | Safe, Sustainable, Smart Infrastructure | Develop guidelines and policies to reopen city facilities in a way that supports safety and flexibility for city staff. | HR | CMO | In Progress | IN PROGRESS: Staff researching best practices, legal requirements, and facility upgrades--and developing a timeline that provides for a safe reopening for staff & the public | Green | 3 | 2
170 | A City that Works | Safe, Sustainable, Smart Infrastructure | Complete a thorough update of the City's Telecommunications regulations including cell tower rules. | CDD | CAO | In Progress | At early steps of initiating by evaluating existing ordinance, coming up to speed with recent changes in federal law, and bringing on consultant partnership to assist staff | Green | 1 | 2 | Initial scope being developed with consultant
171 | A City that Works | Safe, Sustainable, Smart Infrastructure | Complete a thorough review and update of Wastewater and Water regulations, benchmarking with other municipalities and agencies, reviewing latest state requirements and codes to verify City's regulations are not in conflict and provide an equitable application of requirements on businesses and residents while providing safeguards for the utility systems. | PWU | CAO | In Progress | IN PROGRESS: Initiated contracted review of municipal code requirements for wastewater and storm water regulations. | Green | 1 | 2
172 | A City that Works | Safe, Sustainable, Smart Infrastructure | Complete identified CIP Program projects: D St. Bridge emergency repairs; Runway Electrical lighting upgrades; Denman Reach Flood Mitigation Project completion; Water Service repair project; Petaluma Boulevard South Water main replacement; McNear Park Neighborhood water and waste water replacement; Country Club and Victoria water pump station upgrades | PWU |  | Complete | COMPLETE | Complete
173 | A City that Works | Safe, Sustainable, Smart Infrastructure | Install voter ballot boxes at City facilities. | PWU | CAO | Complete | COMPLETE | Complete
174 | A City that Works | Safe, Sustainable, Smart Infrastructure | Complete 2022 Utility Rate Study to ensure rates support sustainable and resilient water distribution, wastewater collection and treatment, and recycled water systems | PWU | FIN | In Progress | IN PROGRESS: Consultant contract authorized to award. Included in the scope is tasks to explore a Customer Assistance program and an alternative rate structure that could be used during a prolonged drought. | Green | 1 | 2
175 | A City that Works | Technology, Org Effectiveness | Research phone systems with the goal of implementing an efficient system that allows for mobility among staff. | EDOG |  | In Progress | IN PROGRESS: Staff reviewing options for new phone systems that maximize flexibility and mobility. | Yellow | 1 | 1 | This needs budget to move forward.
176 | A City that Works | Technology, Org Effectiveness | Procured and implemented FPPC Campaign Statement and Statement of Economic Interest filing software through which filers and treasurers can more easily file statements in a timely manner without error, reducing liability for both filers and the City | CLERK |  | Complete | COMPLETE | Complete
177 | A City that Works | Technology, Org Effectiveness | Procure board management software to streamline the application and appointment process, increase community engagement, and to track ethics and anti-harassment training, for City committees, commissions, and boards. | CLERK | EDOG | In Progress | IN PROGRESS: Procured software. Will implement in calendar year 2021. | Green | 1 | 1 | Contract was signed in May 2021. Implementation will take less than six months.
178 | A City that Works | Technology, Org Effectiveness | Reconstitute a cohesive Community Development Department | CMO | CDD | In Progress | IN PROGRESS: Reconstitute a cohesive Community Development Department to include Planning, Building, Housing, and Code Enforcement to ensure implementation of community vision and process improvements to better serve Petaluma. | Green | 2 | 2
179 | A Safe Community | Safety & Emergency Prep | Complete needed facility upgrades to meet safety standards regarding COVID-19. | PWU | CMO | In Progress | IN PROGRESS: Upgrades to counters to establish transparent barriers between staff and the public have been installed. Other upgrades to restrooms, ventilation systems, and office configurations are underway. | Green | 3 | 2
180 | A Safe Community | Safety & Emergency Prep | Provide safety support and shelter during two significant fires in County, concurrent with COVID-19. | FIRE |  | Complete | COMPLETE | Complete
181 | A Safe Community | Safety & Emergency Prep | Establish a CAHOOTS program. | CMO | PD | Complete | COMPLETE: Assessment nearing completion; svc provider contract to Council on May 3 | Complete
182 | A Safe Community | Safety & Emergency Prep | Complete an updated Local Hazard Mitigation Plan | PWU |  | Complete | COMPLETE | Complete
183 | A Safe Community | Safety & Emergency Prep | Complete a thorough update of City Certified Unified Program Agency (CUPA) regulations. | FIRE | CAO | Not Initiated | NOT INITIATED | Yellow | 1 | 3 | Pending hire of Deputy Fire Marshal
184 | Economy that Prospers | Biz Attraction / Retention | Establish a Free Range, outdoor dining program that allows merchants impacted by the Covid Shelter in Place regulations to operate their business outdoors. | EDOG | PWU | Complete | COMPLETE: Issued 60 outdoor permits and provided tents to 50 businesses. Also reviewed and approved 2 parklets paid for by an art grant. | Complete
185 | Economy that Prospers | Biz Attraction / Retention | Reach out to individual businesses to determine how Covid shutdowns are affecting them and to see how staff could support them. | EDOG |  | Complete | COMPLETE | Complete
186 | Economy that Prospers | Biz Attraction / Retention | Work with local businesses who need support during COVID recovery. | EDOG |  | In Progress | IN PROGRESS: teed up footprint expansion via Free Range Program, kicked off shop local campaign with Shop Petaluma website and gift card | Green | 1 | 1
187 | Economy that Prospers | Biz Attraction / Retention | Develop a ShopPetaluma website, supported with marketing and a dedicated gift card program. | EDOG |  | Complete | COMPLETE | Complete
188 | Economy that Prospers | Biz Attraction / Retention | Develop and issue loans to businesses to support their cashflow needs during COVID Stay at Home regulations. | FIN |  | Complete | COMPLETE | Complete
189 | Environmental Legacy | Climate Ready | Impose a temporary emergency moratorium on all riparian, vernal pool/wet meadow, wetland, and floodplain development until the General Plan EIR is completed and the City has prepared and adopted a Climate Adaptation and Resilience Plan as recommended by the CEF. | CDD | CAO | Not Initiated | NOT INITIATED: Need to examining how this can be legally accomplished given the letter from the State on this subject. | Yellow |  |  | Concerns with moratorium that impacts housing development based on SB 330 and HE consistency. With appropriate resources can explore different options based on assumed intent of the task description. Will also be a significant part of the discussion of the GP and HE update
190 | Environmental Legacy | Climate Ready | Make permanent the moratorium on new gas stations and develop a plan for building out publicly available EV charging infrastructure and capacity to meet projected needs. | CDD | CMO | Complete | COMPLETE: Mortarium on new gas stations was made permanent through Council ordinance. Additional EV charging infrastructure is continuously added, City is prioritizing fleet electrification and supporting infrastructure | Complete
191 | Environmental Legacy | Climate Ready | Develop an initial outreach and engagement plan that the city funds as part of resourcing and educating Petalumans, including outreach campaigns and events to increase knowledge of energy efficiency and building electrification benefits and ensure that local energy providers or businesses that sell home energy equipment provide up-to-date and climate-smart options | CMO | EDOG | In Progress | IN PROGRESS: Climate Ready Petaluma 2030 initiative underway, with the webpage active. Climate Action Commission ad hoc subcommittee established to assist staff with initiative development. | Green | 1 | 1 | This would largely involved compiling existing resources and programs offered by other agencies with regular updates to incorporate new tasks. Climate Action Coordinator/Manager task
192 | Environmental Legacy | Climate Ready | Ensure equitable new development, including affordable housing and shelters, by revising the General Plan, building and development codes, and other relevant City policies to apply climate-action equity priorities fairly across the board. | CDD | CMO | In Progress | IN PROGRESS: General Plan update underway, which prioritizes equity and climate/environmental justice. | Green | 3 | 3 | Through the GP update equity will be a lens under which all policies are evaluated. While the GP update is a longer term project with adoption anticipated in late 2022/2023, staff will continue to facilitate equity considerations in all code updates
193 | Environmental Legacy | Climate Ready | Identify funds to support Storm Water program and infrastructure | PWU | FIN | In Progress | IN PROGRESS: Staff is looking to review current municipal code, design standards, building code, and state requirements and identify options for revenue to support the storm water program administration, infrastructure maintenance, and capital improvements. | Green | 1 | 2
194 | Environmental Legacy | Climate Ready | Adopt a VMT policy that is consistent with the 2030 carbon neutrality goal. In order to meet these targets, prepare policy recommendations for rapidly implementing alternative clean, safe, accessible, and affordable and active and public transportation modes to meet the rising community need for climate-friendly transportation. | CDD | PWU | In Progress | IN PROGRESS: Vehicle Miles Travelled Technical Advisory Committee is meeting, and it is expected that recommendations will be sent to Council in Fiscal Year 2022. Need work to establish VMT baseline in order to be able to measure progress over time. | Green | 1 | 1 | The first step in creating a robust VMT program is the adoption of implementation guidelines for CEQA, which is scheduled for CC adoption on 6/21. Additional work will then be initiated to look at city wide mitigation options both in the short term and as part of the GP update. Need to have a stronger understanding of current City VMT to create baseline for future analysis.
195 | Environmental Legacy | Climate Ready | Enact a prohibition on new gas stations throughout the City. | CDD |  | Complete | COMPLETE | Complete
196 | Environmental Legacy | Climate Ready | Update the City's Integrated Pest Management Plan and formalize a policy of how the City maintains its parks, trails, open spaces, streetscape, creeks, landscape assessment districts, and other City’s properties in a more sustainable way that is better for the environment, the community, and the health of the public and staff. | PARK&REC | CMO | In Progress | IN PROGRESS: The City has continued to build better landscape management practices, over the past many months staff attended pesticide-free workshops, continued to reduce the use of pesticides in parks and public spaces, continued the policy of not using glyphosate containing products in public spaces, built and installed more owl boxes at parks, routinely mulched for weed control, and reviewed the recently updated integrated pest management plans of other local agencies to include City of Windsor, City of Rohnert Park, City of Santa Rosa, Sonoma Water, Petaluma City School District, and Marin County Parks. Through In order to develop a comprehensive and progressive IPMP that considers the needs of the City for landscaping and pest management the assistance of an expert consultant is needed. In benchmarking with other agencies a consultant was identified with 30 years experience in the development of IPMP with agencies in the Bay Area. A scope of work has been developed and negotiated and staff is seeking authorization to award a contract for these services. | Green | 1 | 2
197 | Environmental Legacy | Climate Ready | Inform and invite local California Native peoples into our ongoing dialogue as part of cultivating respectful and collaborative relationships with indigenous communities with the intention to understand, highlight, and integrate their community needs, climate action priorities, and ecological insight and values into our climate actions | CMO |  | In Progress | IN PROGRESS: Outreach regarding CEQA and AB 52 related to major development projects are referred to the Federated Indians of Graton Rancheria is standard operating procedure. Additional outreach for future projects and programs is in development. | Green | 1 | 3 | Of particular note is staff's ongoing collaboration with FIGR re Cedar Grove as discussed under a separate task.
198 | Environmental Legacy | Climate Ready | Adopt 2030 as the City's target for carbon neutrality | CMO |  | Complete | COMPLETE: Adopted Climate Emergency Framework on January 11, 2021, which set carbon neutrality by 2030 as a goal | Complete
199 | Environmental Legacy | Climate Ready | Adopt the Climate Emergency Framework (CEF) and use it as a guide for city department planning, budgeting, procurement and other activities. City Departments should align actions with the attainment of the framework’s climate goals and performance against those goals should be reviewed annually as part of determining departmental performance. | CMO |  | Ongoing | ONGOING: Climate Emergency Framework adopted. Framework is a priority and departments are adapting to its goals. Continuous improvement and alignment with Framework goals will be ongoing | Ongoing
200 | Environmental Legacy | Climate Ready | Use the Climate Emergency Framework as a foundation for the new General Plan update, including all guiding principles. | CDD | CMO | In Progress | IN PROGRESS: Climate Emergency Framework was included as a guiding document in the RFP for the General Plan update consultant, and is referenced throughout the consultant's scope of work | Green | 3 | 3 | Ongoing as part of GP update.
201 | Environmental Legacy | Climate Ready | Integrate climate action, environmental justice and public health improvements throughout the General Plan document and include elements and/or extensive discussion (including community and expert discussion) and metrics for Environmental Justice, Climate and Healthy Communities so that all planning and land use related CEF goals and objectives are fully developed and embodied in the General Plan. As part of the General Plan process develop and adopt a Climate Action Plan that contains the actions the City shall take and ask the community to undertake over the life of the General Plan towards meeting the CEF goals. Ensure equitable new development by revising building and development codes, and other relevant City policies to apply climate-action equity priorities fairly across the board concurrently or in advance of the General Plan update process. | CDD | CMO | In Progress | IN PROGRESS: General Plan update process has been initiated, GPAC was formed (whose feedback will be incorporated into the General Plan), Climate Action Commission will provide feedback to incorporate these goals into the General Plan and Climate Action and Adaption Plan developed by consultant | Green | 3 | 3 | Ongoing as part of GP update
202 | Environmental Legacy | Climate Ready | Develop a plan and timeline to source 100% renewable energy for use in City facilities, and advocate and work with regional partners to ensure 100% clean renewable power for all City residents in order to meet Petaluma’s 2030 carbon neutrality target | CMO |  | Complete | COMPLETE: City will switch to EverGreen 100% renewable energy July 2021. City will examine feasibility of energy efficiency upgrades and on-site renewable generation to reduce cost | Complete
203 | Environmental Legacy | Climate Ready | Impose a moratorium on City purchases of fossil fuel powered vehicles, power equipment, and appliances, with limited exceptions for emergency vehicles and equipment where no low climate pollution causing alternatives are reasonably available. | CMO |  | In Progress | IN PROGRESS: Staff is developing an electrification and supporting infrastructure plan for city facilities. Fossil fuel equipment is effectively on hold due to City Council action | Green | 1 | 1 | Development of a Fleet Policy would memorialize this and will be recommended as part of the June 21 fleet presentation to Council
204 | Environmental Legacy | Climate Ready | Evaluate the process to divest from all fossil-fuel investments including pension funds and the costs/benefits of developing a new carbon neutral and green economy investment portfolio. | FIN | CMO | In Progress | IN PROGRESS: Staff has sent a Council resolution to CalPERS requesting the option to place Petaluma CalPERS funds into high-performing Environmental, Social, and Corporate Governance (ESG) portfolios, and allowing other municipalities to do the same. Staff is examining whether any of local City investment portfolios benefit fossil fuel industries | Green |  | 3 | This work can begin once a climate action manager is hired.
205 | Environmental Legacy | Climate Ready | Adopt a resolution requiring all individual departments to report fossil fuel purchasing separately and setting annual fossil fuel budget reductions of 10% for every city department based on the base year of 2020. | CMO | All | Not Initiated | NOT INITIATED | Yellow | 1 | 2 | Initial inventory of fossil fuel purchases by department was included in the FY 22 Budget. Determining the feasibility of a 10% reduction per year requires additional analysis.
206 | Environmental Legacy | Climate Ready | Develop an assessment of climate change impacts by neighborhood and demographic group to assess where and for whom environmental justice and equity work needs to be focused. | CDD | CMO | Not Initiated | NOT INITIATED: Some studies have been scoped (e.g. sea level rise, local hazard mitigation plan, fire hazard studies), but a comprehensive, neighborhood-level plan has not yet been initiated. This effort will be part of the General Plan / Climate Action and Adaptation Plan process. | Green | 1 | 2
207 | Environmental Legacy | Climate Ready | Adopt a natural gas ban for new construction and adopt a policy to phase in building energy retrofits for existing buildings to meet climate targets. Provide resources and programs to ensure retrofits are available and affordable to low income residents and do not cause rent increases for tenants over and above monthly savings on utility bills from the upgrades and include tenant protections to avoid displacement and eviction. | CDD |  | In Progress | IN PROGRESS: All electric for new construction expected to be considered by City Council on May 3, 2021. Resources and education about decarbonizing existing buildings are expected to become a larger focus in FY 2022. | Green | 1 | 3 | The code has been adopted. Staff efforts will now need to shift to education and resources.
208 | Spaces & Places | Climate Ready | Complete a Greenhouse Gas Inventory Assessment for parks maintenance to establish a baseline assessment of city facilities and adopt best practices for future maintenance. | PARK&REC | PW&U | Not Initiated | NOT INITIATED | Green | 1 | 1
209 | Spaces & Places | Improve/Reimagining Parks | Open the Paula Lane Nature Preserve to the public, including agricultural demonstration activities, trails, interpretive signage, and educational research | PARK&REC | REC | In Progress | IN PROGRESS: In partnership with Daily Acts, the Sonoma County Resource Conservation District, and the University of California Cooperative Extension, the City has made progress on all milestones required by the Matching Grant Program with the Open Space District. Staff expects the preserve will be open to the public with all objectives complete in 2021. | Green | 1 | 1 | All milestones are expected to be completed by December 2021.
210 | Spaces & Places | Inspirational Spaces/Public Art | Identify location, select artists, and safely install a Black Lives Matter Mural. | CDD | PWU | Complete | COMPLETE | Complete
211 | Spaces & Places | Safe, Vibrant Neighborhoods | Establish a Slow Streets program that creates safe spaces for pedestrians and outdoor recreation. | PWU |  | In Progress | IN PROGRESS: Established Slow Streets with community feedback and support. | Yellow | 1 | 2 | Need to identify transition out of Slow Streets program to permanent traffic calming, pedestrian, and bike safety infrastructure.
212 | Spaces & Places | Safe, Vibrant Neighborhoods | Parklets - create a permanent parklet program that includes clear guidelines on how parklets can be installed in Petaluma's public right of way areas. | EDOG | CDD | In Progress | IN PROGRESS: Technical guidelines are drafted. Next steps include reviewing other City programs, conducting community outreach for input and the drafting comprehensive guidelines to assure parklets maximize public benefit, support the Downtown aesthetic, and are safe. | Green | 1 | 2 | Staff has developed draft guidelines for safety. Design review and parking considerations need to be addressed. Additional legal review may push project beyond FY 21-22.
213 | Spaces & Places | Safe, Vibrant Neighborhoods | Objective Design Standards | CDD |  | In Progress | IN PROGRESS: Preparation of Objective Design Standards for housing projects governed by state streamlining initiatives. | Green | 1 | 2 | In process. PC study session was held in May 2021. Initial outreach completed. Drafting guidelines for further outreach and ultimate adoption.
214 | Spaces & Places | Improve/Reimagining Parks | Cedar Grove Park and Open Space | CDD |  | In Progress | IN PROGRESS: Continue to collaborate with representatives of the Federated Indians of Graton Rancheria and other outside agency partners to explore creation of passive recreation and open space area. | Green | 3 | 3 | Continued collaboration with FIGR, Sonoma County Land Trust, and So Co Open Space District to acquire and program passive park space
215 | A City that Works | Safe, Sustainable, Smart Infrastructure | Update the Transit vision for the City including reviewing transit service levels, alternative delivery models, reducing barriers to use, and increasing ridership | PWU |  | In Progress | IN PROGRESS: Short Range Transit Plan is underway but hit COVID delays. Plan will address all noted topics and include community outreach and feedback opportunities. | Yellow | 1 | 2 | Additional staffing/consultant resources needed to advance.
216 | A City that Works | Safe, Sustainable, Smart Infrastructure | Establish and staff an Ad Hoc Committee on Active Transportation | PWU | Transit | Not Initiated | Staff's strong recommendation is not to layer the support of another committee onto staff's workload, but to utilize the Pedestrian and Bicycle Advisory Committee or an adhoc of this committee to support this initiative. | Red | 1 | 3
217 | A City that Works | Safe, Sustainable, Smart Infrastructure | Establish metrics to review who receives services with the goal of increasing services to underserved populations. | CMO | CDD | Not Initiated | Equity Index (General Plan) | Green | 2 | 3 | This will be incorporated into the General Plan
218 | A City that Works | Safe, Sustainable, Smart Infrastructure | Look at ways / locations to increase river footbridges | PWU | CDD | Not Initiated |  | Red |  |  | Need Clarification if this is building new foot bridges and/or maintaining existing. For the latter, CIP for FY21/22 has an assessment and some initial funding for projects. For the former, the Petaluma River Access and Enhancement Plan is being followed, maybe an update with General Plan update to guide new foot/bike bridges.
219 | Economy that Prospers | Biz Attraction / Retention | Develop marketing materials and incentives to encourage re-tenanting of downtown storefronts | EDOG |  | Not Initiated | NOT INITIATED | Yellow | 1 | 1 | Additional staffing/consultant resources needed to advance.
220 | Economy that Prospers | Biz Attraction / Retention | Develop a Business Plan for ShopPetaluma to track impressions and transactions related to the program. | EDOG |  | Not Initiated | NOT INITIATED | Yellow | 1 | 1 | Additional staffing/consultant resources needed to advance.
221 | Economy that Prospers | Biz Attraction / Retention | Revisit Cannabis Ordinance and consider storefront options | EDOG |  | Not Initiated | NOT INITIATED | Green | 1 | 2 | Additional staffing/consultant resources needed to advance.
222 | Environmental Legacy | Climate Ready | Adopt a new wetlands policy aimed at restoration vs. mitigation | PWU | CDD | Not Initiated |  | Yellow | 3 | 3 | Need some clarification on what is being sought here. I think it's more focus on restoration, while continuing mitigating impacts on wetlands from all our human activities and development as required.
223 | Environmental Legacy | Climate Ready | Changes to tree ordinance to support sequestration | CDD | CMO | Not Initiated |  | Yellow | 1 | 3
224 | Spaces & Places | Improve/Reimagining Parks | Develop a scope and plan to initiate a vision for City parks and open space for Council consideration. | REC | PWU | Not Initiated |  | Green | 2 | 2
225 | Spaces & Places | Improve/Reimagining Parks | Execute contract for skatepark community outreach and complete re-design. | PARK&REC | PWU | In Progress | Design is in FY 21/22 budget | Green | 2 | 2
226 | Spaces & Places | Improve/Reimagining Parks | Revitalize McNear grandstand, lights, softball & baseball fields | REC | PWU | Not Initiated | Not initiated. Need to confirm that this should go into our CIP program. | Red | 3 | 3 | Is this a priority or not? Staff likes the idea, but there has been neighborhood pushback on the lights in particular in the past.
227 | Spaces & Places | Connections to History & Each other | Look at ways to increase / improve place making on the East side. | CDD | EDOG | Not Initiated | What does this look like? General Plan… Active Transportation ?? | Yellow | 2 | 3
228 | Spaces & Places | Improve/Reimagining Parks | Look into creating a Parks Foundation | CMO | REC | Not Initiated |  | Yellow | 1 | 3
229 | Spaces & Places | Safe, Vibrant Neighborhoods | Gas Powered Leaf Blower Ban | CMO | CAO | Not Initiated |  | Yellow | 1 | 2
230 | Spaces and Places | Safe, Vibrant Neighborhoods | Develop a formula retail ordinance to regulate chain businesses in downtown core to preserve historic character and design | CDD | CAO | In Progress | Staff has developed initial ordinance outline | Yellow | 1 | 2 | Initial ordinance drafted. Internal review and community outreach needed before PC and CC consideration. There are potential constitutional issues with formula retail regulations under the Commerce Clause that need to be avoided. Legal research and review will require additional time to complete.
231 | A City that Works | Fiscal & Org Sustainability | Develop activities and events to promote teamwork, collaborative relationships, celebrating staff successes and City of Petaluma years of service to rebuild in-person workplace culture. | HR |  | Not Initiated | NOT INITIATED | Green | 1 | 2
232 | An Economy that Prospers | Biz Attraction / Retention | Develop a workforce development program aimed at attracting, training, and retaining green jobs. | EDOG |  | Not Initiated | NOT INITIATED | Yellow | 1 | 2 | Additional staff will be needed to begin this project.
233 | A City that Works | Fiscal & Org Sustainability | Update City's purchasing ordinance and policies | CMO | CAO | Not Initiated | NOT INITIATED | Green | 1 | 2
234 | A City that Works | Fiscal & Org Sustainability | Develop new citywide administrative rules/policies and/or safety administration rules as require by legal mandates. |  |  | Ongoing |  | Ongoing
235 | A Safe Community | Diverse & Affordable Housing | Just Cause, Ellis Act Imlementation | CAO |  | Not Initiated |  | Green | 1 | 2