## Sheet0
Resource Plan
Project Name: | Project Atlas
Period: | Q2 2030
Lead: | Zola Bekker
Name | Role | Task | Duration |  | Assigned Hours |  |  |  |  | Capacity (Hours) | Utilization % | Status | Notes
|  |  | Start | End | Week 1 | Week 2 | Week 3 | Week 4 | Total
Asher | UI Designer | Website redesign | 2030-06-01 | 2030-07-01 | 20 | 25 | 15 | 10 | 70 | 160 | 43.75% | Balanced | Front-end visuals
Jesse | Developer | API integration | 2030-06-01 | 2030-07-01 | 35 | 40 | 38 | 32 | 145 | 160 | 90.62% | Overloaded | Needs support Week 2–3
Isla | QA Engineer | Test suite | 2030-06-01 | 2030-07-01 | 15 | 18 | 20 | 22 | 75 | 160 | 46.88% | Underutilized | Can help dev team
Lana | Product Manager | Project coordination | 2030-06-01 | 2030-07-01 | 25 | 25 | 25 | 25 | 100 | 160 | 62.5% | Balanced | Meetings + planning
Rain | Data Analyst | Reporting | 2030-06-01 | 2030-07-01 | 10 | 12 | 15 | 18 | 55 | 160 | 34.38% | Underutilized | Assign to extra analysis
Add name here | Add role here | Add task here |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Add status here | Add notes here.
|  |  |  | TOTAL | 105 | 120 | 113 | 107 | 445 | 800