## Sheet0
Weekly Task Tracker
Project Name: | Mosaic Campaign |  | Lead: | Margo Sleet
Team: | Core Team |  | Week of: | June 3
Day | Category | Task | Status | Due Date | Assigned To | Estimated Hours | Actual Hours | Blockers
Monday
| Admin | Finalize contractor payment list | Done | June 3 | Kiana Nadar | 2 | 4 | Waiting for updated invoice
| Marketing | Prepare social media content plan for the week | Done | June 4 | Edith Fernsby | 3 | 3 | Needs approval from manager
| Content | Draft landing page copy | In Progress | June 4 | Job Park | 4 |  | Brief updated this morning
Tuesday
| Marketing | Research competitor ads | Not Started | June 5 | Edith Fernsby | 4 |  | Missing data
| Content | Write blog content for the website | Not Started | June 5 | Job Park | 5 |  | Needs topic confirmation
| Design | Create visual mockups for homepage banner | Not Started | June 6 | Ade Mabasa | 5 |  | Waiting for copy draft
Wednesday
|  | Add more as needed. | Not Started | June 7 | Name here | 0 | 0 | Add blockers here.